## Options GW and Hyd
| RFF | [5 empty] | Option details | [7 empty] | Partnership | [9 empty] | Time scale
1 | WB ID | Name | HMWB | Improve or No deterioration | Stage 3 investigation associated with option (Element) | RFF ID (pressure/SWMI) | RBMP measure ID | Action to be written by (e.g. Fisheries) | Action description | Action type 1 | Action type 2 | Action type 3 | NGR (u/s, d/s or centre) | Length or river improved | Lead sector | Name of Organisation | Potential partners | Total cost | Funded or unfunded | Predicted improvement | Certainty (VC, QC, UC) | Eco benefit for HMWB | Is this part of a project? Project REF | Funding stream | Length of time to implement action | Planned start | Planned end | Is this a catchment wide solution | Climate change scenario (current, wet, dry, any) | Additional notes
19 | 17079 | Loddon (Basingstoke to Lyde) | yes | Improve | Hydrology | Flow/groundwater abstraction |  | Groundwater Hydrology | limit development at Basingstoke | To control or manage abstraction | Water Demand Management | Water efficiency activity |  |  |  |  | Council, residents, water companies, developers |  | Unfunded | Contribute to improvement of 1+ element | VC | [6 empty] | no | any
20 | 17080 | Loddon (Basingstoke to Lyde) | yes | Improve | Hydrology | Flow/groundwater abstraction |  | Groundwater Hydrology | Reduce pumping at West Ham, find alternative source. | To control or manage abstraction | Water Demand Management | Water efficiency activity |  |  |  |  | Council, residents, water companies, developers |  | Unfunded | Contribute to improvement of 1+ element | VC | [6 empty] | no | any
21 | 17080 | Loddon (Basingstoke to Lyde) | yes | Improve | Hydrology | Flow/groundwater abstraction |  | Groundwater A&R F&B | Investigat the effects of West Ham on the ecology of the River Loddon between the abstraction points and the discharge outlet of Basingstoke STW | To control or manage abstraction | Use alternative source/relocate abstraction or discharge | Change abstraction location |  |  |  |  | Council, residents, water companies, developers |  | Unfunded | No deterioration | VC | [6 empty] | no | any
22 | 17080 | Loddon (Basingstoke to Lyde) | yes | Improve | Hydrology | Flow/groundwater abstraction |  | Groundwater A&R F&B | Investigat the effects of West Ham on the ecology of the Lower Bow Brook between the abstraction points and the discharge outlet of Basingstoke STW | To control or manage abstraction | Use alternative source/relocate abstraction or discharge | Change abstraction location |  |  |  |  | Council, residents, water companies, developers | 50000 | Unfunded | No deterioration | VC | [6 empty] | no | any
22 | 17080 | Loddon (Basingstoke to Lyde) | yes | Improve | Hydrology | Flow/groundwater abstraction |  |  | Dual water supply system to new housing and potentiall old housing in Basingstoke (grey water and potable water) to reduce abstraction and volumes of water going through STW. | To control or manage abstraction | Use alternative source/relocate abstraction or discharge | Change abstraction location |  |  |  |  | Council, residents, water companies, developers |  | Unfunded | Contribute to improvement of 1+ element | VC | [6 empty] | no | any
23 | 17080 | Loddon (Basingstoke to Lyde) | yes | Improve | Hydrology | Flow/groundwater abstraction |  | Groundwater A&R F&B | Investigat the effects of West Ham on the ecology of the Vyne Stream between the abstraction points and the discharge outlet of Basingstoke STW | To control or manage abstraction | Use alternative source/relocate abstraction or discharge | Change abstraction location |  |  |  |  | Council, residents, water companies, developers | 50000 | Unfunded | No deterioration | VC | [6 empty] | no | any
23 | 17080 | Loddon (Basingstoke to Lyde) | yes | Improve | Hydrology | Flow/groundwater abstraction |  | EM | Water company led water efficiency campaign | To control or manage abstraction | Water Demand Management | Water efficiency activity |  |  |  |  | Council, residents, water companies, developers | 1000 | Unfunded | No deterioration | UC | [6 empty] | no | any
23 | 17080 | Loddon (Basingstoke to Lyde) | yes | Improve | Hydrology | Flow/groundwater abstraction |  | EM | Run a targetted water efficiency campaign for all licensed abstractors in a waterbody. | To control or manage abstraction | Water Demand Management | Water efficiency activity |  |  |  |  | Council, residents, water companies, developers | 1000 | Unfunded | No deterioration | UC | [6 empty] | no | any
23 | 17080 | Loddon (Basingstoke to Lyde) | yes | Improve | Hydrology | Flow/groundwater abstraction |  | Groundwater Hydrology | Effluent re-use, duel water use. | To control or manage abstraction | Use alternative source/relocate abstraction or discharge | Water efficiency activity |  |  |  |  | Council, residents, water companies, developers |  | Unfunded | Contribute to improvement of 1+ element | VC | [6 empty] | no | any
31 | 17090 | Hart (Crondal to Elvetham) | no | Improve | Hydrology | flow/grounwater abstraction |  | Hydrology Groundwater | Reduce abstraction impact by 3 Ml/d if further investigation indicates need | To control or manage abstraction | Water Demand Management | Water efficiency activity |  |  |  |  | Council, residents, water companies, developers |  | Unfunded | Contribute to improvement of 1+ element | VC | [6 empty] | no | any
36 | 17090 | Hart (Crondal to Elvetham) | no | Improve | Fish | Hydrology, natural conditions - low flow |  | Hydrology | Investigate Boxalls Lane, Oak Park Golf Club and Itchell puming station effect on biology. | To control or manage abstraction | Water Demand Management | Water efficiency activity |  |  |  |  | Council, residents, water companies, developers |  | Unfunded | Contribute to improvement of 1+ element | VC | [6 empty] | no | any
36 | 17090 | Hart (Crondal to Elvetham) | no | Improve | Fish | Hydrology, natural conditions - low flow |  | EM | Water company led water efficiency campaign | To control or manage abstraction | Water Demand Management | Water efficiency activity |  |  |  |  | Council, residents, water companies, developers | 1000 | Unfunded | No deterioration | UC | [6 empty] | no | any
36 | 17090 | Hart (Crondal to Elvetham) | no | Improve | Fish | Hydrology, natural conditions - low flow |  | EM | Run a targetted water efficiency campaign for all licensed abstractors in a waterbody. | To control or manage abstraction | Water Demand Management | Water efficiency activity |  |  |  |  | Council, residents, water companies, developers | 1000 | Unfunded | No deterioration | UC | [6 empty] | no | any
36 | 17090 | Hart (Crondal to Elvetham) | no | Improve | Fish | Hydrology, natural conditions - low flow |  | Groundwater Hydrology | Effluent re-use, uel water use. | To control or manage abstraction | Use alternative source/relocate abstraction or discharge | Water efficiency activity |  |  |  |  | Council, residents, water companies, developers |  | Unfunded | Contribute to improvement of 1+ element | VC | [6 empty] | no | any
9*

## Options EM
| RFF | [5 empty] | Option details | [7 empty] | Partnership | [9 empty] | Time scale
1 | WB ID | Name | HMWB | Improve or No deterioration | Stage 3 investigation associated with option (Element) | RFF ID (pressure/SWMI) | RBMP measure ID | Action to be written by (e.g. Fisheries) | Action description | Action type 1 | Action type 2 | Action type 3 | NGR (u/s, d/s or centre) | Length or river improved | Lead sector | Name of Organisation | Potential partners | Total cost | Funded or unfunded | Predicted improvement | Certainty (VC, QC, UC) | Eco benefit for HMWB | Is this part of a project? Project REF | Funding stream | Length of time to implement action | Planned start | Planned end | Is this a catchment wide solution | Climate change scenario (current, wet, dry, any) | Additional notes
24 | 17090 | Hart (Crondal to Elvetham) | no | Improve | Fish | Sediment/agricultural run off |  | EM | Use the Catchment Sensitive Farming initative to raise awareness and reduce pesticide\phosphate\sediment pollution in this waterbody. | To control or manage diffuse source inputs | Reduce diffuse pollution at source | Field & Crop - Arable soils |  |  |  |  | EA, WLT, NFU , TW, UCL,KCL, RU, |  | unfunded | Contribute to improvement to 1+ element. | UC | [6 empty] | Yes | any
24 | 17090 | Hart (Crondal to Elvetham) | no | Improve | Fish | Sediment/agricultural run off |  | EM | Run an awareness campaign through on-farm demonstrations and undertake individual advisory farm visits on high risk farms, to reduce the amount of sediment, nutrients and chemicals entering a waterbody from farmland. Educate the farming | To control or manage diffuse source inputs | Reduce diffuse pollution at source | Field & Crop - Arable soils |  |  |  |  | EA, WLT, NFU , TW, UCL,KCL, RU, |  | unfunded | Contribute to improvement to 1+ element. | UC | [6 empty] | Yes | any
24 | 17090 | Hart (Crondal to Elvetham) | no | Improve | Fish | Sediment/agricultural run off |  | EM | Creation of buffer strips to reduce land run off | To control or manage diffuse source inputs | Reduce diffuse pollution pathways (i.e. control entry to water environment) | Riparian management |  |  |  |  | EA, WLT, NFU , TW, UCL,KCL, RU, |  | unfunded | Contribute to improvement to 1+ element. | UC | [6 empty] | Yes | any
46 | 17090 | Hart (Crondal to Elvetham) | no | Improve | Phosphate | Unknown |  | EM | Fencing to reduce cattle poaching and sediments carrying hosphates efrom entering the river. | To control or manage diffuse source inputs | Reduce diffuse pollution pathways (i.e. control entry to water environment) | Field & Crop - Livestock |  |  |  |  | EA, WLT, NFU , TW, UCL,KCL, RU, |  | unfunded | Contribute to improvement to 1+ element. | UC | [6 empty] | Yes | any
46 | 17090 | Hart (Crondal to Elvetham) | no | Improve | Phosphate | Unknown |  | EM | Creation of buffer strips to reduce sediments carrying hosphates efrom entering the river. | To control or manage diffuse source inputs | Reduce diffuse pollution pathways (i.e. control entry to water environment) | Riparian management |  |  |  |  | EA, WLT, NFU , TW, UCL,KCL, RU, |  | unfunded | Contribute to improvement to 1+ element. | UC | [6 empty] | Yes | any
46 | 17090 | Hart (Crondal to Elvetham) | no | Improve | Phosphate | Unknown |  | EM | Use the Catchment Sensitive Farming initative to raise awareness and reduce pesticide\phosphate\sediment pollution in this waterbody. | To control or manage diffuse source inputs | Reduce diffuse pollution at source | Field & Crop - Arable soils |  |  |  |  | EA, WLT, NFU , TW, UCL,KCL, RU, |  | unfunded | Contribute to improvement to 1+ element. | UC | [6 empty] | Yes | any
48 | 17110 | Vyne Stream | yes | Improve | Phosphate | Diffuse/agriculture |  | EM | Fencing to reduce cattle poaching and sediments carrying hosphates efrom entering the river. | To control or manage diffuse source inputs | Reduce diffuse pollution pathways (i.e. control entry to water environment) | Field & Crop - Livestock |  |  |  |  | EA, WLT, NFU , TW, UCL,KCL, RU, |  | unfunded | Contribute to improvement to 1+ element. | UC | [6 empty] | Yes | any
48 | 17110 | Vyne Stream | yes | Improve | Phosphate | Diffuse/agriculture |  | EM | Use the Catchment Sensitive Farming initative to raise awareness and reduce pesticide\phosphate\sediment pollution in this waterbody. | To control or manage diffuse source inputs | Reduce diffuse pollution at source | Field & Crop - Arable soils |  |  |  |  | EA, WLT, NFU , TW, UCL,KCL, RU, |  | unfunded | Contribute to improvement to 1+ element. | UC | [6 empty] | Yes | any
48 | 17110 | Vyne Stream | yes | Improve | Phosphate | Diffuse/agriculture |  | EM | Run an awareness campaign through on-farm demonstrations and undertake individual advisory farm visits on high risk farms, to reduce the amount of sediment, nutrients and chemicals entering a waterbody from farmland. Educate the farming | To control or manage diffuse source inputs | Reduce diffuse pollution at source | Field & Crop - Arable soils |  |  |  |  | EA, WLT, NFU , TW, UCL,KCL, RU, |  | unfunded | Contribute to improvement to 1+ element. | UC | [6 empty] | Yes | any
48 | 17110 | Vyne Stream | yes | Improve | Phosphate | Diffuse/agriculture |  | EM | Creation of buffer strips to reduce land run off | To control or manage diffuse source inputs | Reduce diffuse pollution pathways (i.e. control entry to water environment) | Riparian management |  |  |  |  | EA, WLT, NFU , TW, UCL,KCL, RU, |  | unfunded | Contribute to improvement to 1+ element. | UC | [6 empty] | Yes | any
51 | 17120 | Fleet Brook | yes | Improve | Invertebrates | DO/diffuse/mixed drainage |  | EM | Ensure that all discharges from urban areas are being discharged to the correct drainage system. For example, All car washes should be discharged to foul sewer under a consent from the local water authority. | To control or manage point source inputs | Reduce point source pathways (i.e. control entry to water environment) | Sewerage system re-design and rebuild |  |  |  |  | EA, WLT, NFU , TW, UCL,KCL, RU, |  | unfunded | Contribute to improvement to 1+ element. | UC | [6 empty] | Yes | any
51 | 17120 | Fleet Brook | yes | Improve | Invertebrates | DO/diffuse/mixed drainage |  | EM | Businesses and households should ensure all applies are connected to the right drain. For example dish washer, washing machine etc are commonly just plumbed into the surface water drains. | To control or manage point source inputs | Reduce point source pollution at source | Sewerage system re-design and rebuild |  |  |  |  | EA, WLT, NFU , TW, UCL,KCL, RU, |  | unfunded | Contribute to improvement to 1+ element. | UC | [6 empty] | Yes | any
57 | 17120 | Fleet Brook | yes | Improve | Fish | DO/diffuse/mixed drainage |  | EM | Ensure that all discharges from urban areas are being discharged to the correct drainage system. For example, All car washes should be discharged to foul sewer under a consent from the local water authority. | To control or manage point source inputs | Reduce point source pathways (i.e. control entry to water environment) | Sewerage system re-design and rebuild |  |  |  |  | EA, WLT, NFU , TW, UCL,KCL, RU, |  | unfunded | Contribute to improvement to 1+ element. | UC | [6 empty] | Yes | any
57 | 17120 | Fleet Brook | yes | Improve | Fish | DO/diffuse/mixed drainage |  | EM | Businesses and households should ensure all applies are connected to the right drain. For example dish washer, washing machine etc are commonly just plumbed into the surface water drains. | To control or manage point source inputs | Reduce point source pollution at source | Sewerage system re-design and rebuild |  |  |  |  | EA, WLT, NFU , TW, UCL,KCL, RU, |  | unfunded | Contribute to improvement to 1+ element. | UC | [6 empty] | Yes | any
58 | 17120 | Fleet Brook | yes | Improve | Fish | Sediment/agricultural run off |  | EM | Use the Catchment Sensitive Farming initative to raise awareness and reduce pesticide\phosphate\sediment pollution in this waterbody. | To control or manage diffuse source inputs | Reduce diffuse pollution at source | Field & Crop - Arable soils |  |  |  |  | EA, WLT, NFU , TW, UCL,KCL, RU, |  | unfunded | Contribute to improvement to 1+ element. | UC | [6 empty] | Yes | any
58 | 17120 | Fleet Brook | yes | Improve | Fish | Sediment/agricultural run off |  | EM | Run an awareness campaign through on-farm demonstrations and undertake individual advisory farm visits on high risk farms, to reduce the amount of sediment, nutrients and chemicals entering a waterbody from farmland. Educate the farming | To control or manage diffuse source inputs | Reduce diffuse pollution at source | Field & Crop - Arable soils |  |  |  |  | EA, WLT, NFU , TW, UCL,KCL, RU, |  | unfunded | Contribute to improvement to 1+ element. | UC | [6 empty] | Yes | any
58 | 17120 | Fleet Brook | yes | Improve | Fish | Sediment/agricultural run off |  | EM | Creation of buffer strips to reduce land run off | To control or manage diffuse source inputs | Reduce diffuse pollution pathways (i.e. control entry to water environment) | Riparian management |  |  |  |  | EA, WLT, NFU , TW, UCL,KCL, RU, |  | unfunded | Contribute to improvement to 1+ element. | UC | [6 empty] | Yes | any
60 | 17130 | Cove Brook | yes | Improve | Fish | Iron/diffuse/contaminated land |  | EM | Creation of buffer strips to reduce land run off | To control or manage diffuse source inputs | Reduce diffuse pollution pathways (i.e. control entry to water environment) | Riparian management |  |  |  |  | EA, WLT, NFU , TW, UCL,KCL, RU, |  | unfunded | Contribute to improvement to 1+ element. | UC | [6 empty] | Yes | any
61 | 17130 | Cove Brook | yes | Improve | Invertebrates | DO/diffuse/mixed drainage |  | EM | Ensure that all discharges from urban areas are being discharged to the correct drainage system. For example, All car washes should be discharged to foul sewer under a consent from the local water authority. | To control or manage point source inputs | Reduce point source pathways (i.e. control entry to water environment) | Sewerage system re-design and rebuild |  |  |  |  | EA, WLT, NFU , TW, UCL,KCL, RU, |  | unfunded | Contribute to improvement to 1+ element. | UC | [6 empty] | Yes | any
61 | 17130 | Cove Brook | yes | Improve | Invertebrates | DO/diffuse/mixed drainage |  | EM | Businesses and households should ensure all applies are connected to the right drain. For example dish washer, washing machine etc are commonly just plumbed into the surface water drains. | To control or manage point source inputs | Reduce point source pollution at source | Sewerage system re-design and rebuild |  |  |  |  | EA, WLT, NFU , TW, UCL,KCL, RU, |  | unfunded | Contribute to improvement to 1+ element. | UC | [6 empty] | Yes | any
68 | 17130 | Cove Brook | yes | Improve | Fish | Iron/diffuse/mixed drainage |  | EM | Ensure that all discharges from urban areas are being discharged to the correct drainage system. For example, All car washes should be discharged to foul sewer under a consent from the local water authority. | To control or manage point source inputs | Reduce point source pathways (i.e. control entry to water environment) | Sewerage system re-design and rebuild |  |  |  |  | EA, WLT, NFU , TW, UCL,KCL, RU, |  | unfunded | Contribute to improvement to 1+ element. | UC | [6 empty] | Yes | any
68 | 17130 | Cove Brook | yes | Improve | Fish | Iron/diffuse/mixed drainage |  | EM | Businesses and households should ensure all applies are connected to the right drain. For example dish washer, washing machine etc are commonly just plumbed into the surface water drains. | To control or manage point source inputs | Reduce point source pollution at source | Sewerage system re-design and rebuild |  |  |  |  | EA, WLT, NFU , TW, UCL,KCL, RU, |  | unfunded | Contribute to improvement to 1+ element. | UC | [6 empty] | Yes | any
78 | 17160 | Bow Brook ( Pamber End to Sherfield Green) | no | Improve | Phosphate | Diffuse/agriculture |  | EM | Use the Catchment Sensitive Farming initative to raise awareness and reduce pesticide\phosphate\sediment pollution in this waterbody. | To control or manage diffuse source inputs | Reduce diffuse pollution at source | Field & Crop - Arable soils |  |  |  |  | EA, WLT, NFU , TW, UCL,KCL, RU, |  | unfunded | Contribute to improvement to 1+ element. | UC | [6 empty] | Yes | any
78 | 17160 | Bow Brook ( Pamber End to Sherfield Green) | no | Improve | Phosphate | Diffuse/agriculture |  | EM | Run an awareness campaign through on-farm demonstrations and undertake individual advisory farm visits on high risk farms, to reduce the amount of sediment, nutrients and chemicals entering a waterbody from farmland. Educate the farming | To control or manage diffuse source inputs | Reduce diffuse pollution at source | Field & Crop - Arable soils |  |  |  |  | EA, WLT, NFU , TW, UCL,KCL, RU, |  | unfunded | Contribute to improvement to 1+ element. | UC | [6 empty] | Yes | any
78 | 17160 | Bow Brook ( Pamber End to Sherfield Green) | no | Improve | Phosphate | Diffuse/agriculture |  | EM | Creation of buffer strips to reduce land run off | To control or manage diffuse source inputs | Reduce diffuse pollution pathways (i.e. control entry to water environment) | Riparian management |  |  |  |  | EA, WLT, NFU , TW, UCL,KCL, RU, |  | unfunded | Contribute to improvement to 1+ element. | UC | [6 empty] | Yes | any
85 | 17180 | Blackwater (Aldershot to Cove Brook) | yes | Improve | Phosphate | Point source/industrial discharge |  | EM | Ensure that all discharges from urban areas are being discharged to the correct drainage system. For example, All car washes should be discharged to foul sewer under a consent from the local water authority. | To control or manage point source inputs | Reduce point source pathways (i.e. control entry to water environment) | Sewerage system re-design and rebuild |  |  |  |  | EA, WLT, NFU , TW, UCL,KCL, RU, |  | unfunded | Contribute to improvement to 1+ element. | UC | [6 empty] | Yes | any
93 | 17180 | Blackwater (Aldershot to Cove Brook) | yes | Improve | Invertebrates | DO/diffuse/mixed drainage |  | EM | Ensure that all discharges from urban areas are being discharged to the correct drainage system. For example, All car washes should be discharged to foul sewer under a consent from the local water authority. | To control or manage point source inputs | Reduce point source pathways (i.e. control entry to water environment) | Sewerage system re-design and rebuild |  |  |  |  | EA, WLT, NFU , TW, UCL,KCL, RU, |  | unfunded | Contribute to improvement to 1+ element. | UC | [6 empty] | Yes | any
93 | 17180 | Blackwater (Aldershot to Cove Brook) | yes | Improve | Invertebrates | DO/diffuse/mixed drainage |  | EM | Businesses and households should ensure all applies are connected to the right drain. For example dish washer, washing machine etc are commonly just plumbed into the surface water drains. | To control or manage point source inputs | Reduce point source pollution at source | Sewerage system re-design and rebuild |  |  |  |  | EA, WLT, NFU , TW, UCL,KCL, RU, |  | unfunded | Contribute to improvement to 1+ element. | UC | [6 empty] | Yes | any
97 | 17180 | Blackwater (Aldershot to Cove Brook) | yes | Improve | Invertebrates | Ammonia/Diffuse pollution/contaminated land |  | EM | Use the Catchment Sensitive Farming initative to raise awareness and reduce pesticide\phosphate\sediment pollution in this waterbody. | To control or manage diffuse source inputs | Reduce diffuse pollution at source | Field & Crop - Arable soils |  |  |  |  | EA, WLT, NFU , TW, UCL,KCL, RU, |  | unfunded | Contribute to improvement to 1+ element. | UC | [6 empty] | Yes | any
97 | 17180 | Blackwater (Aldershot to Cove Brook) | yes | Improve | Invertebrates | Ammonia/Diffuse pollution/contaminated land |  | EM | Run an awareness campaign through on-farm demonstrations and undertake individual advisory farm visits on high risk farms, to reduce the amount of sediment, nutrients and chemicals entering a waterbody from farmland. Educate the farming | To control or manage diffuse source inputs | Reduce diffuse pollution at source | Field & Crop - Arable soils |  |  |  |  | EA, WLT, NFU , TW, UCL,KCL, RU, |  | unfunded | Contribute to improvement to 1+ element. | UC | [6 empty] | Yes | any
97 | 17180 | Blackwater (Aldershot to Cove Brook) | yes | Improve | Invertebrates | Ammonia/Diffuse pollution/contaminated land |  | EM | Creation of buffer strips to reduce land run off | To control or manage diffuse source inputs | Reduce diffuse pollution pathways (i.e. control entry to water environment) | Riparian management |  |  |  |  | EA, WLT, NFU , TW, UCL,KCL, RU, |  | unfunded | Contribute to improvement to 1+ element. | UC | [6 empty] | Yes | any
102 | 17180 | Blackwater (Aldershot to Cove Brook) | yes | Improve | Fish | ammonia/diffuse contaminated land |  | EM | Use the Catchment Sensitive Farming initative to raise awareness and reduce pesticide\phosphate\sediment pollution in this waterbody. | To control or manage diffuse source inputs | Reduce diffuse pollution at source | Field & Crop - Arable soils |  |  |  |  | EA, WLT, NFU , TW, UCL,KCL, RU, |  | unfunded | Contribute to improvement to 1+ element. | UC | [6 empty] | Yes | any
102 | 17180 | Blackwater (Aldershot to Cove Brook) | yes | Improve | Fish | ammonia/diffuse contaminated land |  | EM | Run an awareness campaign through on-farm demonstrations and undertake individual advisory farm visits on high risk farms, to reduce the amount of sediment, nutrients and chemicals entering a waterbody from farmland. Educate the farming | To control or manage diffuse source inputs | Reduce diffuse pollution at source | Field & Crop - Arable soils |  |  |  |  | EA, WLT, NFU , TW, UCL,KCL, RU, |  | unfunded | Contribute to improvement to 1+ element. | UC | [6 empty] | Yes | any
102 | 17180 | Blackwater (Aldershot to Cove Brook) | yes | Improve | Fish | ammonia/diffuse contaminated land |  | EM | Creation of buffer strips to reduce land run off | To control or manage diffuse source inputs | Reduce diffuse pollution pathways (i.e. control entry to water environment) | Riparian management |  |  |  |  | EA, WLT, NFU , TW, UCL,KCL, RU, |  | unfunded | Contribute to improvement to 1+ element. | UC | [6 empty] | Yes | any
103 | 17180 | Blackwater (Aldershot to Cove Brook) | yes | Improve | Fish | DO/diffuse/mixed drainage |  | EM | Ensure that all discharges from urban areas are being discharged to the correct drainage system. For example, All car washes should be discharged to foul sewer under a consent from the local water authority. | To control or manage point source inputs | Reduce point source pathways (i.e. control entry to water environment) | Sewerage system re-design and rebuild |  |  |  |  | EA, WLT, NFU , TW, UCL,KCL, RU, |  | unfunded | Contribute to improvement to 1+ element. | UC | [6 empty] | Yes | any
103 | 17180 | Blackwater (Aldershot to Cove Brook) | yes | Improve | Fish | DO/diffuse/mixed drainage |  | EM | Businesses and households should ensure all applies are connected to the right drain. For example dish washer, washing machine etc are commonly just plumbed into the surface water drains. | To control or manage point source inputs | Reduce point source pollution at source | Sewerage system re-design and rebuild |  |  |  |  | EA, WLT, NFU , TW, UCL,KCL, RU, |  | unfunded | Contribute to improvement to 1+ element. | UC | [6 empty] | Yes | any
111 | 17240 | Whitewater | no | Improve | Fish | Sediment/mixed agricultural run off |  | EM | Use the Catchment Sensitive Farming initative to raise awareness and reduce pesticide\phosphate\sediment pollution in this waterbody. | To control or manage diffuse source inputs | Reduce diffuse pollution at source | Field & Crop - Arable soils |  |  |  |  | EA, WLT, NFU , TW, UCL,KCL, RU, |  | unfunded | Contribute to improvement to 1+ element. | UC | [6 empty] | Yes | any
111 | 17240 | Whitewater | no | Improve | Fish | Sediment/mixed agricultural run off |  | EM | Run an awareness campaign through on-farm demonstrations and undertake individual advisory farm visits on high risk farms, to reduce the amount of sediment, nutrients and chemicals entering a waterbody from farmland. Educate the farming | To control or manage diffuse source inputs | Reduce diffuse pollution at source | Field & Crop - Arable soils |  |  |  |  | EA, WLT, NFU , TW, UCL,KCL, RU, |  | unfunded | Contribute to improvement to 1+ element. | UC | [6 empty] | Yes | any
111 | 17240 | Whitewater | no | Improve | Fish | Sediment/mixed agricultural run off |  | EM | Creation of buffer strips to reduce land run off | To control or manage diffuse source inputs | Reduce diffuse pollution pathways (i.e. control entry to water environment) | Riparian management |  |  |  |  | EA, WLT, NFU , TW, UCL,KCL, RU, |  | unfunded | Contribute to improvement to 1+ element. | UC | [6 empty] | Yes | any
131 | 17330 | Loddon (Sherfield on Loddon to Swallowfield) | no | Improve | Phytobenthos | Phosphate/Diffuse /agriculture |  | EM | Use the Catchment Sensitive Farming initative to raise awareness and reduce pesticide\phosphate\sediment pollution in this waterbody. | To control or manage diffuse source inputs | Reduce diffuse pollution at source | Field & Crop - Arable soils |  |  |  |  | EA, WLT, NFU , TW, UCL,KCL, RU, |  | unfunded | Contribute to improvement to 1+ element. | UC | [6 empty] | Yes | any
131 | 17330 | Loddon (Sherfield on Loddon to Swallowfield) | no | Improve | Phytobenthos | Phosphate/Diffuse /agriculture |  | EM | Run an awareness campaign through on-farm demonstrations and undertake individual advisory farm visits on high risk farms, to reduce the amount of sediment, nutrients and chemicals entering a waterbody from farmland. Educate the farming | To control or manage diffuse source inputs | Reduce diffuse pollution at source | Field & Crop - Arable soils |  |  |  |  | EA, WLT, NFU , TW, UCL,KCL, RU, |  | unfunded | Contribute to improvement to 1+ element. | UC | [6 empty] | Yes | any
131 | 17330 | Loddon (Sherfield on Loddon to Swallowfield) | no | Improve | Phytobenthos | Phosphate/Diffuse /agriculture |  | EM | Creation of buffer strips to reduce land run off | To control or manage diffuse source inputs | Reduce diffuse pollution pathways (i.e. control entry to water environment) | Riparian management |  |  |  |  | EA, WLT, NFU , TW, UCL,KCL, RU, |  | unfunded | Contribute to improvement to 1+ element. | UC | [6 empty] | Yes | any
139 | 17330 | Loddon (Sherfield on Loddon to Swallowfield) | no | Improve | Phosphate | Diffuse pollution/agriculture |  | EM | Use the Catchment Sensitive Farming initative to raise awareness and reduce pesticide\phosphate\sediment pollution in this waterbody. | To control or manage diffuse source inputs | Reduce diffuse pollution at source | Field & Crop - Arable soils |  |  |  |  | EA, WLT, NFU , TW, UCL,KCL, RU, |  | unfunded | Contribute to improvement to 1+ element. | UC | [6 empty] | Yes | any
139 | 17330 | Loddon (Sherfield on Loddon to Swallowfield) | no | Improve | Phosphate | Diffuse pollution/agriculture |  | EM | Run an awareness campaign through on-farm demonstrations and undertake individual advisory farm visits on high risk farms, to reduce the amount of sediment, nutrients and chemicals entering a waterbody from farmland. Educate the farming | To control or manage diffuse source inputs | Reduce diffuse pollution at source | Field & Crop - Arable soils |  |  |  |  | EA, WLT, NFU , TW, UCL,KCL, RU, |  | unfunded | Contribute to improvement to 1+ element. | UC | [6 empty] | Yes | any
139 | 17330 | Loddon (Sherfield on Loddon to Swallowfield) | no | Improve | Phosphate | Diffuse pollution/agriculture |  | EM | Creation of buffer strips to reduce land run off | To control or manage diffuse source inputs | Reduce diffuse pollution pathways (i.e. control entry to water environment) | Riparian management |  |  |  |  | EA, WLT, NFU , TW, UCL,KCL, RU, |  | unfunded | Contribute to improvement to 1+ element. | UC | [6 empty] | Yes | any
149 | 17330 | Loddon (Sherfield on Loddon to Swallowfield) | no | Improve | Fish | Sediment/cattle poaching |  | EM | Fencing to reduce cattle poaching and sediments carrying hosphates efrom entering the river. | To control or manage diffuse source inputs | Reduce diffuse pollution pathways (i.e. control entry to water environment) | Field & Crop - Livestock |  |  |  |  | EA, WLT, NFU , TW, UCL,KCL, RU, |  | unfunded | Contribute to improvement to 1+ element. | UC | [6 empty] | Yes | any
151 | 23160 | Loddon (Swallowfield to Thames) | no | Improve | Tributyltin compounds | diffuse/trading estates |  | EM | Fencing to reduce cattle poaching and sediments carrying hosphates efrom entering the river. | To control or manage diffuse source inputs | Reduce diffuse pollution pathways (i.e. control entry to water environment) | Field & Crop - Livestock |  |  |  |  | EA, WLT, NFU , TW, UCL,KCL, RU, |  | unfunded | Contribute to improvement to 1+ element. | UC | [6 empty] | Yes | any
157 | 23190 | Twyford Brook | no | Improve | Phosphate | Arable field/diffuse |  | EM | Use the Catchment Sensitive Farming initative to raise awareness and reduce pesticide\phosphate\sediment pollution in this waterbody. | To control or manage diffuse source inputs | Reduce diffuse pollution at source | Field & Crop - Arable soils |  |  |  |  | EA, WLT, NFU , TW, UCL,KCL, RU, |  | unfunded | Contribute to improvement to 1+ element. | UC | [6 empty] | Yes | any
157 | 23190 | Twyford Brook | no | Improve | Phosphate | Arable field/diffuse |  | EM | Run an awareness campaign through on-farm demonstrations and undertake individual advisory farm visits on high risk farms, to reduce the amount of sediment, nutrients and chemicals entering a waterbody from farmland. Educate the farming | To control or manage diffuse source inputs | Reduce diffuse pollution at source | Field & Crop - Arable soils |  |  |  |  | EA, WLT, NFU , TW, UCL,KCL, RU, |  | unfunded | Contribute to improvement to 1+ element. | UC | [6 empty] | Yes | any
157 | 23190 | Twyford Brook | no | Improve | Phosphate | Arable field/diffuse |  | EM | Creation of buffer strips to reduce land run off | To control or manage diffuse source inputs | Reduce diffuse pollution pathways (i.e. control entry to water environment) | Riparian management |  |  |  |  | EA, WLT, NFU , TW, UCL,KCL, RU, |  | unfunded | Contribute to improvement to 1+ element. | UC | [6 empty] | Yes | any
161 | 23190 | Twyford Brook | no | Improve | Phosphate | Dairy cattle/diffuse |  | EM | Fencing to reduce cattle poaching | [7 empty] | EA, WLT, NFU , TW, UCL,KCL, RU, |  | unfunded | Contribute to improvement to 1+ element. | UC | [6 empty] | Yes | any
161 | 23190 | Twyford Brook | no | Improve | Phosphate | Dairy cattle/diffuse |  | EM | Use the Catchment Sensitive Farming initative to raise awareness and reduce pesticide\phosphate\sediment pollution in this waterbody. | To control or manage diffuse source inputs | Reduce diffuse pollution at source | Field & Crop - Arable soils |  |  |  |  | EA, WLT, NFU , TW, UCL,KCL, RU, |  | unfunded | Contribute to improvement to 1+ element. | UC | [6 empty] | Yes | any
161 | 23190 | Twyford Brook | no | Improve | Phosphate | Dairy cattle/diffuse |  | EM | Run an awareness campaign through on-farm demonstrations and undertake individual advisory farm visits on high risk farms, to reduce the amount of sediment, nutrients and chemicals entering a waterbody from farmland. Educate the farming | To control or manage diffuse source inputs | Reduce diffuse pollution at source | Field & Crop - Arable soils |  |  |  |  | EA, WLT, NFU , TW, UCL,KCL, RU, |  | unfunded | Contribute to improvement to 1+ element. | UC | [6 empty] | Yes | any
161 | 23190 | Twyford Brook | no | Improve | Phosphate | Dairy cattle/diffuse |  | EM | Creation of buffer strips to reduce land run off | To control or manage diffuse source inputs | Reduce diffuse pollution pathways (i.e. control entry to water environment) | Riparian management |  |  |  |  | EA, WLT, NFU , TW, UCL,KCL, RU, |  | unfunded | Contribute to improvement to 1+ element. | UC | [6 empty] | Yes | any
161 | 23190 | Twyford Brook | no | Improve | Phosphate | Dairy cattle/diffuse |  | EM | Fencing to reduce cattle poaching and sediments carrying hosphates efrom entering the river. | To control or manage diffuse source inputs | Reduce diffuse pollution pathways (i.e. control entry to water environment) | Field & Crop - Livestock |  |  |  |  | EA, WLT, NFU , TW, UCL,KCL, RU, |  | unfunded | Contribute to improvement to 1+ element. | UC | [6 empty] | Yes | any
Phytobenthos

## Options Fisheries
| RFF | [5 empty] | Option details | [7 empty] | Partnership | [9 empty] | Time scale
1 | WB ID | Name | HMWB | Improve or No deterioration | Stage 3 investigation associated with option (Element) | RFF ID (pressure/SWMI) | RBMP measure ID | Action to be written by (e.g. Fisheries) | Action description | Action type 1 | Action type 2 | Action type 3 | NGR (u/s, d/s or centre) | Length or river improved | Lead sector | Name of Organisation | Potential partners | Total cost | Funded or unfunded | Predicted improvement | Certainty (VC, QC, UC) | Eco benefit for HMWB | Is this part of a project? Project REF | Funding stream | Length of time to implement action | Planned start | Planned end | Is this a catchment wide solution | Climate change scenario (current, wet, dry, any) | Additional notes
2 | 17080 | Loddon (Basingstoke to Lyde) | yes | Improve | Fish | Morphology/barriers to migration |  | Fisheries | Bartons Mill weir complex removal/lowering or installation of fish pass as required and habitat enhancement | Improve modified habitats | Removal or easement of barriers to fish migration | Improvements to longitudinal connectivity | SU6616753092 | 2 km |  |  | Landowners, WTT, WLT, LFCC, angling club, B&DBC | 180K | unfunded | Contribute to improvement of more than 1 elelment | VC | Fish | no | WFD | 2 years |  |  | no | any
3 | 17080 | Loddon (Basingstoke to Lyde) | yes | Improve | Fish | Morphology/barriers to migration |  | Fisheries | Old Basing fish farm weir removal/lowering or installation of fish pass as required and habitat enhancement | Improve modified habitats | Removal or easement of barriers to fish migration | Improvements to longitudinal connectivity | SU6649453304 | 500 m |  |  | Landowners, WTT, WLT, LFCC, angling club, B&DBC | 10K | unfunded | Contribute to improvement of more than 1 elelment | VC | Fish | no | WFD | 1year |  |  | no | any
3 | 17080 | Loddon (Basingstoke to Lyde) | yes | Improve | Fish | Morphology/barriers to migration |  | Fisheries | Install fish pass at Pyots Hill | Improve modified habitats | Removal or easement of barriers to fish migration | Improvements to longitudinal connectivity | SU6671153687 | 3 km |  |  | Landowners, WTT, WLT, LFCC, angling club, B&DBC | 15 k | unfunded | Contribute to improvement of more than 1 elelment | VC | Fish | no | WFD | 1 year |  |  | no | any
4 | 17080 | Loddon (Basingstoke to Lyde) | yes | Improve | Fish | Morphology/barriers to migration |  | Fisheries | Overspill to side channel u/s Lower Mill | Improve modified habitats | Removal or easement of barriers to fish migration | Improvements to longitudinal connectivity | SU6671353686 | 500 m |  |  | Landowners, WTT, WLT, LFCC, angling club, B&DBC | 10K | funded | Contribute to improvement of more than 1 elelment | VC | Fish | yes | WFD | 1 year | 2013 | 2014 | no | any
5 | 17080 | Loddon (Basingstoke to Lyde) | yes | Improve | Fish | Morphology/barriers to migration |  | Fisheries | Lower Mill weir removal/lowering or installation of fish pass as required and habitat enhancement | Improve modified habitats | Removal or easement of barriers to fish migration | Improvements to longitudinal connectivity | SU6689353810 | 1 km |  |  | Landowners, WTT, WLT, LFCC, angling club, B&DBC | 300 k | unfunded | Contribute to improvement of more than 1 elelment | VC | Fish | no | WFD | 2 years |  |  | no | any | technically diffuicult
6 | 17080 | Loddon (Basingstoke to Lyde) | yes | Improve | Fish | Morphology/barriers to migration |  | Fisheries | LH channel weir d/s Lower Mill | Improve modified habitats | Removal or easement of barriers to fish migration | Improvements to longitudinal connectivity | SU6691353897 | 500 |  |  | land owner | 5000 | unfunded | Contribute to improvement of more than 1 elelment | VC | Fish | no | WFD | 1 year |  |  | no | any
7 | 17080 | Loddon (Basingstoke to Lyde) | yes | Improve | Fish | Morphology/barriers to migration |  | Fisheries | RH channel d/s Lower Mill | Improve modified habitats | Removal or easement of barriers to fish migration | Improvements to longitudinal connectivity | SU6718354038 | 500 |  |  | land owner | 5000 | unfunded | Contribute to improvement of more than 1 elelment | VC | Fish | no | WFD | 1 year |  |  | no | any
8 | 17080 | Loddon (Basingstoke to Lyde) | yes | Improve | Fish | Morphology/barriers to migration |  | Fisheries | Old Basing RH concrete weir | Improve modified habitats | Removal or easement of barriers to fish migration | Improvements to longitudinal connectivity | SU6718554042 (weir 2 Old Basing) | 500 m |  |  | Landowners, WTT, WLT, LFCC, angling club, B&DBC | 0 | funded | Contribute to improvement of more than 1 elelment | VC | Fish | yes | WFD | 1 month | 2013 | 2014 | no | any
9 | 17080 | Loddon (Basingstoke to Lyde) | yes | Improve | Fish | Morphology/barriers to migration |  | Fisheries | Old Basing LH channel redundant weir | Improve modified habitats | Removal or easement of barriers to fish migration | Improvements to longitudinal connectivity | SU6689154017 (weir 1 Old Basing) | 500 m |  |  | Landowners, WTT, WLT, LFCC, angling club, B&DBC | 0 | funded | Contribute to improvement of more than 1 elelment | VC | Fish | yes | WFD | 1 month | 2013 | 2014 | no | any
10 | 17080 | Loddon (Basingstoke to Lyde) | yes | Improve | Fish | Morphology/barriers to migration |  | FCRM | Flow diversion structure d/s Eastrop Park | Improve modified habitats | Removal or easement of barriers to fish migration | Improvements to longitudinal connectivity | SU6523352591 | 500 m |  |  | Landowners, WTT, WLT, LFCC, angling club, B&DBC | 30 | unfunded | Contribute to improvement of more than 1 elelment | VC | Fish | yes | FCRM | 1 year |  |  | no | any | Part of the Eastrop Park project.
14 | 17080 | Loddon (Basingstoke to Lyde) | yes | Improve | Fish | Morphology/physical modification |  | FCRM | Investigat the passability of culverts around Basingstoke, opening culvert/installing fish easment as required (Eastrop Park) | Improve modified habitats | Removal or easement of barriers to fish migration | Improvements to longitudinal connectivity | SU6485952378 | 500 m |  |  | EA LA WTT WLT | 2 million | unfunded | Contribute to improvement of more than 1 elelment | VC | Fish | yes | FCRM/Partnership | 3 years |  |  | no | any | feasibility study complete
15 | 17080 | Loddon (Basingstoke to Lyde) | yes | Improve | Fish | Morphology/physical modification |  | FCRM | Saunders field (headwater of the Loddon). Improve ressilience, wetlands, SUDS. | Improve modified habitats | Improvement to condition of riparian zone and/or wetland habitats | Preserve and restore habitats | SU6221052074 | 300 m |  |  | WLT | 50 k | unfunded | No deterioration |  | Fish | no | LA | 1 year |  |  | no | any
16 | 17080 | Loddon (Basingstoke to Lyde) | yes | Improve | Fish | Morphology/physical modification |  | Fisheries | Introduction of gravels to create spawning opportunities for fish, and restore bed profile variation. Reduce shading to promote in channel vegetation growth and install woody debris in the channel. | Improve modified habitats | Improve condition of channel bed and/or banks/shoreline | Preserve and restore habitats | SU6805055247 to SU6919757549 | 800 m |  |  | WTT WLT Gresham AC TW | 80 k | unfunded | Contribute to improvement of more than 1 elelment | VC | Fish | no | WFD | 1 year |  |  | no | any | 5 riffles over 4 km
17 | 17080 | Loddon (Basingstoke to Lyde) | yes | Improve | Fish | Morphology/physical modification |  | Fisheries | Bank alterations to give channel width variation and two-stage channels. Introduction of meanders in straightened river sections. | Improve modified habitats | Improve condition of channel bed and/or banks/shoreline | Bank rehabilitation / reprofiling | SU6614852985 | 200m |  |  | WLT, WTT | 30k | unfunded | Contribute to improvement of more than 1 elelment | VC | Fish | no | WFD | 1 year |  |  | no | any
17 | 17080 | Loddon (Basingstoke to Lyde) | yes | Improve | Fish | Morphology/physical modification |  | Fisheries | Eastrop Park Partnership Project, deculvert the Loddon at Eastrop park and restore degraded habitats. | To improve modified habitat | Improvement to condition of channel/bed and/or banks/shoreline | Increase in-channel morphological diversity | SU6465452362 | 1 km |  |  | WTT B&DBC | 1 million | unfunded | Contribute to improvement of more than 1 elelment | VC | Fish | no | LA / WFD | 3 years |  |  | no | any | Current partnership established with LA. Feasibility stage complete.
18 | 17080 | Loddon (Basingstoke to Lyde) | yes | Improve | Fish | Morphology/physical modification |  | Fisheries | Bank alterations to give channel width variation and two-stage channels. Introduction of meanders in straightened river sections. | Improve modified habitats | Improve condition of channel bed and/or banks/shoreline | Bank rehabilitation / reprofiling | SU6519052612 to SU6803555235 | 80 m |  |  | TW angling club | 10 k | unfunded | Contribute to improvement of more than 1 elelment | VC | Fish | no | WFD | 1 year |  |  | no | any
18 | 17080 | Loddon (Basingstoke to Lyde) | yes | Improve | Fish | Morphology/physical modification |  | Fisheries | habitat enhancement d/s of notche weir 1 | Improve modified habitats | Improve condition of channel bed and/or banks/shoreline | Preserve and restore habitats | SU6689054024 | 100 m |  |  | Landowners, WTT, WLT, LFCC, angling club, B&DBC |  | unfunded | Contribute to improvement of more than 1 elelment | VC | Fish | yes | WFD | 1 year |  |  | no | any | in addition to the weir notching completed in 2013
19 | 17080 | Loddon (Basingstoke to Lyde) | yes | Improve | Fish | INNS/Signal crayfish |  | Fisheries | Provide advice and training on identification, control and disposal of invasive non-native species to all relevant groups and encourage monitoring schemes. Rolled out through partner organisations BVCP, LFCC etc. Advertise the need for authorisation from the Environment Agency and that traps need to be compliant. | Control or manage invasive species. | Building awareness and understanding. | Seek sustainable and cost-effective methods for managing established invasions of species. | SU7255165634 (centre of catchment) | whole catchment |  |  | LFCC, NE, BVCP, WPS | 500/year | unfunded | No deterioration | UC | Fish | No | WFD | 4 weeks | 2014-01-01 | Continuos | Yes | Any
30 | 17090 | Hart (Crondal to Elvetham) | no | Improve | Fish | INNS/Signal crayfish |  | Fisheries | Provide advice and training on identification, control and disposal of invasive non-native species to all relevant groups and encourage monitoring schemes. Rolled out through partner organisations BVCP, LFCC etc. Advertise the need for authorisation from the Environment Agency and that traps need to be compliant. | Control or manage invasive species. | Building awareness and understanding. | Seek sustainable and cost-effective methods for managing established invasions of species. | SU7255165634 (centre of catchment) | whole catchment |  |  | LFCC, NE, BVCP, WPS | 500/year | Unfunded | No deterioration | UC | Fish | No |  | 4 weeks | 2014-01-01 | Continuos | Yes | Any
32 | 17090 | Hart (Crondal to Elvetham) | no | Improve | Fish | Morphology/barriers to fish migration |  | Fisheries | larinier or bristle or pre barrage on weir structure at Pilcot Mill and habitat enhancement. | Improve modified habitats | Removal or easement of barriers to fish migration | Improvements to longitudinal connectivity | SU7864252793 | 4 km |  |  | Mill owner WTT WLT SE water | 40 k | Unfunded | Contribute to improvement of more than 1 elelment | VC | Fish | No | WFD | 1 year |  |  | no | Any | improve hart and itchell brook
33 | 17090 | Hart (Crondal to Elvetham) | no | Improve | Fish | Morphology/barriers to fish migration |  | Fisheries | Pre barrage fish pass at Basingstoke canal culvert and habitat enhancement. | Improve modified habitats | Removal or easement of barriers to fish migration | Improvements to longitudinal connectivity | SU7943851601 | 3 km |  |  | WTT WLT BCA | 5 k | Unfunded | Contribute to improvement of more than 1 elelment | VC | Fish | No | WFD | 1 year |  |  | no | Any | poor access
34 | 17090 | Hart (Crondal to Elvetham) | no | no deterioration | Fish | Morphology/barriers to fish migration |  | Fisheries | Elvetham to M3 improve morphology. New channel,Re meander, add Gravel riffles, bank reprofiling. | Improve modified habitats | Removal or easement of barriers to fish migration | Improvements to longitudinal connectivity | Hotel to M3 | 1 km |  |  | Highways, landowner/estate | 30 k | Unfunded | Contribute to improvement of more than 1 elelment | VC | Fish | No | WFD | 2 years |  |  | no | Any | WTT report as Stage 2 investigation. Add to database.
35 | 17090 | Hart (Crondal to Elvetham) | no | Improve | Fish | Morphology/barriers to fish migration |  | Fisheries | Elvetham Estate weir removal/lowering or installation of fish pass as required and habitat enhancement | Improve modified habitats | Removal or easement of barriers to fish migration | Improvements to longitudinal connectivity | SU7841556756 | 5 km |  |  | Hotel/Estate WTT WLT | 50 k (removal) | Unfunded | Contribute to improvement of more than 1 elelment | VC | Fish | No | WFD | 1 year |  |  | no | Any | removal prefered option
47 | 17080 | Vyne Stream | yes | Improve | Mitigation measure | physical modification/urbanisation |  | Fisheries Ops | Take The Vyne stillwater off-line to restore river gradient and morphology upstream. | Improve modified habitats | Improve condition of channel bed and/or banks/shoreline | Preserve and restore habitats | SU6363456910 | 4km |  |  | National Trust | 1000k | unfunded | Contribute to improvement of more than 1 elelment | VC | Fish | no | WFD | 3 years |  |  | no | any | Might not be feasible due to heritage issues
49 | 17120 | Fleet Brook | yes | Improve | Mitigation measure | physical modification/urbanisation |  | Fisheries Ops | Install LWD, manage canopy and introduce gravel between Mwy and Turners Green | Improve modified habitats | Improve condition of channel bed and/or banks/shoreline | Preserve and restore habitats | SU8078156569 | 2km |  |  | Thames Water | 30k | unfunded | Contribute to improvement of more than 1 elelment | QC | Fish | no | WFD | 1 year |  |  | no | any
50 |  | Fleet Brook | yes | Improve | Mitigation measure | physical modification/urbanisation |  | EM | PP MOD | To control or manage diffuse source inputs | Reduce diffuse pollution at source | Surface run-off & drainage management | SU8375252243 | 5.7 km |  |  | MOD, HWLT Fleet Pond Sociecty HDC | >10000 |  | Overall improvement, but below GES or GEP | UC | [6 empty] | no | wet
59 | 17130 | Cove Brook | yes | Improve | Invertebrates | physical modification/development of infrastructure |  | Fisheries Ops | Bank alterations to give channel width variation and two-stage channels. Introduction of meanders in straightened river sections. | Improve modified habitats | Improve condition of channel bed and/or banks/shoreline | Bank rehabilitation / reprofiling |  |  |  |  | BVCP, Cove Brook Group, LA |  | unfunded | Contribute to improvement of more than 1 elelment | VC | Fish | no | WFD | 1 year |  |  | no | any
71 | 17130 | Cove Brook | yes | Improve | Fish | Morphology/physical modification/Flood prevention structures |  | Fisheries | Introduction of gravels to create spawning opportunities for fish, and restore bed profile variation. Reduce shading to promote in channel vegetation growth and install woody debris in the channel. | Improve modified habitats | Improve condition of channel bed and/or banks/shoreline | Preserve and restore habitats | SU8558855587 | 2km |  |  | BVCP, Cove Brook Group, LA | 40k | unfunded | Contribute to improvement of more than 1 elelment | VC | Fish | no | WFD | 1 year |  |  | no | any
72 | 17130 | Cove Brook | yes | Improve | Fish | Morphology/physical modification/Flood prevention structures |  | Fisheries | Bank alterations to give channel width variation and two-stage channels. Introduction of meanders in straightened river sections. | Improve modified habitats | Improve condition of channel bed and/or banks/shoreline | Bank rehabilitation / reprofiling |  |  |  |  | BVCP, Cove Brook Group, LA |  | unfunded | Contribute to improvement of more than 1 elelment | VC | Fish | no | WFD | 1 year |  |  | no | any
73 | 17130 | Cove Brook | yes | Improve | Fish | Barriers to fish migration |  | Fisheries | weir removal/lowering or installation of fish pass as required and habitat enhancement | Improve modified habitats | Removal or easement of barriers to fish migration | Improvements to longitudinal connectivity | SU8555756773 | 3 km |  |  | BVCP, Cove Brook Group, LA |  | unfunded | Contribute to improvement of more than 1 elelment | VC | Fish | no | WFD | 1 year |  |  | no | any
79 | 17150 | Loddon (Hartley Wespall to Sherfield on Loddon) | no | Improve | Expert judgement | physical modification/barriers to migration |  | Fisheries | Fish pass or bypass channel on Longbridge Mill sluice/weir | Improve modified habitats | Removal or easement of barriers to fish migration | Improvements to longitudinal connectivity | SU6835758189 | 11 km |  |  | Estate/landowner, brewery | 150k | unfunded | Contribute to improvement of more than 1 elelment | VC | Fish | No | WFD | 2 years |  |  | no | any | improves outside of this waterbody (Loddon (7km) and Lyde (4km)
82 | 17150 | Loddon (Hartley Wespall to Sherfield on Loddon) | no | Improve | Expert judgement | impoundments - no water storage/flow |  | Hydrology Fisheries | Remove Longbridge Mill sluice/weir | Improve modified habitats | Removal or easement of barriers to fish migration | Improvements to longitudinal connectivity | SU6835758189 | 11 km |  |  | Estate/landowner, brewery | £100k | unfunded | Contribute to improvement of more than 1 elelment | VC | Fish, WQ | No | WFD | 2 years |  |  | no | Any | improves outside of this waterbody (Loddon (7km) and Lyde (4km). This is a working mill; it would require significant negotiations to get Landowner agreement to remove the impounding structure (however, this would be the preferred option for the site).
83 | 17180 | Blackwater (Aldershot to Cove Brook) | yes | No deterioration | Invertebrates | INNS/Signal crayfish |  | Fisheries | Provide advice and training on identification, control and disposal of invasive non-native species to all relevant groups and encourage monitoring schemes. Rolled out through partner organisations BVCP, LFCC etc. Advertise the need for authorisation from the Environment Agency and that traps need to be compliant. | Control or manage invasive species. | Building awareness and understanding. | Seek sustainable and cost-effective methods for managing established invasions of species. | SU8502749906 to SU8632958331 | 15 km |  |  | LFCC, NE, BVCP, WPS | 500/year |  | No deterioration | UC |  | No |  | 4 weeks | 2014-01-01 | Continuos | Yes | Any
84 | 17180 | Blackwater (Aldershot to Cove Brook) | yes | No deterioration | Fish | INNS/Signal crayfish |  | Fisheries | Provide advice and training on identification, control and disposal of invasive non-native species to all relevant groups and encourage monitoring schemes. Rolled out through partner organisations BVCP, LFCC etc. Advertise the need for authorisation from the Environment Agency and that traps need to be compliant. | Control or manage invasive species. | Building awareness and understanding. | Seek sustainable and cost-effective methods for managing established invasions of species. | SU8502749906 to SU8632958331 | 15 km |  |  | LFCC, NE, BVCP, WPS | 500/year |  | No deterioration | UC | Fish | No |  | 4 weeks | 2014-01-01 | Continuos | Yes | Any
99 | 17180 | Blackwater (Aldershot to Cove Brook) | yes | Improve | Fish | Morphology/physical modification |  | FCRM | Introduction of gravels to create spawning opportunities for fish, and restore bed profile variation. Reduce shading to promote in channel vegetation growth and install woody debris in the channel. Bank alterations to give channel width variation and two-stage channels. Introduction of meanders in straightened river sections. | Improve modified habitats | Improve condition of channel bed and/or banks/shoreline | Preserve and restore habitats | Farnham Quarry Phase 3 |  |  |  | Hansons BVCP EA WTT | 60k |  |  |  | Fish |  | FCRM
100 | 17180 | Blackwater (Aldershot to Cove Brook) | yes | Improve | Fish | Morphology/physical modification |  | Fisheries | Introduction of gravels to create spawning opportunities for fish, and restore bed profile variation. Reduce shading to promote in channel vegetation growth and install woody debris in the channel. Bank alterations to give channel width variation and two-stage channels. Introduction of meanders in straightened river sections. | Improve modified habitats | Improve condition of channel bed and/or banks/shoreline | Preserve and restore habitats | SU8594659275 and SU8812348988 | 1 km |  |  | LFCC, BVCP | 40k for 2sites. | unfunded | Contribute to improvement of more than 1 elelment | VC | Fish | no | WFD | 1 year |  |  | no | any
101 | 17180 | Blackwater (Aldershot to Cove Brook) | yes | Improve | Fish | Barriers to migration |  | Fisheries | Badshot Lea Lake outlet. Take Badshot Lea offline. | Improve modified habitats | Removal or easement of barriers to fish migration | Improvements to longitudinal connectivity | SU8649249177 | 2 km |  |  | LFCC, BVCP, LA | 100k | unfunded | Contribute to improvement of more than 1 elelment | VC | Fish | no | WFD | 3 years |  |  | no | any
105 | 17180 | Blackwater (Aldershot to Cove Brook) | yes | Improve | Invertebrates | Morphology/physical modification |  | Fisheries | Morphology options will help. | [10 empty] | Contribute to improvement of more than 1 elelment |  | invertebrates
112 | 17240 | Whitewater | no | Improve | Fish | INNS/Signal crayfish |  | Fisheries | Provide advice and training on identification, control and disposal of invasive non-native species to all relevant groups and encourage monitoring schemes. Rolled out through partner organisations BVCP, LFCC etc. Advertise the need for authorisation from the Environment Agency and that traps need to be compliant. | Control or manage invasive species. | Building awareness and understanding. | Seek sustainable and cost-effective methods for managing established invasions of species. | SU8594354787 | Catchment |  |  | LFCC, NE, BVCP, WPS | 500/year |  | No deterioration | UC | Fish | No |  | 4 weeks | 2014-01-01 | Continuos | Yes | Any
113 | 17240 | Whitewater | no | Improve | Fish | morphology/barriers to migration |  | Fisheries | Risley Mill, bypass channel/easement and habitat enhancement. | Improve modified habitats | Removal or easement of barriers to fish migration | Improvements to longitudinal connectivity | SU7381762353 | 6 km |  |  | landowaner | 30k |  | Contribute to improvement of 1 elelment | VC | Fish | No |  | 2 years
114 |  | Whitewater | no | Improve | Fish | morphology/barriers to migration |  | Fisheries | Dipley Mill complex (5 structures) technical and bypass, as well as habitat enhancement. | Improve modified habitats | Removal or easement of barriers to fish migration | Improvements to longitudinal connectivity | SU7423957695 | 3km |  |  | landowner | 50k |  | Contribute to improvement of 1 elelment | VC | Fish | No |  | 3 years |  |  |  |  | Add morphology help?! Technical fish passes will require morphology help as impoundin effect will remain - add £20 for gravel and woody debris
115 |  | Whitewater | no | Improve | Fish | morphology/barriers to migration |  | Fisheries | remove weir d/s Whitwater Mill, Scotts Farm and habitat enhancement. | Improve modified habitats | Removal or easement of barriers to fish migration | Improvements to longitudinal connectivity | SU7383755503 | 1km |  |  | Landowner Parish Council | 10k |  | Contribute to improvement of 1 elelment | VC | Fish | No |  | 2 years
116 |  | Whitewater | no | Improve | Fish | morphology/barriers to migration |  | Fisheries | technical and bypass Whitewater Mill and habitat enhancement. | Improve modified habitats | Removal or easement of barriers to fish migration | Improvements to longitudinal connectivity | SU7363455117 | 2.5km |  |  | landowner | 40k |  | Contribute to improvement of 1 elelment | VC | Fish | No |  | 2 years
117 | 17240 | Whitewater | no | Improve | Fish | morphology/barriers to migration |  | Fisheries | Poland Mill structures, technical fish pass or removal and habitat enhancement. | Improve modified habitats | Removal or easement of barriers to fish migration | Improvements to longitudinal connectivity | SU7428853140 | 2km |  |  | landowner | 100k |  | Contribute to improvement of 1 elelment | VC | Fish | No |  | 2 years
118 | 17240 | Whitewater | no | Improve | Fish | morphology/barriers to migration |  | Fisheries | Habitat enhancemets to ensure that weirs at Lodge Farm complex (7 weirs) and gauging weir ar e passable. | Improve modified habitats | Removal or easement of barriers to fish migration | Improvements to longitudinal connectivity | SU7341552346 | 1km |  |  | landowner | 50k |  | Contribute to improvement of 1 elelment | VC | Fish | No
119 | 17240 | Whitewater | no | Improve | Fish | morphology/barriers to migration |  | Fisheries | The Mill House, Warnborough Green. Lower weir and narrow stream to make the weir passable as well as habitat enhancement. | Improve modified habitats | Removal or easement of barriers to fish migration | Improvements to longitudinal connectivity | SU7315652146 | 500m |  |  | landowner | 50k |  | Contribute to improvement of 1 elelment | VC | Fish | No | [6 empty] | not a fish passage option, reducing impounding effect and narrowing channel.
120 | 17239 | Whitewater | no | Improve | Fish | morphology/barriers to migration |  | Fisheries | Castle Mill, lower wier and bypass channel and habitat enhancement. | Improve modified habitats | Removal or easement of barriers to fish migration | Improvements to longitudinal connectivity | SU7272651962 | 2km |  |  | landowner | 30k |  | Contribute to improvement of 1 elelment | VC | Fish | No
121 | 17239 | Whitewater | no | Improve | Fish | morphology/barriers to migration |  | Fisheries | Educate Mill owners on connectivity and flow. | Improve modified habitats | Removal or easement of barriers to fish migration | Improvements to longitudinal connectivity | waterbody |  |  |  | WWPS | 1000 |  | Contribute to improvement of 1 elelment | UC | Fish | No
129 | 17320 | Blackwater (Bramshill to Swallowfield | No | Improve | Fish | Barriers to migration |  | Fisheries | Enable fish passage at the Swallowfield gauging stations and consider replacing with non-impounding gauging equipment. | Improve modified habitats | Removal or easement of barriers to fish migration | Improvements to longitudinal connectivity | SU7309964786 | 5km |  |  | Hydrometry | 200k |  | Contribute to improvement of 1 elelment | VC | Fish | No |  | 1 year |  |  |  |  | Uncertain about the cost of replacement gauging equipments (of non-impounding nature). Baffle solutions would be lower cost but not prefferable
133 | 17330 | Loddon (Sherfield on Loddon to Swallowfield) | no | Improve | Fish | impoundments - no water storage/flow |  | Fisheries | Take the broadwater off-line | Improve modified habitats | Removal or easement of barriers to fish migration | Improvements to longitudinal connectivity | SU7047961821 | 5km |  |  | Estate / Landowner | 500k | unfunded | Contribute to improvement of 1 elelment | VC | Fish | No | WFD | 3 years
134 | 17330 | Loddon (Sherfield on Loddon to Swallowfield) | no | Improve | Fish | impoundments - no water storage/flow |  | Fisheries | Remove imounding structure at Priory Mill | Improve modified habitats | Removal or easement of barriers to fish migration | Improvements to longitudinal connectivity | SU7086464119 | 1km |  |  | Estate / Landowner | 10k | unfunded | Contribute to improvement of 1 elelment | QC | Fish | No | WFD | 1 year |  |  | No | Any
137 | 17330 | Loddon (Sherfield on Loddon to Swallowfield) | no | Improve | Phytobenthos | Sediment/impoundment |  | Fisheries | Remove imounding structure at Priory Mill | Improve modified habitats | Removal or easement of barriers to fish migration | Improvements to longitudinal connectivity | SU7086464119 | 1km |  |  | Estate / Landowner | 10k | unfunded | Contribute to improvement of 1 elelment | QC | Fish | No | WFD | 2 year |  |  | No | Any
138 | 17330 | Loddon (Sherfield on Loddon to Swallowfield) | no | Improve | Fish | INNS/Signal crayfish |  | Fisheries | Provide advice and training on identification, control and disposal of invasive non-native species to all relevant groups and encourage monitoring schemes. Rolled out through partner organisations BVCP, LFCC etc. Advertise the need for authorisation from the Environment Agency and that traps need to be compliant. | Control or manage invasive species. | Building awareness and understanding. | Seek sustainable and cost-effective methods for managing established invasions of species. | SU7255165634 (centre of catchment) | whole catchment |  |  | LFCC, NE, BVCP, WPS | 500/year |  | No deterioration | UC | Fish | No |  | 4 weeks | 2014-01-01 | Continuos | Yes | Any
144 | 23160 | Loddon (Sherfield on Loddon to Swallowfield) | no | Improve | Fish | morphology/barriers to migration |  | Fisheries | Improvements to bypass channel at Sheepbridge and enhance habitat | Improve modified habitats | Removal or easement of barriers to fish migration | Improvements to longitudinal connectivity | SU7188364976 | 5km |  |  | Landowner, Swallowfield fishing club, Hydrometry | 80k | unfunded | Contribute to improvement of more than 1 elelment | VC | Fish | No | WFD | 2 years |  |  | no | Any
144 | 23160 | Loddon (Sherfield on Loddon to Swallowfield) | no | Improve | Fish | morphology/barriers to migration |  | Fisheries | Sheep Bridge (2) weir removal/lowering or installation of fish pass as required and habitat enhancement | Improve modified habitats | Removal or easement of barriers to fish migration | Improvements to longitudinal connectivity | SU7203565318 | 5km |  |  | Hydrometry, Landowner | 150k | unfunded | Contribute to improvement of more than 1 elelment | QC | Fish | No | WFD | 2 years |  |  | no | Any
145 | 23160 | Loddon (Sherfield on Loddon to Swallowfield) | no | Improve | Fish | morphology/barriers to migration |  | Fisheries | Stanford End (3)weir removal/lowering or installation of fish pass as required and habitat enhancement | Improve modified habitats | Removal or easement of barriers to fish migration | Improvements to longitudinal connectivity | SU7072563071 | [6 empty] | Contribute to improvement of more than 1 elelment |  | Fish
146 | 23160 | Loddon (Sherfield on Loddon to Swallowfield) | no | Improve | Fish | morphology/barriers to migration |  | Fisheries | Stratfield Saye weir removal/lowering or installation of fish pass as required and habitat enhancement | Improve modified habitats | Removal or easement of barriers to fish migration | Improvements to longitudinal connectivity | SU6829659537 | 3km |  |  | Landowner | 100k | unfunded | Contribute to improvement of more than 1 elelment | QC | Fish | No | WFD | 2 years |  |  | no | any
147 | 23160 | Loddon (Sherfield on Loddon to Swallowfield) | no | Improve | Fish | morphology/barriers to migration |  | Fisheries | Tumbling Bay weirs (2)weir removal/lowering or installation of fish pass as required and habitat enhancement | Improve modified habitats | Removal or easement of barriers to fish migration | Improvements to longitudinal connectivity | SU7051462085 | 3km |  |  | Landowner | 150k | unfunded | Contribute to improvement of more than 1 elelment |  | Fish | No | WFD | 2 years |  |  | no | any
148 | 17330 | Loddon (Sherfield on Loddon to Swallowfield) | no | Improve | Fish | physical modification/barriers to migration |  | Fisheries | Improve habitats and connectivity at the Priory Mill complex, removal/lowering or installation of fish pass as required and habitat enhancement | Improve modified habitats | Removal or easement of barriers to fish migration | Improvements to longitudinal connectivity | SU7032363443 | 2km |  |  | landowner | 150k | unfunded | Contribute to improvement of more than 1 elelment | UC | Fish | No | WFD | 2 years |  |  | no | any
150 | 23130 | Emm Brook | yes | Improve | Mitigation measures assessment | Physical modification/land drainiage/operational management |  |  | Remove structure / install fish pass or bypass channel at Riverside walk, Wokingham and enhance river morphology | Improve modified habitats | Removal or easement of barriers to fish migration | Improvements to longitudinal connectivity | SU7983769265 | 3km |  |  | LA | 100k | unfunded | Contribute to improvement of more than 1 elelment | QC | fish | No | WFD | 2 years |  |  | no | any
152 | 23160 | Loddon (Swallowfield to Thames) | no | Improve | Fish | morphology/barriers to migration |  | Fisheries | Twyford Mill structures (2) weir removal/lowering or installation of fish pass as required and habitat enhancement | Improve modified habitats | Removal or easement of barriers to fish migration | Improvements to longitudinal connectivity | SU7852276002 | 4km |  |  | LA | 50k | unfunded | Contribute to improvement of 1 elelment | VC | Fish | No | WFD | 1 year |  |  | no | any
153 | 23160 | Loddon (Swallowfield to Thames) | no | Improve | Fish | morphology/barriers to migration |  | Fisheries | Weir feeding distributary u/s Sandford Bridge weir removal/lowering or installation of fish pass as required and habitat enhancement | Improve modified habitats | Removal or easement of barriers to fish migration | Improvements to longitudinal connectivity | SU7792772716 | 1km |  |  | Country Park / LA | 10k | unfunded | Contribute to improvement of 1 elelment | UC | Fish | No | WFD | 1 Year |  |  | no | any
154 | 23160 | Loddon (Swallowfield to Thames) | no | Improve | Fish | morphology/barriers to migration |  | Fisheries | Sindlesham Mill (3) weir removal/lowering or installation of fish pass as required and habitat enhancement | Improve modified habitats | Removal or easement of barriers to fish migration | Improvements to longitudinal connectivity | SU7668270272 | 3km |  |  | Farnham AC | 150k | unfunded | Contribute to improvement of 1 elelment | QC | Fish | No | WFD | 2 years |  |  | no | any
155 | 23160 | Loddon (Swallowfield to Thames) | no | No deterioration | Fish |  |  | Fisheries | St Patricks Stream, river and wetland project. Create a back water and use the gravel to create riffles and spawning habitat, include woody debris. | Improve modified habitats | Improve condition of channel bed and/or banks/shoreline | Preserve and restore habitats | SU7720477553 | 4 km |  |  | Twyford & District, New AC, residents, FCRM, Barbel Society, CLPS, | 30 k |  | Contribute to improvement of 1 elelment | VC | Fish |  | WFD, FCRM, private | 2 years |  |  | no | any | Will improve the Thames and Loddon Waterbodies. Design complete.
156 | 23160 | Loddon (Swallowfield to Thames) | no | Improve | Fish | morphology/barriers to migration |  | Fisheries | Sandford Farm weir removal/lowering or installation of fish pass as required and habitat enhancement | Improve modified habitats | Removal or easement of barriers to fish migration | Improvements to longitudinal connectivity | SU7824473743 | 3km |  |  | Developer / LA / Landowner | 150k | unfunded | Contribute to improvement of 1 elelment | VC | Fish | No | WFD, Private | 1 |  |  | no | any | Linked to large housing development and land decontamination adjacent to site
Note on A51: ssheridan: This line includes both gauging stations at Swallowfield because realistically they would be tackled as one project
Note on A58: ssheridan: Might need to modify this in light of current situation

## Sheet1
Upper Loddon
Remove/lower barrier or install fish pass as required, and habitat enhancement.
Investigat the passability of culverts around Basingstoke, opening culvert/installing fish easment as required (Eastrop Park)
Saunders field (headwater of the Loddon). Improve ressilience, wetlands, SUDS.
Introduction of gravels to create spawning opportunities for fish, and restore bed profile variation. Reduce shading to promote in channel vegetation growth and install woody debris in the channel.
Bank alterations to give channel width variation and two-stage channels. Introduction of meanders in straightened river sections.
Provide advice and training on identification, control and disposal of invasive non-native species to all relevant groups and encourage monitoring schemes. Rolled out through partner organisations BVCP, LFCC etc. Advertise the need for authorisation from the Environment Agency and that traps need to be compliant.
limit development at Basingstoke
Reduce pumping at West Ham, find alternative source.
Investigat the effects of West Ham on the ecology of the River Loddon between the abstraction points and the discharge outlet of Basingstoke STW
Investigat the effects of West Ham on the ecology of the Lower Bow Brook between the abstraction points and the discharge outlet of Basingstoke STW
Dual water supply system to new housing and potentiall old housing in Basingstoke (grey water and potable water) to reduce abstraction and volumes of water going through STW.
Investigat the effects of West Ham on the ecology of the Vyne Stream between the abstraction points and the discharge outlet of Basingstoke STW
Water company led water efficiency campaign
Run a targetted water efficiency campaign for all licensed abstractors in a waterbody.
Effluent re-use, duel water use.
Take the broadwater off-line
Use the Catchment Sensitive Farming initative to raise awareness and reduce pesticide\phosphate\sediment pollution in this waterbody.
Run an awareness campaign through on-farm demonstrations and undertake individual advisory farm visits on high risk farms, to reduce the amount of sediment, nutrients and chemicals entering a waterbody from farmland. Educate the farming
Creation of buffer strips to reduce land run off
Creation of buffer strips to reduce land run off

## Summary
| RFF | [6 empty] | Option details | [7 empty] | Partnership | [9 empty] | Time scale
1 | WB ID | WBID full | Name | HMWB | Improve or No deterioration | Stage 3 investigation associated with option (Element) | RFF ID (pressure/SWMI) | RBMP measure ID | Action to be written by (e.g. Fisheries) | Action description | Action type 1 | Action type 2 | Action type 3 | NGR (u/s, d/s or centre) | Length or river improved | Lead sector | Name of Organisation | Potential partners | Total cost | Funded or unfunded | Predicted improvement | Certainty (VC, QC, UC) | Eco benefit for HMWB | Is this part of a project? Project REF | Funding stream | Length of time to implement action | Planned start | Planned end | Is this a catchment wide solution | Climate change scenario (current, wet, dry, any) | Additional notes
17 | 17080 | GB106039017080 | Loddon (Basingstoke to Lyde) | yes | Improve | Fish | Morphology/physical modification |  | Fisheries | Bank alterations to give channel width variation and two-stage channels. Introduction of meanders in straightened river sections. | Improve modified habitats | Improve condition of channel bed and/or banks/shoreline | Bank rehabilitation / reprofiling | SU6614852985 | 200m |  |  | WLT, WTT | 30k | unfunded | Contribute to improvement of more than 1 elelment | VC | Fish | no | WFD | 1 year |  |  | no | any
18 | 17080 | GB106039017080 | Loddon (Basingstoke to Lyde) | yes | Improve | Fish | Morphology/physical modification |  | Fisheries | Bank alterations to give channel width variation and two-stage channels. Introduction of meanders in straightened river sections. | Improve modified habitats | Improve condition of channel bed and/or banks/shoreline | Bank rehabilitation / reprofiling | SU6519052612 to SU6803555235 | 80 m |  |  | TW angling club | 10 k | unfunded | Contribute to improvement of more than 1 elelment | VC | Fish | no | WFD | 1 year |  |  | no | any
2 | 17080 | GB106039017080 | Loddon (Basingstoke to Lyde) | yes | Improve | Fish | Morphology/barriers to migration |  | Fisheries | Bartons Mill weir complex removal/lowering or installation of fish pass as required and habitat enhancement | Improve modified habitats | Removal or easement of barriers to fish migration | Improvements to longitudinal connectivity | SU6616753092 | 2 km |  |  | Landowners, WTT, WLT, LFCC, angling club, B&DBC | 180K | unfunded | Contribute to improvement of more than 1 elelment | VC | Fish | no | WFD | 2 years |  |  | no | any
22 | 17080 | GB106039017080 | Loddon (Basingstoke to Lyde) | yes | Improve | Hydrology | Flow/groundwater abstraction |  |  | Dual water supply system to new housing and potentiall old housing in Basingstoke (grey water and potable water) to reduce abstraction and volumes of water going through STW. | To control or manage abstraction | Use alternative source/relocate abstraction or discharge | Change abstraction location |  |  |  |  | Council, residents, water companies, developers |  | Unfunded | Contribute to improvement of 1+ element | VC | [6 empty] | no | any
17 | 17080 | GB106039017080 | Loddon (Basingstoke to Lyde) | yes | Improve | Fish | Morphology/physical modification |  | Fisheries | Eastrop Park Partnership Project, deculvert the Loddon at Eastrop park and restore degraded habitats. | To improve modified habitat | Improvement to condition of channel/bed and/or banks/shoreline | Increase in-channel morphological diversity | SU6465452362 | 1 km |  |  | WTT B&DBC | 1 million | unfunded | Contribute to improvement of more than 1 elelment | VC | Fish | no | LA / WFD | 3 years |  |  | no | any | Current partnership established with LA. Feasibility stage complete.
23 | 17080 | GB106039017080 | Loddon (Basingstoke to Lyde) | yes | Improve | Hydrology | Flow/groundwater abstraction |  | Groundwater Hydrology | Effluent re-use, duel water use. | To control or manage abstraction | Use alternative source/relocate abstraction or discharge | Water efficiency activity |  |  |  |  | Council, residents, water companies, developers |  | Unfunded | Contribute to improvement of 1+ element | VC | [6 empty] | no | any
10 | 17080 | GB106039017080 | Loddon (Basingstoke to Lyde) | yes | Improve | Fish | Morphology/barriers to migration |  | FCRM | Flow diversion structure d/s Eastrop Park | Improve modified habitats | Removal or easement of barriers to fish migration | Improvements to longitudinal connectivity | SU6523352591 | 500 m |  |  | Landowners, WTT, WLT, LFCC, angling club, B&DBC | 30 | unfunded | Contribute to improvement of more than 1 elelment | VC | Fish | yes | FCRM | 1 year |  |  | no | any | Part of the Eastrop Park project.
18 | 17080 | GB106039017080 | Loddon (Basingstoke to Lyde) | yes | Improve | Fish | Morphology/physical modification |  | Fisheries | habitat enhancement d/s of notche weir 1 | Improve modified habitats | Improve condition of channel bed and/or banks/shoreline | Preserve and restore habitats | SU6689054024 | 100 m |  |  | Landowners, WTT, WLT, LFCC, angling club, B&DBC |  | unfunded | Contribute to improvement of more than 1 elelment | VC | Fish | yes | WFD | 1 year |  |  | no | any | in addition to the weir notching completed in 2013
3 | 17080 | GB106039017080 | Loddon (Basingstoke to Lyde) | yes | Improve | Fish | Morphology/barriers to migration |  | Fisheries | Install fish pass at Pyots Hill | Improve modified habitats | Removal or easement of barriers to fish migration | Improvements to longitudinal connectivity | SU6671153687 | 3 km |  |  | Landowners, WTT, WLT, LFCC, angling club, B&DBC | 15 k | unfunded | Contribute to improvement of more than 1 elelment | VC | Fish | no | WFD | 1 year |  |  | no | any
16 | 17080 | GB106039017080 | Loddon (Basingstoke to Lyde) | yes | Improve | Fish | Morphology/physical modification |  | Fisheries | Introduction of gravels to create spawning opportunities for fish, and restore bed profile variation. Reduce shading to promote in channel vegetation growth and install woody debris in the channel. | Improve modified habitats | Improve condition of channel bed and/or banks/shoreline | Preserve and restore habitats | SU6805055247 to SU6919757549 | 800 m |  |  | WTT WLT Gresham AC TW | 80 k | unfunded | Contribute to improvement of more than 1 elelment | VC | Fish | no | WFD | 1 year |  |  | no | any | 5 riffles over 4 km
22 | 17080 | GB106039017080 | Loddon (Basingstoke to Lyde) | yes | Improve | Hydrology | Flow/groundwater abstraction |  | Groundwater A&R F&B | Investigat the effects of West Ham on the ecology of the Lower Bow Brook between the abstraction points and the discharge outlet of Basingstoke STW | To control or manage abstraction | Use alternative source/relocate abstraction or discharge | Change abstraction location |  |  |  |  | Council, residents, water companies, developers | 50000 | Unfunded | No deterioration | VC | [6 empty] | no | any
21 | 17080 | GB106039017080 | Loddon (Basingstoke to Lyde) | yes | Improve | Hydrology | Flow/groundwater abstraction |  | Groundwater A&R F&B | Investigat the effects of West Ham on the ecology of the River Loddon between the abstraction points and the discharge outlet of Basingstoke STW | To control or manage abstraction | Use alternative source/relocate abstraction or discharge | Change abstraction location |  |  |  |  | Council, residents, water companies, developers |  | Unfunded | No deterioration | VC | [6 empty] | no | any
23 | 17080 | GB106039017080 | Loddon (Basingstoke to Lyde) | yes | Improve | Hydrology | Flow/groundwater abstraction |  | Groundwater A&R F&B | Investigat the effects of West Ham on the ecology of the Vyne Stream between the abstraction points and the discharge outlet of Basingstoke STW | To control or manage abstraction | Use alternative source/relocate abstraction or discharge | Change abstraction location |  |  |  |  | Council, residents, water companies, developers | 50000 | Unfunded | No deterioration | VC | [6 empty] | no | any
14 | 17080 | GB106039017080 | Loddon (Basingstoke to Lyde) | yes | Improve | Fish | Morphology/physical modification |  | FCRM | Investigat the passability of culverts around Basingstoke, opening culvert/installing fish easment as required (Eastrop Park) | Improve modified habitats | Removal or easement of barriers to fish migration | Improvements to longitudinal connectivity | SU6485952378 | 500 m |  |  | EA LA WTT WLT | 2 million | unfunded | Contribute to improvement of more than 1 elelment | VC | Fish | yes | FCRM/Partnership | 3 years |  |  | no | any | feasibility study complete
6 | 17080 | GB106039017080 | Loddon (Basingstoke to Lyde) | yes | Improve | Fish | Morphology/barriers to migration |  | Fisheries | LH channel weir d/s Lower Mill | Improve modified habitats | Removal or easement of barriers to fish migration | Improvements to longitudinal connectivity | SU6691353897 | 500 |  |  | land owner | 5000 | unfunded | Contribute to improvement of more than 1 elelment | VC | Fish | no | WFD | 1 year |  |  | no | any
19 | 17080 | GB106039017080 | Loddon (Basingstoke to Lyde) | yes | Improve | Hydrology | Flow/groundwater abstraction |  | Groundwater Hydrology | limit development at Basingstoke | To control or manage abstraction | Water Demand Management | Water efficiency activity |  |  |  |  | Council, residents, water companies, developers |  | Unfunded | Contribute to improvement of 1+ element | VC | [6 empty] | no | any
5 | 17080 | GB106039017080 | Loddon (Basingstoke to Lyde) | yes | Improve | Fish | Morphology/barriers to migration |  | Fisheries | Lower Mill weir removal/lowering or installation of fish pass as required and habitat enhancement | Improve modified habitats | Removal or easement of barriers to fish migration | Improvements to longitudinal connectivity | SU6689353810 | 1 km |  |  | Landowners, WTT, WLT, LFCC, angling club, B&DBC | 300 k | unfunded | Contribute to improvement of more than 1 elelment | VC | Fish | no | WFD | 2 years |  |  | no | any | technically diffuicult
3 | 17080 | GB106039017080 | Loddon (Basingstoke to Lyde) | yes | Improve | Fish | Morphology/barriers to migration |  | Fisheries | Old Basing fish farm weir removal/lowering or installation of fish pass as required and habitat enhancement | Improve modified habitats | Removal or easement of barriers to fish migration | Improvements to longitudinal connectivity | SU6649453304 | 500 m |  |  | Landowners, WTT, WLT, LFCC, angling club, B&DBC | 10K | unfunded | Contribute to improvement of more than 1 elelment | VC | Fish | no | WFD | 1year |  |  | no | any
9 | 17080 | GB106039017080 | Loddon (Basingstoke to Lyde) | yes | Improve | Fish | Morphology/barriers to migration |  | Fisheries | Old Basing LH channel redundant weir | Improve modified habitats | Removal or easement of barriers to fish migration | Improvements to longitudinal connectivity | SU6689154017 (weir 1 Old Basing) | 500 m |  |  | Landowners, WTT, WLT, LFCC, angling club, B&DBC | 0 | funded | Contribute to improvement of more than 1 elelment | VC | Fish | yes | WFD | 1 month | 2013 | 2014 | no | any
8 | 17080 | GB106039017080 | Loddon (Basingstoke to Lyde) | yes | Improve | Fish | Morphology/barriers to migration |  | Fisheries | Old Basing RH concrete weir | Improve modified habitats | Removal or easement of barriers to fish migration | Improvements to longitudinal connectivity | SU6718554042 (weir 2 Old Basing) | 500 m |  |  | Landowners, WTT, WLT, LFCC, angling club, B&DBC | 0 | funded | Contribute to improvement of more than 1 elelment | VC | Fish | yes | WFD | 1 month | 2013 | 2014 | no | any
4 | 17080 | GB106039017080 | Loddon (Basingstoke to Lyde) | yes | Improve | Fish | Morphology/barriers to migration |  | Fisheries | Overspill to side channel u/s Lower Mill | Improve modified habitats | Removal or easement of barriers to fish migration | Improvements to longitudinal connectivity | SU6671353686 | 500 m |  |  | Landowners, WTT, WLT, LFCC, angling club, B&DBC | 10K | funded | Contribute to improvement of more than 1 elelment | VC | Fish | yes | WFD | 1 year | 2013 | 2014 | no | any
19 | 17080 | GB106039017080 | Loddon (Basingstoke to Lyde) | yes | Improve | Fish | INNS/Signal crayfish |  | Fisheries | Provide advice and training on identification, control and disposal of invasive non-native species to all relevant groups and encourage monitoring schemes. Rolled out through partner organisations BVCP, LFCC etc. Advertise the need for authorisation from the Environment Agency and that traps need to be compliant. | Control or manage invasive species. | Building awareness and understanding. | Seek sustainable and cost-effective methods for managing established invasions of species. | SU7255165634 (centre of catchment) | whole catchment |  |  | LFCC, NE, BVCP, WPS | 500/year | unfunded | No deterioration | UC | Fish | No | WFD | 4 weeks | 2014-01-01 | Continuos | Yes | Any
20 | 17080 | GB106039017080 | Loddon (Basingstoke to Lyde) | yes | Improve | Hydrology | Flow/groundwater abstraction |  | Groundwater Hydrology | Reduce pumping at West Ham, find alternative source. | To control or manage abstraction | Water Demand Management | Water efficiency activity |  |  |  |  | Council, residents, water companies, developers |  | Unfunded | Contribute to improvement of 1+ element | VC | [6 empty] | no | any
7 | 17080 | GB106039017080 | Loddon (Basingstoke to Lyde) | yes | Improve | Fish | Morphology/barriers to migration |  | Fisheries | RH channel d/s Lower Mill | Improve modified habitats | Removal or easement of barriers to fish migration | Improvements to longitudinal connectivity | SU6718354038 | 500 |  |  | land owner | 5000 | unfunded | Contribute to improvement of more than 1 elelment | VC | Fish | no | WFD | 1 year |  |  | no | any
23 | 17080 | GB106039017080 | Loddon (Basingstoke to Lyde) | yes | Improve | Hydrology | Flow/groundwater abstraction |  | EM | Run a targetted water efficiency campaign for all licensed abstractors in a waterbody. | To control or manage abstraction | Water Demand Management | Water efficiency activity |  |  |  |  | Council, residents, water companies, developers | 1000 | Unfunded | No deterioration | UC | [6 empty] | no | any
15 | 17080 | GB106039017080 | Loddon (Basingstoke to Lyde) | yes | Improve | Fish | Morphology/physical modification |  | FCRM | Saunders field (headwater of the Loddon). Improve ressilience, wetlands, SUDS. | Improve modified habitats | Improvement to condition of riparian zone and/or wetland habitats | Preserve and restore habitats | SU6221052074 | 300 m |  |  | WLT | 50 k | unfunded | No deterioration |  | Fish | no | LA | 1 year |  |  | no | any
47 | 17080 | GB106039017080 | Vyne Stream | yes | Improve | Mitigation measure | physical modification/urbanisation |  | Fisheries Ops | Take The Vyne stillwater off-line to restore river gradient and morphology upstream. | Improve modified habitats | Improve condition of channel bed and/or banks/shoreline | Preserve and restore habitats | SU6363456910 | 4km |  |  | National Trust | 1000k | unfunded | Contribute to improvement of more than 1 elelment | VC | Fish | no | WFD | 3 years |  |  | no | any | Might not be feasible due to heritage issues
23 | 17080 | GB106039017080 | Loddon (Basingstoke to Lyde) | yes | Improve | Hydrology | Flow/groundwater abstraction |  | EM | Water company led water efficiency campaign | To control or manage abstraction | Water Demand Management | Water efficiency activity |  |  |  |  | Council, residents, water companies, developers | 1000 | Unfunded | No deterioration | UC | [6 empty] | no | any
24 | 17090 | GB106039017090 | Hart (Crondal to Elvetham) | no | Improve | Fish | Sediment/agricultural run off |  | EM | Creation of buffer strips to reduce land run off | To control or manage diffuse source inputs | Reduce diffuse pollution pathways (i.e. control entry to water environment) | Riparian management |  |  |  |  | EA, WLT, NFU , TW, UCL,KCL, RU, |  | unfunded | Contribute to improvement to 1+ element. | UC | [6 empty] | Yes | any
46 | 17090 | GB106039017090 | Hart (Crondal to Elvetham) | no | Improve | Phosphate | Unknown |  | EM | Creation of buffer strips to reduce sediments carrying hosphates efrom entering the river. | To control or manage diffuse source inputs | Reduce diffuse pollution pathways (i.e. control entry to water environment) | Riparian management |  |  |  |  | EA, WLT, NFU , TW, UCL,KCL, RU, |  | unfunded | Contribute to improvement to 1+ element. | UC | [6 empty] | Yes | any
36 | 17090 | GB106039017090 | Hart (Crondal to Elvetham) | no | Improve | Fish | Hydrology, natural conditions - low flow |  | Groundwater Hydrology | Effluent re-use, uel water use. | To control or manage abstraction | Use alternative source/relocate abstraction or discharge | Water efficiency activity |  |  |  |  | Council, residents, water companies, developers |  | Unfunded | Contribute to improvement of 1+ element | VC | [6 empty] | no | any
35 | 17090 | GB106039017090 | Hart (Crondal to Elvetham) | no | Improve | Fish | Morphology/barriers to fish migration |  | Fisheries | Elvetham Estate weir removal/lowering or installation of fish pass as required and habitat enhancement | Improve modified habitats | Removal or easement of barriers to fish migration | Improvements to longitudinal connectivity | SU7841556756 | 5 km |  |  | Hotel/Estate WTT WLT | 50 k (removal) | Unfunded | Contribute to improvement of more than 1 elelment | VC | Fish | No | WFD | 1 year |  |  | no | Any | removal prefered option
34 | 17090 | GB106039017090 | Hart (Crondal to Elvetham) | no | no deterioration | Fish | Morphology/barriers to fish migration |  | Fisheries | Elvetham to M3 improve morphology. New channel,Re meander, add Gravel riffles, bank reprofiling. | Improve modified habitats | Removal or easement of barriers to fish migration | Improvements to longitudinal connectivity | Hotel to M3 | 1 km |  |  | Highways, landowner/estate | 30 k | Unfunded | Contribute to improvement of more than 1 elelment | VC | Fish | No | WFD | 2 years |  |  | no | Any | WTT report as Stage 2 investigation. Add to database.
46 | 17090 | GB106039017090 | Hart (Crondal to Elvetham) | no | Improve | Phosphate | Unknown |  | EM | Fencing to reduce cattle poaching and sediments carrying hosphates efrom entering the river. | To control or manage diffuse source inputs | Reduce diffuse pollution pathways (i.e. control entry to water environment) | Field & Crop - Livestock |  |  |  |  | EA, WLT, NFU , TW, UCL,KCL, RU, |  | unfunded | Contribute to improvement to 1+ element. | UC | [6 empty] | Yes | any
36 | 17090 | GB106039017090 | Hart (Crondal to Elvetham) | no | Improve | Fish | Hydrology, natural conditions - low flow |  | Hydrology | Investigate Boxalls Lane, Oak Park Golf Club and Itchell puming station effect on biology. | To control or manage abstraction | Water Demand Management | Water efficiency activity |  |  |  |  | Council, residents, water companies, developers |  | Unfunded | Contribute to improvement of 1+ element | VC | [6 empty] | no | any
32 | 17090 | GB106039017090 | Hart (Crondal to Elvetham) | no | Improve | Fish | Morphology/barriers to fish migration |  | Fisheries | larinier or bristle or pre barrage on weir structure at Pilcot Mill and habitat enhancement. | Improve modified habitats | Removal or easement of barriers to fish migration | Improvements to longitudinal connectivity | SU7864252793 | 4 km |  |  | Mill owner WTT WLT SE water | 40 k | Unfunded | Contribute to improvement of more than 1 elelment | VC | Fish | No | WFD | 1 year |  |  | no | Any | improve hart and itchell brook
33 | 17090 | GB106039017090 | Hart (Crondal to Elvetham) | no | Improve | Fish | Morphology/barriers to fish migration |  | Fisheries | Pre barrage fish pass at Basingstoke canal culvert and habitat enhancement. | Improve modified habitats | Removal or easement of barriers to fish migration | Improvements to longitudinal connectivity | SU7943851601 | 3 km |  |  | WTT WLT BCA | 5 k | Unfunded | Contribute to improvement of more than 1 elelment | VC | Fish | No | WFD | 1 year |  |  | no | Any | poor access
30 | 17090 | GB106039017090 | Hart (Crondal to Elvetham) | no | Improve | Fish | INNS/Signal crayfish |  | Fisheries | Provide advice and training on identification, control and disposal of invasive non-native species to all relevant groups and encourage monitoring schemes. Rolled out through partner organisations BVCP, LFCC etc. Advertise the need for authorisation from the Environment Agency and that traps need to be compliant. | Control or manage invasive species. | Building awareness and understanding. | Seek sustainable and cost-effective methods for managing established invasions of species. | SU7255165634 (centre of catchment) | whole catchment |  |  | LFCC, NE, BVCP, WPS | 500/year | Unfunded | No deterioration | UC | Fish | No |  | 4 weeks | 2014-01-01 | Continuos | Yes | Any
31 | 17090 | GB106039017090 | Hart (Crondal to Elvetham) | no | Improve | Hydrology | flow/grounwater abstraction |  | Hydrology Groundwater | Reduce abstraction impact by 3 Ml/d if further investigation indicates need | To control or manage abstraction | Water Demand Management | Water efficiency activity |  |  |  |  | Council, residents, water companies, developers |  | Unfunded | Contribute to improvement of 1+ element | VC | [6 empty] | no | any
36 | 17090 | GB106039017090 | Hart (Crondal to Elvetham) | no | Improve | Fish | Hydrology, natural conditions - low flow |  | EM | Run a targetted water efficiency campaign for all licensed abstractors in a waterbody. | To control or manage abstraction | Water Demand Management | Water efficiency activity |  |  |  |  | Council, residents, water companies, developers | 1000 | Unfunded | No deterioration | UC | [6 empty] | no | any
24 | 17090 | GB106039017090 | Hart (Crondal to Elvetham) | no | Improve | Fish | Sediment/agricultural run off |  | EM | Run an awareness campaign through on-farm demonstrations and undertake individual advisory farm visits on high risk farms, to reduce the amount of sediment, nutrients and chemicals entering a waterbody from farmland. Educate the farming | To control or manage diffuse source inputs | Reduce diffuse pollution at source | Field & Crop - Arable soils |  |  |  |  | EA, WLT, NFU , TW, UCL,KCL, RU, |  | unfunded | Contribute to improvement to 1+ element. | UC | [6 empty] | Yes | any
24 | 17090 | GB106039017090 | Hart (Crondal to Elvetham) | no | Improve | Fish | Sediment/agricultural run off |  | EM | Use the Catchment Sensitive Farming initative to raise awareness and reduce pesticide\phosphate\sediment pollution in this waterbody. | To control or manage diffuse source inputs | Reduce diffuse pollution at source | Field & Crop - Arable soils |  |  |  |  | EA, WLT, NFU , TW, UCL,KCL, RU, |  | unfunded | Contribute to improvement to 1+ element. | UC | [6 empty] | Yes | any
46 | 17090 | GB106039017090 | Hart (Crondal to Elvetham) | no | Improve | Phosphate | Unknown |  | EM | Use the Catchment Sensitive Farming initative to raise awareness and reduce pesticide\phosphate\sediment pollution in this waterbody. | To control or manage diffuse source inputs | Reduce diffuse pollution at source | Field & Crop - Arable soils |  |  |  |  | EA, WLT, NFU , TW, UCL,KCL, RU, |  | unfunded | Contribute to improvement to 1+ element. | UC | [6 empty] | Yes | any
36 | 17090 | GB106039017090 | Hart (Crondal to Elvetham) | no | Improve | Fish | Hydrology, natural conditions - low flow |  | EM | Water company led water efficiency campaign | To control or manage abstraction | Water Demand Management | Water efficiency activity |  |  |  |  | Council, residents, water companies, developers | 1000 | Unfunded | No deterioration | UC | [6 empty] | no | any
48 | 17110 | GB106039017110 | Vyne Stream | yes | Improve | Phosphate | Diffuse/agriculture |  | EM | Creation of buffer strips to reduce land run off | To control or manage diffuse source inputs | Reduce diffuse pollution pathways (i.e. control entry to water environment) | Riparian management |  |  |  |  | EA, WLT, NFU , TW, UCL,KCL, RU, |  | unfunded | Contribute to improvement to 1+ element. | UC | [6 empty] | Yes | any
48 | 17110 | GB106039017110 | Vyne Stream | yes | Improve | Phosphate | Diffuse/agriculture |  | EM | Fencing to reduce cattle poaching and sediments carrying hosphates efrom entering the river. | To control or manage diffuse source inputs | Reduce diffuse pollution pathways (i.e. control entry to water environment) | Field & Crop - Livestock |  |  |  |  | EA, WLT, NFU , TW, UCL,KCL, RU, |  | unfunded | Contribute to improvement to 1+ element. | UC | [6 empty] | Yes | any
48 | 17110 | GB106039017110 | Vyne Stream | yes | Improve | Phosphate | Diffuse/agriculture |  | EM | Run an awareness campaign through on-farm demonstrations and undertake individual advisory farm visits on high risk farms, to reduce the amount of sediment, nutrients and chemicals entering a waterbody from farmland. Educate the farming | To control or manage diffuse source inputs | Reduce diffuse pollution at source | Field & Crop - Arable soils |  |  |  |  | EA, WLT, NFU , TW, UCL,KCL, RU, |  | unfunded | Contribute to improvement to 1+ element. | UC | [6 empty] | Yes | any
48 | 17110 | GB106039017110 | Vyne Stream | yes | Improve | Phosphate | Diffuse/agriculture |  | EM | Use the Catchment Sensitive Farming initative to raise awareness and reduce pesticide\phosphate\sediment pollution in this waterbody. | To control or manage diffuse source inputs | Reduce diffuse pollution at source | Field & Crop - Arable soils |  |  |  |  | EA, WLT, NFU , TW, UCL,KCL, RU, |  | unfunded | Contribute to improvement to 1+ element. | UC | [6 empty] | Yes | any
51 | 17120 | GB106039017120 | Fleet Brook | yes | Improve | Invertebrates | DO/diffuse/mixed drainage |  | EM | Businesses and households should ensure all applies are connected to the right drain. For example dish washer, washing machine etc are commonly just plumbed into the surface water drains. | To control or manage point source inputs | Reduce point source pollution at source | Sewerage system re-design and rebuild |  |  |  |  | EA, WLT, NFU , TW, UCL,KCL, RU, |  | unfunded | Contribute to improvement to 1+ element. | UC | [6 empty] | Yes | any
57 | 17120 | GB106039017120 | Fleet Brook | yes | Improve | Fish | DO/diffuse/mixed drainage |  | EM | Businesses and households should ensure all applies are connected to the right drain. For example dish washer, washing machine etc are commonly just plumbed into the surface water drains. | To control or manage point source inputs | Reduce point source pollution at source | Sewerage system re-design and rebuild |  |  |  |  | EA, WLT, NFU , TW, UCL,KCL, RU, |  | unfunded | Contribute to improvement to 1+ element. | UC | [6 empty] | Yes | any
58 | 17120 | GB106039017120 | Fleet Brook | yes | Improve | Fish | Sediment/agricultural run off |  | EM | Creation of buffer strips to reduce land run off | To control or manage diffuse source inputs | Reduce diffuse pollution pathways (i.e. control entry to water environment) | Riparian management |  |  |  |  | EA, WLT, NFU , TW, UCL,KCL, RU, |  | unfunded | Contribute to improvement to 1+ element. | UC | [6 empty] | Yes | any
51 | 17120 | GB106039017120 | Fleet Brook | yes | Improve | Invertebrates | DO/diffuse/mixed drainage |  | EM | Ensure that all discharges from urban areas are being discharged to the correct drainage system. For example, All car washes should be discharged to foul sewer under a consent from the local water authority. | To control or manage point source inputs | Reduce point source pathways (i.e. control entry to water environment) | Sewerage system re-design and rebuild |  |  |  |  | EA, WLT, NFU , TW, UCL,KCL, RU, |  | unfunded | Contribute to improvement to 1+ element. | UC | [6 empty] | Yes | any
57 | 17120 | GB106039017120 | Fleet Brook | yes | Improve | Fish | DO/diffuse/mixed drainage |  | EM | Ensure that all discharges from urban areas are being discharged to the correct drainage system. For example, All car washes should be discharged to foul sewer under a consent from the local water authority. | To control or manage point source inputs | Reduce point source pathways (i.e. control entry to water environment) | Sewerage system re-design and rebuild |  |  |  |  | EA, WLT, NFU , TW, UCL,KCL, RU, |  | unfunded | Contribute to improvement to 1+ element. | UC | [6 empty] | Yes | any
49 | 17120 | GB106039017120 | Fleet Brook | yes | Improve | Mitigation measure | physical modification/urbanisation |  | Fisheries Ops | Install LWD, manage canopy and introduce gravel between Mwy and Turners Green | Improve modified habitats | Improve condition of channel bed and/or banks/shoreline | Preserve and restore habitats | SU8078156569 | 2km |  |  | Thames Water | 30k | unfunded | Contribute to improvement of more than 1 elelment | QC | Fish | no | WFD | 1 year |  |  | no | any
50 | 17120 | GB106039017120 | Fleet Brook | yes | Improve | Mitigation measure | physical modification/urbanisation |  | EM | PP MOD | To control or manage diffuse source inputs | Reduce diffuse pollution at source | Surface run-off & drainage management | SU8375252243 | 5.7 km |  |  | MOD, HWLT Fleet Pond Sociecty HDC | >10000 |  | Overall improvement, but below GES or GEP | UC | [6 empty] | no | wet
58 | 17120 | GB106039017120 | Fleet Brook | yes | Improve | Fish | Sediment/agricultural run off |  | EM | Run an awareness campaign through on-farm demonstrations and undertake individual advisory farm visits on high risk farms, to reduce the amount of sediment, nutrients and chemicals entering a waterbody from farmland. Educate the farming | To control or manage diffuse source inputs | Reduce diffuse pollution at source | Field & Crop - Arable soils |  |  |  |  | EA, WLT, NFU , TW, UCL,KCL, RU, |  | unfunded | Contribute to improvement to 1+ element. | UC | [6 empty] | Yes | any
58 | 17120 | GB106039017120 | Fleet Brook | yes | Improve | Fish | Sediment/agricultural run off |  | EM | Use the Catchment Sensitive Farming initative to raise awareness and reduce pesticide\phosphate\sediment pollution in this waterbody. | To control or manage diffuse source inputs | Reduce diffuse pollution at source | Field & Crop - Arable soils |  |  |  |  | EA, WLT, NFU , TW, UCL,KCL, RU, |  | unfunded | Contribute to improvement to 1+ element. | UC | [6 empty] | Yes | any
59 | 17130 | GB106039017130 | Cove Brook | yes | Improve | Invertebrates | physical modification/development of infrastructure |  | Fisheries Ops | Bank alterations to give channel width variation and two-stage channels. Introduction of meanders in straightened river sections. | Improve modified habitats | Improve condition of channel bed and/or banks/shoreline | Bank rehabilitation / reprofiling |  |  |  |  | BVCP, Cove Brook Group, LA |  | unfunded | Contribute to improvement of more than 1 elelment | VC | Fish | no | WFD | 1 year |  |  | no | any
72 | 17130 | GB106039017130 | Cove Brook | yes | Improve | Fish | Morphology/physical modification/Flood prevention structures |  | Fisheries | Bank alterations to give channel width variation and two-stage channels. Introduction of meanders in straightened river sections. | Improve modified habitats | Improve condition of channel bed and/or banks/shoreline | Bank rehabilitation / reprofiling |  |  |  |  | BVCP, Cove Brook Group, LA |  | unfunded | Contribute to improvement of more than 1 elelment | VC | Fish | no | WFD | 1 year |  |  | no | any
61 | 17130 | GB106039017130 | Cove Brook | yes | Improve | Invertebrates | DO/diffuse/mixed drainage |  | EM | Businesses and households should ensure all applies are connected to the right drain. For example dish washer, washing machine etc are commonly just plumbed into the surface water drains. | To control or manage point source inputs | Reduce point source pollution at source | Sewerage system re-design and rebuild |  |  |  |  | EA, WLT, NFU , TW, UCL,KCL, RU, |  | unfunded | Contribute to improvement to 1+ element. | UC | [6 empty] | Yes | any
68 | 17130 | GB106039017130 | Cove Brook | yes | Improve | Fish | Iron/diffuse/mixed drainage |  | EM | Businesses and households should ensure all applies are connected to the right drain. For example dish washer, washing machine etc are commonly just plumbed into the surface water drains. | To control or manage point source inputs | Reduce point source pollution at source | Sewerage system re-design and rebuild |  |  |  |  | EA, WLT, NFU , TW, UCL,KCL, RU, |  | unfunded | Contribute to improvement to 1+ element. | UC | [6 empty] | Yes | any
60 | 17130 | GB106039017130 | Cove Brook | yes | Improve | Fish | Iron/diffuse/contaminated land |  | EM | Creation of buffer strips to reduce land run off | To control or manage diffuse source inputs | Reduce diffuse pollution pathways (i.e. control entry to water environment) | Riparian management |  |  |  |  | EA, WLT, NFU , TW, UCL,KCL, RU, |  | unfunded | Contribute to improvement to 1+ element. | UC | [6 empty] | Yes | any
61 | 17130 | GB106039017130 | Cove Brook | yes | Improve | Invertebrates | DO/diffuse/mixed drainage |  | EM | Ensure that all discharges from urban areas are being discharged to the correct drainage system. For example, All car washes should be discharged to foul sewer under a consent from the local water authority. | To control or manage point source inputs | Reduce point source pathways (i.e. control entry to water environment) | Sewerage system re-design and rebuild |  |  |  |  | EA, WLT, NFU , TW, UCL,KCL, RU, |  | unfunded | Contribute to improvement to 1+ element. | UC | [6 empty] | Yes | any
68 | 17130 | GB106039017130 | Cove Brook | yes | Improve | Fish | Iron/diffuse/mixed drainage |  | EM | Ensure that all discharges from urban areas are being discharged to the correct drainage system. For example, All car washes should be discharged to foul sewer under a consent from the local water authority. | To control or manage point source inputs | Reduce point source pathways (i.e. control entry to water environment) | Sewerage system re-design and rebuild |  |  |  |  | EA, WLT, NFU , TW, UCL,KCL, RU, |  | unfunded | Contribute to improvement to 1+ element. | UC | [6 empty] | Yes | any
71 | 17130 | GB106039017130 | Cove Brook | yes | Improve | Fish | Morphology/physical modification/Flood prevention structures |  | Fisheries | Introduction of gravels to create spawning opportunities for fish, and restore bed profile variation. Reduce shading to promote in channel vegetation growth and install woody debris in the channel. | Improve modified habitats | Improve condition of channel bed and/or banks/shoreline | Preserve and restore habitats | SU8558855587 | 2km |  |  | BVCP, Cove Brook Group, LA | 40k | unfunded | Contribute to improvement of more than 1 elelment | VC | Fish | no | WFD | 1 year |  |  | no | any
73 | 17130 | GB106039017130 | Cove Brook | yes | Improve | Fish | Barriers to fish migration |  | Fisheries | weir removal/lowering or installation of fish pass as required and habitat enhancement | Improve modified habitats | Removal or easement of barriers to fish migration | Improvements to longitudinal connectivity | SU8555756773 | 3 km |  |  | BVCP, Cove Brook Group, LA |  | unfunded | Contribute to improvement of more than 1 elelment | VC | Fish | no | WFD | 1 year |  |  | no | any
79 | 17150 | GB106039017150 | Loddon (Hartley Wespall to Sherfield on Loddon) | no | Improve | Expert judgement | physical modification/barriers to migration |  | Fisheries | Fish pass or bypass channel on Longbridge Mill sluice/weir | Improve modified habitats | Removal or easement of barriers to fish migration | Improvements to longitudinal connectivity | SU6835758189 | 11 km |  |  | Estate/landowner, brewery | 150k | unfunded | Contribute to improvement of more than 1 elelment | VC | Fish | No | WFD | 2 years |  |  | no | any | improves outside of this waterbody (Loddon (7km) and Lyde (4km)
82 | 17150 | GB106039017150 | Loddon (Hartley Wespall to Sherfield on Loddon) | no | Improve | Expert judgement | impoundments - no water storage/flow |  | Hydrology Fisheries | Remove Longbridge Mill sluice/weir | Improve modified habitats | Removal or easement of barriers to fish migration | Improvements to longitudinal connectivity | SU6835758189 | 11 km |  |  | Estate/landowner, brewery | £100k | unfunded | Contribute to improvement of more than 1 elelment | VC | Fish, WQ | No | WFD | 2 years |  |  | no | Any | improves outside of this waterbody (Loddon (7km) and Lyde (4km). This is a working mill; it would require significant negotiations to get Landowner agreement to remove the impounding structure (however, this would be the preferred option for the site).
78 | 17160 | GB106039017160 | Bow Brook ( Pamber End to Sherfield Green) | no | Improve | Phosphate | Diffuse/agriculture |  | EM | Creation of buffer strips to reduce land run off | To control or manage diffuse source inputs | Reduce diffuse pollution pathways (i.e. control entry to water environment) | Riparian management |  |  |  |  | EA, WLT, NFU , TW, UCL,KCL, RU, |  | unfunded | Contribute to improvement to 1+ element. | UC | [6 empty] | Yes | any
78 | 17160 | GB106039017160 | Bow Brook ( Pamber End to Sherfield Green) | no | Improve | Phosphate | Diffuse/agriculture |  | EM | Run an awareness campaign through on-farm demonstrations and undertake individual advisory farm visits on high risk farms, to reduce the amount of sediment, nutrients and chemicals entering a waterbody from farmland. Educate the farming | To control or manage diffuse source inputs | Reduce diffuse pollution at source | Field & Crop - Arable soils |  |  |  |  | EA, WLT, NFU , TW, UCL,KCL, RU, |  | unfunded | Contribute to improvement to 1+ element. | UC | [6 empty] | Yes | any
78 | 17160 | GB106039017160 | Bow Brook ( Pamber End to Sherfield Green) | no | Improve | Phosphate | Diffuse/agriculture |  | EM | Use the Catchment Sensitive Farming initative to raise awareness and reduce pesticide\phosphate\sediment pollution in this waterbody. | To control or manage diffuse source inputs | Reduce diffuse pollution at source | Field & Crop - Arable soils |  |  |  |  | EA, WLT, NFU , TW, UCL,KCL, RU, |  | unfunded | Contribute to improvement to 1+ element. | UC | [6 empty] | Yes | any
101 | 17180 | GB106039017180 | Blackwater (Aldershot to Cove Brook) | yes | Improve | Fish | Barriers to migration |  | Fisheries | Badshot Lea Lake outlet. Take Badshot Lea offline. | Improve modified habitats | Removal or easement of barriers to fish migration | Improvements to longitudinal connectivity | SU8649249177 | 2 km |  |  | LFCC, BVCP, LA | 100k | unfunded | Contribute to improvement of more than 1 elelment | VC | Fish | no | WFD | 3 years |  |  | no | any
93 | 17180 | GB106039017180 | Blackwater (Aldershot to Cove Brook) | yes | Improve | Invertebrates | DO/diffuse/mixed drainage |  | EM | Businesses and households should ensure all applies are connected to the right drain. For example dish washer, washing machine etc are commonly just plumbed into the surface water drains. | To control or manage point source inputs | Reduce point source pollution at source | Sewerage system re-design and rebuild |  |  |  |  | EA, WLT, NFU , TW, UCL,KCL, RU, |  | unfunded | Contribute to improvement to 1+ element. | UC | [6 empty] | Yes | any
103 | 17180 | GB106039017180 | Blackwater (Aldershot to Cove Brook) | yes | Improve | Fish | DO/diffuse/mixed drainage |  | EM | Businesses and households should ensure all applies are connected to the right drain. For example dish washer, washing machine etc are commonly just plumbed into the surface water drains. | To control or manage point source inputs | Reduce point source pollution at source | Sewerage system re-design and rebuild |  |  |  |  | EA, WLT, NFU , TW, UCL,KCL, RU, |  | unfunded | Contribute to improvement to 1+ element. | UC | [6 empty] | Yes | any
97 | 17180 | GB106039017180 | Blackwater (Aldershot to Cove Brook) | yes | Improve | Invertebrates | Ammonia/Diffuse pollution/contaminated land |  | EM | Creation of buffer strips to reduce land run off | To control or manage diffuse source inputs | Reduce diffuse pollution pathways (i.e. control entry to water environment) | Riparian management |  |  |  |  | EA, WLT, NFU , TW, UCL,KCL, RU, |  | unfunded | Contribute to improvement to 1+ element. | UC | [6 empty] | Yes | any
102 | 17180 | GB106039017180 | Blackwater (Aldershot to Cove Brook) | yes | Improve | Fish | ammonia/diffuse contaminated land |  | EM | Creation of buffer strips to reduce land run off | To control or manage diffuse source inputs | Reduce diffuse pollution pathways (i.e. control entry to water environment) | Riparian management |  |  |  |  | EA, WLT, NFU , TW, UCL,KCL, RU, |  | unfunded | Contribute to improvement to 1+ element. | UC | [6 empty] | Yes | any
85 | 17180 | GB106039017180 | Blackwater (Aldershot to Cove Brook) | yes | Improve | Phosphate | Point source/industrial discharge |  | EM | Ensure that all discharges from urban areas are being discharged to the correct drainage system. For example, All car washes should be discharged to foul sewer under a consent from the local water authority. | To control or manage point source inputs | Reduce point source pathways (i.e. control entry to water environment) | Sewerage system re-design and rebuild |  |  |  |  | EA, WLT, NFU , TW, UCL,KCL, RU, |  | unfunded | Contribute to improvement to 1+ element. | UC | [6 empty] | Yes | any
93 | 17180 | GB106039017180 | Blackwater (Aldershot to Cove Brook) | yes | Improve | Invertebrates | DO/diffuse/mixed drainage |  | EM | Ensure that all discharges from urban areas are being discharged to the correct drainage system. For example, All car washes should be discharged to foul sewer under a consent from the local water authority. | To control or manage point source inputs | Reduce point source pathways (i.e. control entry to water environment) | Sewerage system re-design and rebuild |  |  |  |  | EA, WLT, NFU , TW, UCL,KCL, RU, |  | unfunded | Contribute to improvement to 1+ element. | UC | [6 empty] | Yes | any
103 | 17180 | GB106039017180 | Blackwater (Aldershot to Cove Brook) | yes | Improve | Fish | DO/diffuse/mixed drainage |  | EM | Ensure that all discharges from urban areas are being discharged to the correct drainage system. For example, All car washes should be discharged to foul sewer under a consent from the local water authority. | To control or manage point source inputs | Reduce point source pathways (i.e. control entry to water environment) | Sewerage system re-design and rebuild |  |  |  |  | EA, WLT, NFU , TW, UCL,KCL, RU, |  | unfunded | Contribute to improvement to 1+ element. | UC | [6 empty] | Yes | any
99 | 17180 | GB106039017180 | Blackwater (Aldershot to Cove Brook) | yes | Improve | Fish | Morphology/physical modification |  | FCRM | Introduction of gravels to create spawning opportunities for fish, and restore bed profile variation. Reduce shading to promote in channel vegetation growth and install woody debris in the channel. Bank alterations to give channel width variation and two-stage channels. Introduction of meanders in straightened river sections. | Improve modified habitats | Improve condition of channel bed and/or banks/shoreline | Preserve and restore habitats | Farnham Quarry Phase 3 |  |  |  | Hansons BVCP EA WTT | 60k |  |  |  | Fish |  | FCRM
100 | 17180 | GB106039017180 | Blackwater (Aldershot to Cove Brook) | yes | Improve | Fish | Morphology/physical modification |  | Fisheries | Introduction of gravels to create spawning opportunities for fish, and restore bed profile variation. Reduce shading to promote in channel vegetation growth and install woody debris in the channel. Bank alterations to give channel width variation and two-stage channels. Introduction of meanders in straightened river sections. | Improve modified habitats | Improve condition of channel bed and/or banks/shoreline | Preserve and restore habitats | SU8594659275 and SU8812348988 | 1 km |  |  | LFCC, BVCP | 40k for 2sites. | unfunded | Contribute to improvement of more than 1 elelment | VC | Fish | no | WFD | 1 year |  |  | no | any
105 | 17180 | GB106039017180 | Blackwater (Aldershot to Cove Brook) | yes | Improve | Invertebrates | Morphology/physical modification |  | Fisheries | Morphology options will help. | [10 empty] | Contribute to improvement of more than 1 elelment |  | invertebrates
83 | 17180 | GB106039017180 | Blackwater (Aldershot to Cove Brook) | yes | No deterioration | Invertebrates | INNS/Signal crayfish |  | Fisheries | Provide advice and training on identification, control and disposal of invasive non-native species to all relevant groups and encourage monitoring schemes. Rolled out through partner organisations BVCP, LFCC etc. Advertise the need for authorisation from the Environment Agency and that traps need to be compliant. | Control or manage invasive species. | Building awareness and understanding. | Seek sustainable and cost-effective methods for managing established invasions of species. | SU8502749906 to SU8632958331 | 15 km |  |  | LFCC, NE, BVCP, WPS | 500/year |  | No deterioration | UC |  | No |  | 4 weeks | 2014-01-01 | Continuos | Yes | Any
84 | 17180 | GB106039017180 | Blackwater (Aldershot to Cove Brook) | yes | No deterioration | Fish | INNS/Signal crayfish |  | Fisheries | Provide advice and training on identification, control and disposal of invasive non-native species to all relevant groups and encourage monitoring schemes. Rolled out through partner organisations BVCP, LFCC etc. Advertise the need for authorisation from the Environment Agency and that traps need to be compliant. | Control or manage invasive species. | Building awareness and understanding. | Seek sustainable and cost-effective methods for managing established invasions of species. | SU8502749906 to SU8632958331 | 15 km |  |  | LFCC, NE, BVCP, WPS | 500/year |  | No deterioration | UC | Fish | No |  | 4 weeks | 2014-01-01 | Continuos | Yes | Any
97 | 17180 | GB106039017180 | Blackwater (Aldershot to Cove Brook) | yes | Improve | Invertebrates | Ammonia/Diffuse pollution/contaminated land |  | EM | Run an awareness campaign through on-farm demonstrations and undertake individual advisory farm visits on high risk farms, to reduce the amount of sediment, nutrients and chemicals entering a waterbody from farmland. Educate the farming | To control or manage diffuse source inputs | Reduce diffuse pollution at source | Field & Crop - Arable soils |  |  |  |  | EA, WLT, NFU , TW, UCL,KCL, RU, |  | unfunded | Contribute to improvement to 1+ element. | UC | [6 empty] | Yes | any
102 | 17180 | GB106039017180 | Blackwater (Aldershot to Cove Brook) | yes | Improve | Fish | ammonia/diffuse contaminated land |  | EM | Run an awareness campaign through on-farm demonstrations and undertake individual advisory farm visits on high risk farms, to reduce the amount of sediment, nutrients and chemicals entering a waterbody from farmland. Educate the farming | To control or manage diffuse source inputs | Reduce diffuse pollution at source | Field & Crop - Arable soils |  |  |  |  | EA, WLT, NFU , TW, UCL,KCL, RU, |  | unfunded | Contribute to improvement to 1+ element. | UC | [6 empty] | Yes | any
97 | 17180 | GB106039017180 | Blackwater (Aldershot to Cove Brook) | yes | Improve | Invertebrates | Ammonia/Diffuse pollution/contaminated land |  | EM | Use the Catchment Sensitive Farming initative to raise awareness and reduce pesticide\phosphate\sediment pollution in this waterbody. | To control or manage diffuse source inputs | Reduce diffuse pollution at source | Field & Crop - Arable soils |  |  |  |  | EA, WLT, NFU , TW, UCL,KCL, RU, |  | unfunded | Contribute to improvement to 1+ element. | UC | [6 empty] | Yes | any
102 | 17180 | GB106039017180 | Blackwater (Aldershot to Cove Brook) | yes | Improve | Fish | ammonia/diffuse contaminated land |  | EM | Use the Catchment Sensitive Farming initative to raise awareness and reduce pesticide\phosphate\sediment pollution in this waterbody. | To control or manage diffuse source inputs | Reduce diffuse pollution at source | Field & Crop - Arable soils |  |  |  |  | EA, WLT, NFU , TW, UCL,KCL, RU, |  | unfunded | Contribute to improvement to 1+ element. | UC | [6 empty] | Yes | any
120 | 17240 | GB106039017240 | Whitewater | no | Improve | Fish | morphology/barriers to migration |  | Fisheries | Castle Mill, lower wier and bypass channel and habitat enhancement. | Improve modified habitats | Removal or easement of barriers to fish migration | Improvements to longitudinal connectivity | SU7272651962 | 2km |  |  | landowner | 30k |  | Contribute to improvement of 1 elelment | VC | Fish | No
111 | 17240 | GB106039017240 | Whitewater | no | Improve | Fish | Sediment/mixed agricultural run off |  | EM | Creation of buffer strips to reduce land run off | To control or manage diffuse source inputs | Reduce diffuse pollution pathways (i.e. control entry to water environment) | Riparian management |  |  |  |  | EA, WLT, NFU , TW, UCL,KCL, RU, |  | unfunded | Contribute to improvement to 1+ element. | UC | [6 empty] | Yes | any
114 | 17240 | GB106039017240 | Whitewater | no | Improve | Fish | morphology/barriers to migration |  | Fisheries | Dipley Mill complex (5 structures) technical and bypass, as well as habitat enhancement. | Improve modified habitats | Removal or easement of barriers to fish migration | Improvements to longitudinal connectivity | SU7423957695 | 3km |  |  | landowner | 50k |  | Contribute to improvement of 1 elelment | VC | Fish | No |  | 3 years |  |  |  |  | Add morphology help?! Technical fish passes will require morphology help as impoundin effect will remain - add £20 for gravel and woody debris
121 | 17240 | GB106039017240 | Whitewater | no | Improve | Fish | morphology/barriers to migration |  | Fisheries | Educate Mill owners on connectivity and flow. | Improve modified habitats | Removal or easement of barriers to fish migration | Improvements to longitudinal connectivity | waterbody |  |  |  | WWPS | 1000 |  | Contribute to improvement of 1 elelment | UC | Fish | No
118 | 17240 | GB106039017240 | Whitewater | no | Improve | Fish | morphology/barriers to migration |  | Fisheries | Habitat enhancemets to ensure that weirs at Lodge Farm complex (7 weirs) and gauging weir ar e passable. | Improve modified habitats | Removal or easement of barriers to fish migration | Improvements to longitudinal connectivity | SU7341552346 | 1km |  |  | landowner | 50k |  | Contribute to improvement of 1 elelment | VC | Fish | No
117 | 17240 | GB106039017240 | Whitewater | no | Improve | Fish | morphology/barriers to migration |  | Fisheries | Poland Mill structures, technical fish pass or removal and habitat enhancement. | Improve modified habitats | Removal or easement of barriers to fish migration | Improvements to longitudinal connectivity | SU7428853140 | 2km |  |  | landowner | 100k |  | Contribute to improvement of 1 elelment | VC | Fish | No |  | 2 years
112 | 17240 | GB106039017240 | Whitewater | no | Improve | Fish | INNS/Signal crayfish |  | Fisheries | Provide advice and training on identification, control and disposal of invasive non-native species to all relevant groups and encourage monitoring schemes. Rolled out through partner organisations BVCP, LFCC etc. Advertise the need for authorisation from the Environment Agency and that traps need to be compliant. | Control or manage invasive species. | Building awareness and understanding. | Seek sustainable and cost-effective methods for managing established invasions of species. | SU8594354787 | Catchment |  |  | LFCC, NE, BVCP, WPS | 500/year |  | No deterioration | UC | Fish | No |  | 4 weeks | 2014-01-01 | Continuos | Yes | Any
115 | 17240 | GB106039017240 | Whitewater | no | Improve | Fish | morphology/barriers to migration |  | Fisheries | remove weir d/s Whitwater Mill, Scotts Farm and habitat enhancement. | Improve modified habitats | Removal or easement of barriers to fish migration | Improvements to longitudinal connectivity | SU7383755503 | 1km |  |  | Landowner Parish Council | 10k |  | Contribute to improvement of 1 elelment | VC | Fish | No |  | 2 years
113 | 17240 | GB106039017240 | Whitewater | no | Improve | Fish | morphology/barriers to migration |  | Fisheries | Risley Mill, bypass channel/easement and habitat enhancement. | Improve modified habitats | Removal or easement of barriers to fish migration | Improvements to longitudinal connectivity | SU7381762353 | 6 km |  |  | landowaner | 30k |  | Contribute to improvement of 1 elelment | VC | Fish | No |  | 2 years
111 | 17240 | GB106039017240 | Whitewater | no | Improve | Fish | Sediment/mixed agricultural run off |  | EM | Run an awareness campaign through on-farm demonstrations and undertake individual advisory farm visits on high risk farms, to reduce the amount of sediment, nutrients and chemicals entering a waterbody from farmland. Educate the farming | To control or manage diffuse source inputs | Reduce diffuse pollution at source | Field & Crop - Arable soils |  |  |  |  | EA, WLT, NFU , TW, UCL,KCL, RU, |  | unfunded | Contribute to improvement to 1+ element. | UC | [6 empty] | Yes | any
116 | 17240 | GB106039017240 | Whitewater | no | Improve | Fish | morphology/barriers to migration |  | Fisheries | technical and bypass Whitewater Mill and habitat enhancement. | Improve modified habitats | Removal or easement of barriers to fish migration | Improvements to longitudinal connectivity | SU7363455117 | 2.5km |  |  | landowner | 40k |  | Contribute to improvement of 1 elelment | VC | Fish | No |  | 2 years
119 | 17240 | GB106039017240 | Whitewater | no | Improve | Fish | morphology/barriers to migration |  | Fisheries | The Mill House, Warnborough Green. Lower weir and narrow stream to make the weir passable as well as habitat enhancement. | Improve modified habitats | Removal or easement of barriers to fish migration | Improvements to longitudinal connectivity | SU7315652146 | 500m |  |  | landowner | 50k |  | Contribute to improvement of 1 elelment | VC | Fish | No | [6 empty] | not a fish passage option, reducing impounding effect and narrowing channel.
111 | 17240 | GB106039017240 | Whitewater | no | Improve | Fish | Sediment/mixed agricultural run off |  | EM | Use the Catchment Sensitive Farming initative to raise awareness and reduce pesticide\phosphate\sediment pollution in this waterbody. | To control or manage diffuse source inputs | Reduce diffuse pollution at source | Field & Crop - Arable soils |  |  |  |  | EA, WLT, NFU , TW, UCL,KCL, RU, |  | unfunded | Contribute to improvement to 1+ element. | UC | [6 empty] | Yes | any
129 | 17320 | GB106039017320 | Blackwater (Bramshill to Swallowfield | No | Improve | Fish | Barriers to migration |  | Fisheries | Enable fish passage at the Swallowfield gauging stations and consider replacing with non-impounding gauging equipment. | Improve modified habitats | Removal or easement of barriers to fish migration | Improvements to longitudinal connectivity | SU7309964786 | 5km |  |  | Hydrometry | 200k |  | Contribute to improvement of 1 elelment | VC | Fish | No |  | 1 year |  |  |  |  | Uncertain about the cost of replacement gauging equipments (of non-impounding nature). Baffle solutions would be lower cost but not prefferable
131 | 17330 | GB106039017330 | Loddon (Sherfield on Loddon to Swallowfield) | no | Improve | Phytobenthos | Phosphate/Diffuse /agriculture |  | EM | Creation of buffer strips to reduce land run off | To control or manage diffuse source inputs | Reduce diffuse pollution pathways (i.e. control entry to water environment) | Riparian management |  |  |  |  | EA, WLT, NFU , TW, UCL,KCL, RU, |  | unfunded | Contribute to improvement to 1+ element. | UC | [6 empty] | Yes | any
139 | 17330 | GB106039017330 | Loddon (Sherfield on Loddon to Swallowfield) | no | Improve | Phosphate | Diffuse pollution/agriculture |  | EM | Creation of buffer strips to reduce land run off | To control or manage diffuse source inputs | Reduce diffuse pollution pathways (i.e. control entry to water environment) | Riparian management |  |  |  |  | EA, WLT, NFU , TW, UCL,KCL, RU, |  | unfunded | Contribute to improvement to 1+ element. | UC | [6 empty] | Yes | any
149 | 17330 | GB106039017330 | Loddon (Sherfield on Loddon to Swallowfield) | no | Improve | Fish | Sediment/cattle poaching |  | EM | Fencing to reduce cattle poaching and sediments carrying hosphates efrom entering the river. | To control or manage diffuse source inputs | Reduce diffuse pollution pathways (i.e. control entry to water environment) | Field & Crop - Livestock |  |  |  |  | EA, WLT, NFU , TW, UCL,KCL, RU, |  | unfunded | Contribute to improvement to 1+ element. | UC | [6 empty] | Yes | any
148 | 17330 | GB106039017330 | Loddon (Sherfield on Loddon to Swallowfield) | no | Improve | Fish | physical modification/barriers to migration |  | Fisheries | Improve habitats and connectivity at the Priory Mill complex, removal/lowering or installation of fish pass as required and habitat enhancement | Improve modified habitats | Removal or easement of barriers to fish migration | Improvements to longitudinal connectivity | SU7032363443 | 2km |  |  | landowner | 150k | unfunded | Contribute to improvement of more than 1 elelment | UC | Fish | No | WFD | 2 years |  |  | no | any
138 | 17330 | GB106039017330 | Loddon (Sherfield on Loddon to Swallowfield) | no | Improve | Fish | INNS/Signal crayfish |  | Fisheries | Provide advice and training on identification, control and disposal of invasive non-native species to all relevant groups and encourage monitoring schemes. Rolled out through partner organisations BVCP, LFCC etc. Advertise the need for authorisation from the Environment Agency and that traps need to be compliant. | Control or manage invasive species. | Building awareness and understanding. | Seek sustainable and cost-effective methods for managing established invasions of species. | SU7255165634 (centre of catchment) | whole catchment |  |  | LFCC, NE, BVCP, WPS | 500/year |  | No deterioration | UC | Fish | No |  | 4 weeks | 2014-01-01 | Continuos | Yes | Any
134 | 17330 | GB106039017330 | Loddon (Sherfield on Loddon to Swallowfield) | no | Improve | Fish | impoundments - no water storage/flow |  | Fisheries | Remove imounding structure at Priory Mill | Improve modified habitats | Removal or easement of barriers to fish migration | Improvements to longitudinal connectivity | SU7086464119 | 1km |  |  | Estate / Landowner | 10k | unfunded | Contribute to improvement of 1 elelment | QC | Fish | No | WFD | 1 year |  |  | No | Any
137 | 17330 | GB106039017330 | Loddon (Sherfield on Loddon to Swallowfield) | no | Improve | Phytobenthos | Sediment/impoundment |  | Fisheries | Remove imounding structure at Priory Mill | Improve modified habitats | Removal or easement of barriers to fish migration | Improvements to longitudinal connectivity | SU7086464119 | 1km |  |  | Estate / Landowner | 10k | unfunded | Contribute to improvement of 1 elelment | QC | Fish | No | WFD | 2 year |  |  | No | Any
131 | 17330 | GB106039017330 | Loddon (Sherfield on Loddon to Swallowfield) | no | Improve | Phytobenthos | Phosphate/Diffuse /agriculture |  | EM | Run an awareness campaign through on-farm demonstrations and undertake individual advisory farm visits on high risk farms, to reduce the amount of sediment, nutrients and chemicals entering a waterbody from farmland. Educate the farming | To control or manage diffuse source inputs | Reduce diffuse pollution at source | Field & Crop - Arable soils |  |  |  |  | EA, WLT, NFU , TW, UCL,KCL, RU, |  | unfunded | Contribute to improvement to 1+ element. | UC | [6 empty] | Yes | any
139 | 17330 | GB106039017330 | Loddon (Sherfield on Loddon to Swallowfield) | no | Improve | Phosphate | Diffuse pollution/agriculture |  | EM | Run an awareness campaign through on-farm demonstrations and undertake individual advisory farm visits on high risk farms, to reduce the amount of sediment, nutrients and chemicals entering a waterbody from farmland. Educate the farming | To control or manage diffuse source inputs | Reduce diffuse pollution at source | Field & Crop - Arable soils |  |  |  |  | EA, WLT, NFU , TW, UCL,KCL, RU, |  | unfunded | Contribute to improvement to 1+ element. | UC | [6 empty] | Yes | any
133 | 17330 | GB106039017330 | Loddon (Sherfield on Loddon to Swallowfield) | no | Improve | Fish | impoundments - no water storage/flow |  | Fisheries | Take the broadwater off-line | Improve modified habitats | Removal or easement of barriers to fish migration | Improvements to longitudinal connectivity | SU7047961821 | 5km |  |  | Estate / Landowner | 500k | unfunded | Contribute to improvement of 1 elelment | VC | Fish | No | WFD | 3 years
131 | 17330 | GB106039017330 | Loddon (Sherfield on Loddon to Swallowfield) | no | Improve | Phytobenthos | Phosphate/Diffuse /agriculture |  | EM | Use the Catchment Sensitive Farming initative to raise awareness and reduce pesticide\phosphate\sediment pollution in this waterbody. | To control or manage diffuse source inputs | Reduce diffuse pollution at source | Field & Crop - Arable soils |  |  |  |  | EA, WLT, NFU , TW, UCL,KCL, RU, |  | unfunded | Contribute to improvement to 1+ element. | UC | [6 empty] | Yes | any
139 | 17330 | GB106039017330 | Loddon (Sherfield on Loddon to Swallowfield) | no | Improve | Phosphate | Diffuse pollution/agriculture |  | EM | Use the Catchment Sensitive Farming initative to raise awareness and reduce pesticide\phosphate\sediment pollution in this waterbody. | To control or manage diffuse source inputs | Reduce diffuse pollution at source | Field & Crop - Arable soils |  |  |  |  | EA, WLT, NFU , TW, UCL,KCL, RU, |  | unfunded | Contribute to improvement to 1+ element. | UC | [6 empty] | Yes | any
150 | 23130 | GB106039023130 | Emm Brook | yes | Improve | Mitigation measures assessment | Physical modification/land drainiage/operational management |  |  | Remove structure / install fish pass or bypass channel at Riverside walk, Wokingham and enhance river morphology | Improve modified habitats | Removal or easement of barriers to fish migration | Improvements to longitudinal connectivity | SU7983769265 | 3km |  |  | LA | 100k | unfunded | Contribute to improvement of more than 1 elelment | QC | fish | No | WFD | 2 years |  |  | no | any
151 | 23160 | GB106039023160 | Loddon (Swallowfield to Thames) | no | Improve | Tributyltin compounds | diffuse/trading estates |  | EM | Fencing to reduce cattle poaching and sediments carrying hosphates efrom entering the river. | To control or manage diffuse source inputs | Reduce diffuse pollution pathways (i.e. control entry to water environment) | Field & Crop - Livestock |  |  |  |  | EA, WLT, NFU , TW, UCL,KCL, RU, |  | unfunded | Contribute to improvement to 1+ element. | UC | [6 empty] | Yes | any
144 | 23160 | GB106039023160 | Loddon (Sherfield on Loddon to Swallowfield) | no | Improve | Fish | morphology/barriers to migration |  | Fisheries | Improvements to bypass channel at Sheepbridge and enhance habitat | Improve modified habitats | Removal or easement of barriers to fish migration | Improvements to longitudinal connectivity | SU7188364976 | 5km |  |  | Landowner, Swallowfield fishing club, Hydrometry | 80k | unfunded | Contribute to improvement of more than 1 elelment | VC | Fish | No | WFD | 2 years |  |  | no | Any
156 | 23160 | GB106039023160 | Loddon (Swallowfield to Thames) | no | Improve | Fish | morphology/barriers to migration |  | Fisheries | Sandford Farm weir removal/lowering or installation of fish pass as required and habitat enhancement | Improve modified habitats | Removal or easement of barriers to fish migration | Improvements to longitudinal connectivity | SU7824473743 | 3km |  |  | Developer / LA / Landowner | 150k | unfunded | Contribute to improvement of 1 elelment | VC | Fish | No | WFD, Private | 1 |  |  | no | any | Linked to large housing development and land decontamination adjacent to site
144 | 23160 | GB106039023160 | Loddon (Sherfield on Loddon to Swallowfield) | no | Improve | Fish | morphology/barriers to migration |  | Fisheries | Sheep Bridge (2) weir removal/lowering or installation of fish pass as required and habitat enhancement | Improve modified habitats | Removal or easement of barriers to fish migration | Improvements to longitudinal connectivity | SU7203565318 | 5km |  |  | Hydrometry, Landowner | 150k | unfunded | Contribute to improvement of more than 1 elelment | QC | Fish | No | WFD | 2 years |  |  | no | Any
154 | 23160 | GB106039023160 | Loddon (Swallowfield to Thames) | no | Improve | Fish | morphology/barriers to migration |  | Fisheries | Sindlesham Mill (3) weir removal/lowering or installation of fish pass as required and habitat enhancement | Improve modified habitats | Removal or easement of barriers to fish migration | Improvements to longitudinal connectivity | SU7668270272 | 3km |  |  | Farnham AC | 150k | unfunded | Contribute to improvement of 1 elelment | QC | Fish | No | WFD | 2 years |  |  | no | any
155 | 23160 | GB106039023160 | Loddon (Swallowfield to Thames) | no | No deterioration | Fish |  |  | Fisheries | St Patricks Stream, river and wetland project. Create a back water and use the gravel to create riffles and spawning habitat, include woody debris. | Improve modified habitats | Improve condition of channel bed and/or banks/shoreline | Preserve and restore habitats | SU7720477553 | 4 km |  |  | Twyford & District, New AC, residents, FCRM, Barbel Society, CLPS, | 30 k |  | Contribute to improvement of 1 elelment | VC | Fish |  | WFD, FCRM, private | 2 years |  |  | no | any | Will improve the Thames and Loddon Waterbodies. Design complete.
145 | 23160 | GB106039023160 | Loddon (Sherfield on Loddon to Swallowfield) | no | Improve | Fish | morphology/barriers to migration |  | Fisheries | Stanford End (3)weir removal/lowering or installation of fish pass as required and habitat enhancement | Improve modified habitats | Removal or easement of barriers to fish migration | Improvements to longitudinal connectivity | SU7072563071 | [6 empty] | Contribute to improvement of more than 1 elelment |  | Fish
146 | 23160 | GB106039023160 | Loddon (Sherfield on Loddon to Swallowfield) | no | Improve | Fish | morphology/barriers to migration |  | Fisheries | Stratfield Saye weir removal/lowering or installation of fish pass as required and habitat enhancement | Improve modified habitats | Removal or easement of barriers to fish migration | Improvements to longitudinal connectivity | SU6829659537 | 3km |  |  | Landowner | 100k | unfunded | Contribute to improvement of more than 1 elelment | QC | Fish | No | WFD | 2 years |  |  | no | any
147 | 23160 | GB106039023160 | Loddon (Sherfield on Loddon to Swallowfield) | no | Improve | Fish | morphology/barriers to migration |  | Fisheries | Tumbling Bay weirs (2)weir removal/lowering or installation of fish pass as required and habitat enhancement | Improve modified habitats | Removal or easement of barriers to fish migration | Improvements to longitudinal connectivity | SU7051462085 | 3km |  |  | Landowner | 150k | unfunded | Contribute to improvement of more than 1 elelment |  | Fish | No | WFD | 2 years |  |  | no | any
152 | 23160 | GB106039023160 | Loddon (Swallowfield to Thames) | no | Improve | Fish | morphology/barriers to migration |  | Fisheries | Twyford Mill structures (2) weir removal/lowering or installation of fish pass as required and habitat enhancement | Improve modified habitats | Removal or easement of barriers to fish migration | Improvements to longitudinal connectivity | SU7852276002 | 4km |  |  | LA | 50k | unfunded | Contribute to improvement of 1 elelment | VC | Fish | No | WFD | 1 year |  |  | no | any
153 | 23160 | GB106039023160 | Loddon (Swallowfield to Thames) | no | Improve | Fish | morphology/barriers to migration |  | Fisheries | Weir feeding distributary u/s Sandford Bridge weir removal/lowering or installation of fish pass as required and habitat enhancement | Improve modified habitats | Removal or easement of barriers to fish migration | Improvements to longitudinal connectivity | SU7792772716 | 1km |  |  | Country Park / LA | 10k | unfunded | Contribute to improvement of 1 elelment | UC | Fish | No | WFD | 1 Year |  |  | no | any
157 | 23190 | GB106039023190 | Twyford Brook | no | Improve | Phosphate | Arable field/diffuse |  | EM | Creation of buffer strips to reduce land run off | To control or manage diffuse source inputs | Reduce diffuse pollution pathways (i.e. control entry to water environment) | Riparian management |  |  |  |  | EA, WLT, NFU , TW, UCL,KCL, RU, |  | unfunded | Contribute to improvement to 1+ element. | UC | [6 empty] | Yes | any
161 | 23190 | GB106039023190 | Twyford Brook | no | Improve | Phosphate | Dairy cattle/diffuse |  | EM | Creation of buffer strips to reduce land run off | To control or manage diffuse source inputs | Reduce diffuse pollution pathways (i.e. control entry to water environment) | Riparian management |  |  |  |  | EA, WLT, NFU , TW, UCL,KCL, RU, |  | unfunded | Contribute to improvement to 1+ element. | UC | [6 empty] | Yes | any
161 | 23190 | GB106039023190 | Twyford Brook | no | Improve | Phosphate | Dairy cattle/diffuse |  | EM | Fencing to reduce cattle poaching | [7 empty] | EA, WLT, NFU , TW, UCL,KCL, RU, |  | unfunded | Contribute to improvement to 1+ element. | UC | [6 empty] | Yes | any
161 | 23190 | GB106039023190 | Twyford Brook | no | Improve | Phosphate | Dairy cattle/diffuse |  | EM | Fencing to reduce cattle poaching and sediments carrying hosphates efrom entering the river. | To control or manage diffuse source inputs | Reduce diffuse pollution pathways (i.e. control entry to water environment) | Field & Crop - Livestock |  |  |  |  | EA, WLT, NFU , TW, UCL,KCL, RU, |  | unfunded | Contribute to improvement to 1+ element. | UC | [6 empty] | Yes | any
157 | 23190 | GB106039023190 | Twyford Brook | no | Improve | Phosphate | Arable field/diffuse |  | EM | Run an awareness campaign through on-farm demonstrations and undertake individual advisory farm visits on high risk farms, to reduce the amount of sediment, nutrients and chemicals entering a waterbody from farmland. Educate the farming | To control or manage diffuse source inputs | Reduce diffuse pollution at source | Field & Crop - Arable soils |  |  |  |  | EA, WLT, NFU , TW, UCL,KCL, RU, |  | unfunded | Contribute to improvement to 1+ element. | UC | [6 empty] | Yes | any
161 | 23190 | GB106039023190 | Twyford Brook | no | Improve | Phosphate | Dairy cattle/diffuse |  | EM | Run an awareness campaign through on-farm demonstrations and undertake individual advisory farm visits on high risk farms, to reduce the amount of sediment, nutrients and chemicals entering a waterbody from farmland. Educate the farming | To control or manage diffuse source inputs | Reduce diffuse pollution at source | Field & Crop - Arable soils |  |  |  |  | EA, WLT, NFU , TW, UCL,KCL, RU, |  | unfunded | Contribute to improvement to 1+ element. | UC | [6 empty] | Yes | any
157 | 23190 | GB106039023190 | Twyford Brook | no | Improve | Phosphate | Arable field/diffuse |  | EM | Use the Catchment Sensitive Farming initative to raise awareness and reduce pesticide\phosphate\sediment pollution in this waterbody. | To control or manage diffuse source inputs | Reduce diffuse pollution at source | Field & Crop - Arable soils |  |  |  |  | EA, WLT, NFU , TW, UCL,KCL, RU, |  | unfunded | Contribute to improvement to 1+ element. | UC | [6 empty] | Yes | any
161 | 23190 | GB106039023190 | Twyford Brook | no | Improve | Phosphate | Dairy cattle/diffuse |  | EM | Use the Catchment Sensitive Farming initative to raise awareness and reduce pesticide\phosphate\sediment pollution in this waterbody. | To control or manage diffuse source inputs | Reduce diffuse pollution at source | Field & Crop - Arable soils |  |  |  |  | EA, WLT, NFU , TW, UCL,KCL, RU, |  | unfunded | Contribute to improvement to 1+ element. | UC | [6 empty] | Yes | any
Note on A104: ssheridan: This line includes both gauging stations at Swallowfield because realistically they would be tackled as one project
Note on A124: ssheridan: Might need to modify this in light of current situation

## Datasheet input
Investigation ID | RFF ID | Action ID | Action description | No deterioration | Prioritisation | Measure level 1 | Measure level 2 | Measure level 3 | EA Owner (Team) | WB ID | Expected effect | Confidence | Cost | Extent (length) | Extent (area) | Lead sector | Lead organisation | Partner organisations | Indicative NGR | Deliverability | Years to implement | Years from action implementation | Operational | Project Ref | Link to funding | Mitigation measures | Comment | FTE Planned | FTE Actual | Planned Start date | Planned end date | Actual start date | Actual end date | Measure ID | Actions written by |  | NGR upstream | easting upstream | northing upstream | NGR downstram | Easting downstream | Northing downstream | Temp NGR | Easting centre point | Northing centre point | Action Funded/unfunded | MitMeasure | Catchment wide solution | Climate change | Date created | Last modified | Modified by | Element | links to RFF ID2 | Links to RFF ID3 | Links to RFF ID4 | Links to RFF ID5 | Links to RFF ID6 | Links to RFF ID7 | Links to RFF ID8 | WBLMA action ID | Spreadsheet no | WBLMA fail | Point
TH2009-15547 | GB106039017080_RFF003 |  | Bank alterations to give channel width variation and two-stage channels. Introduction of meanders in straightened river sections. | No |  | Improve modified habitats | Improve condition of channel bed and/or banks/shoreline | Bank rehabilitation / reprofiling | Fisheries | GB106039017080 | Contribute to improvement of more than 1 elelment | Very Certain | <10000 | 200m |  |  | EA | WLT, WTT |  |  | 1 year | [14 empty] | SU6614852985 | [9 empty] | unfunded |  | No |  | 2013-11-26 | 2013-11-26 | TENTWISTLE
TH2009-15548 | GB106039017080_RFF003 |  | Bank alterations to give channel width variation and two-stage channels. Introduction of meanders in straightened river sections. | No |  | Improve modified habitats | Improve condition of channel bed and/or banks/shoreline | Bank rehabilitation / reprofiling | Fisheries | GB106039017080 | Contribute to improvement of more than 1 elelment | Very Certain | <10000 | 80 m |  |  | EA | TW angling club |  |  | 1 year | [14 empty] | SU6519052612 to SU6803555235 | [9 empty] | unfunded |  | No |  | 2013-11-26 | 2013-11-26 | TENTWISTLE
TH2009-15549 | GB106039017080_RFF003 |  | Bartons Mill weir complex removal/lowering or installation of fish pass as required and habitat enhancement | No |  | Improve modified habitats | Removal or easement of barriers to fish migration | Improvements to longitudinal connectivity | Fisheries | GB106039017080 | Contribute to improvement of more than 1 elelment | Very Certain | <10000 | 2 km |  |  | EA | Landowners, WTT, WLT, LFCC, angling club, B&DBC |  |  | 2 years | [14 empty] | SU6616753092 | [9 empty] | unfunded |  | No |  | 2013-11-26 | 2013-11-26 | TENTWISTLE
TH2009-15550 | GB106039017080_RFF003 |  | Dual water supply system to new housing and potentiall old housing in Basingstoke (grey water and potable water) to reduce abstraction and volumes of water going through STW. | No |  | To control or manage abstraction | Use alternative source/relocate abstraction or discharge | Change abstraction location | 0 | GB106039017080 | Contribute to improvement of 1+ element | Very Certain | <10000 |  |  |  | EA | Council, residents, water companies, developers | [18 empty] | SU6775758417 |  |  | SU6775758417 | [5 empty] | Unfunded |  | No |  | 2013-11-26 | 2013-11-26 | TENTWISTLE
TH2009-15551 | GB106039017080_RFF003 |  | Eastrop Park Partnership Project, deculvert the Loddon at Eastrop park and restore degraded habitats. | No |  | To improve modified habitat | Improvement to condition of channel/bed and/or banks/shoreline | Increase in-channel morphological diversity | Groundwater | GB106039017080 | Contribute to improvement of more than 1 elelment | Very Certain | 10001-25001 | 1 km |  |  | EA | WTT B&DBC |  |  | 3 years | [14 empty] | SU6465452362 | [9 empty] | unfunded |  | No |  | 2013-11-26 | 2013-11-26 | TENTWISTLE
TH2009-15552 | GB106039017080_RFF003 |  | Effluent re-use, duel water use. | No |  | To control or manage abstraction | Use alternative source/relocate abstraction or discharge | Water efficiency activity | Groundwater Hydrology | GB106039017080 | Contribute to improvement of 1+ element | Very Certain | <10000 |  |  |  | EA | Council, residents, water companies, developers | [18 empty] | SU6380657192 |  |  | SU6775758417 | [5 empty] | Unfunded |  | No |  | 2013-11-26 | 2013-11-26 | TENTWISTLE
TH2009-15553 | GB106039017080_RFF003 |  | Flow diversion structure d/s Eastrop Park | No |  | Improve modified habitats | Removal or easement of barriers to fish migration | Improvements to longitudinal connectivity | FCRM | GB106039017080 | Contribute to improvement of more than 1 elelment | Very Certain | <10000 | 500 m |  |  | EA | Landowners, WTT, WLT, LFCC, angling club, B&DBC |  |  | 1 year | [14 empty] | SU6523352591 | [9 empty] | unfunded |  | Yes |  | 2013-11-26 | 2013-11-26 | TENTWISTLE
TH2009-15554 | GB106039017080_RFF003 |  | habitat enhancement d/s of notche weir 1 | No |  | Improve modified habitats | Improve condition of channel bed and/or banks/shoreline | Preserve and restore habitats | Fisheries | GB106039017080 | Contribute to improvement of more than 1 elelment | Very Certain | <10000 | 100 m |  |  | EA | Landowners, WTT, WLT, LFCC, angling club, B&DBC |  |  | 1 year | [14 empty] | SU6689054024 | [9 empty] | unfunded |  | Yes |  | 2013-11-26 | 2013-11-26 | TENTWISTLE
TH2009-15555 | GB106039017080_RFF003 |  | Install fish pass at Pyots Hill | No |  | Improve modified habitats | Removal or easement of barriers to fish migration | Improvements to longitudinal connectivity | Fisheries | GB106039017080 | Contribute to improvement of more than 1 elelment | Very Certain | 10001-25001 | 3 km |  |  | EA | Landowners, WTT, WLT, LFCC, angling club, B&DBC |  |  | 1 year | [14 empty] | SU6671153687 | [9 empty] | unfunded |  | Yes |  | 2013-11-26 | 2013-11-26 | TENTWISTLE
SE2012-00853 | GB106039017090_RFF006 |  | Introduction of gravels to create spawning opportunities for fish, and restore bed profile variation. Reduce shading to promote in channel vegetation growth and install woody debris in the channel. | No |  | Improve modified habitats | Improve condition of channel bed and/or banks/shoreline | Preserve and restore habitats | Fisheries | GB106039017080 | Contribute to improvement of more than 1 elelment | Very Certain | <10000 | 800 m |  |  | EA | WTT WLT Gresham AC TW |  |  | 1 year | [14 empty] | SU6805055247 to SU6919757549 | [9 empty] | unfunded |  | No |  | 2013-11-26 | 2013-11-26 | TENTWISTLE
SE2012-00853 | GB106039017090_RFF006 |  | Investigat the effects of West Ham on the ecology of the Lower Bow Brook between the abstraction points and the discharge outlet of Basingstoke STW | No |  | To control or manage abstraction | Use alternative source/relocate abstraction or discharge | Change abstraction location | Groundwater A&R F&B | GB106039017080 | No deterioration | Very Certain | <10000 |  |  |  | EA | Council, residents, water companies, developers | [27 empty] | Unfunded |  | No |  | 2013-11-26 | 2013-11-26 | TENTWISTLE
SE2012-00853 | GB106039017090_RFF006 |  | Investigat the effects of West Ham on the ecology of the River Loddon between the abstraction points and the discharge outlet of Basingstoke STW | No |  | To control or manage abstraction | Use alternative source/relocate abstraction or discharge | Change abstraction location | Groundwater A&R F&B | GB106039017080 | No deterioration | Very Certain | <10000 |  |  |  | EA | Council, residents, water companies, developers | [27 empty] | Unfunded |  | Yes |  | 2013-11-26 | 2013-11-26 | TENTWISTLE
SE2012-00853 | GB106039017090_RFF006 |  | Investigat the effects of West Ham on the ecology of the Vyne Stream between the abstraction points and the discharge outlet of Basingstoke STW | No |  | To control or manage abstraction | Use alternative source/relocate abstraction or discharge | Change abstraction location | Groundwater A&R F&B | GB106039017080 | No deterioration | Very Certain | <10000 |  |  |  | EA | Council, residents, water companies, developers | [27 empty] | Unfunded |  | Yes |  | 2013-11-26 | 2013-11-26 | TENTWISTLE
SE2012-00853 | GB106039017090_RFF006 |  | Investigat the passability of culverts around Basingstoke, opening culvert/installing fish easment as required (Eastrop Park) | No |  | Improve modified habitats | Removal or easement of barriers to fish migration | Improvements to longitudinal connectivity | FCRM | GB106039017080 | Contribute to improvement of more than 1 elelment | Very Certain | 10001-25001 | 500 m |  |  | EA | EA LA WTT WLT |  |  | 3 years | [14 empty] | SU6485952378 | [9 empty] | unfunded |  | Yes |  | 2013-11-26 | 2013-11-26 | TENTWISTLE
SE2011-00607 | GB106039017090_RFF007 |  | LH channel weir d/s Lower Mill | No |  | Improve modified habitats | Removal or easement of barriers to fish migration | Improvements to longitudinal connectivity | Fisheries | GB106039017080 | Contribute to improvement of more than 1 elelment | Very Certain | <10000 | 500 |  |  | EA | land owner |  |  | 1 year | [14 empty] | SU6691353897 | [9 empty] | unfunded |  | Yes |  | 2013-11-26 | 2013-11-26 | TENTWISTLE
SE2011-00607 | GB106039017090_RFF007 |  | limit development at Basingstoke | No |  | To control or manage abstraction | Water Demand Management | Water efficiency activity | Groundwater Hydrology | GB106039017080 | Contribute to improvement of 1+ element | Very Certain | <10000 |  |  |  | EA | Council, residents, water companies, developers | [27 empty] | Unfunded |  | Yes |  | 2013-11-26 | 2013-11-26 | TENTWISTLE
SE2011-00607 | GB106039017090_RFF007 |  | Lower Mill weir removal/lowering or installation of fish pass as required and habitat enhancement | No |  | Improve modified habitats | Removal or easement of barriers to fish migration | Improvements to longitudinal connectivity | Fisheries | GB106039017080 | Contribute to improvement of more than 1 elelment | Very Certain | <10000 | 1 km |  |  | EA | Landowners, WTT, WLT, LFCC, angling club, B&DBC |  |  | 2 years | [14 empty] | SU6689353810 | [9 empty] | unfunded |  | No |  | 2013-11-26 | 2013-11-26 | TENTWISTLE
SE2011-00607 | GB106039017090_RFF007 |  | Old Basing fish farm weir removal/lowering or installation of fish pass as required and habitat enhancement | No |  | Improve modified habitats | Removal or easement of barriers to fish migration | Improvements to longitudinal connectivity | Fisheries | GB106039017080 | Contribute to improvement of more than 1 elelment | Very Certain | <10000 | 500 m |  |  | EA | Landowners, WTT, WLT, LFCC, angling club, B&DBC |  |  | 1year | [14 empty] | SU6649453304 | [9 empty] | unfunded |  | No |  | 2013-11-26 | 2013-11-26 | TENTWISTLE
SE2011-00607 | GB106039017090_RFF007 |  | Old Basing LH channel redundant weir | No |  | Improve modified habitats | Removal or easement of barriers to fish migration | Improvements to longitudinal connectivity | Fisheries | GB106039017080 | Contribute to improvement of more than 1 elelment | Very Certain | <10000 | 500 m |  |  | EA | Landowners, WTT, WLT, LFCC, angling club, B&DBC |  |  | 1 month | [14 empty] | SU6689154017 (weir 1 Old Basing) | [9 empty] | funded |  | No |  | 2013-11-26 | 2013-11-26 | TENTWISTLE
SE2011-00607 | GB106039017090_RFF007 |  | Old Basing RH concrete weir | No |  | Improve modified habitats | Removal or easement of barriers to fish migration | Improvements to longitudinal connectivity | Fisheries | GB106039017080 | Contribute to improvement of more than 1 elelment | Very Certain | <10000 | 500 m |  |  | EA | Landowners, WTT, WLT, LFCC, angling club, B&DBC |  |  | 1 month | [14 empty] | SU6718554042 (weir 2 Old Basing) | [9 empty] | funded |  | Yes |  | 2013-11-26 | 2013-11-26 | TENTWISTLE
SE2011-00611 | GB106039017110_RFF003 |  | Overspill to side channel u/s Lower Mill | No |  | Improve modified habitats | Removal or easement of barriers to fish migration | Improvements to longitudinal connectivity | Fisheries | GB106039017080 | Contribute to improvement of more than 1 elelment | Very Certain | <10000 | 500 m |  |  | EA | Landowners, WTT, WLT, LFCC, angling club, B&DBC |  |  | 1 year | [14 empty] | SU6671353686 | [9 empty] | funded |  | No |  | 2013-11-26 | 2013-11-26 | TENTWISTLE
SE2011-00611 | GB106039017110_RFF003 |  | Provide advice and training on identification, control and disposal of invasive non-native species to all relevant groups and encourage monitoring schemes. Rolled out through partner organisations BVCP, LFCC etc. Advertise the need for authorisation from the Environment Agency and that traps need to be compliant. | No |  | Control or manage invasive species. | Building awareness and understanding. | Seek sustainable and cost-effective methods for managing established invasions of species. | Fisheries | GB106039017080 | No deterioration | Uncertain | <10000 | whole catchment |  |  | EA | LFCC, NE, BVCP, WPS |  |  | 4 weeks | [14 empty] | SU7255165634 (centre of catchment) | [9 empty] | unfunded |  | Yes |  | 2013-11-26 | 2013-11-26 | TENTWISTLE
SE2011-00611 | GB106039017110_RFF003 |  | Reduce pumping at West Ham, find alternative source. | No |  | To control or manage abstraction | Water Demand Management | Water efficiency activity | Groundwater Hydrology | GB106039017080 | Contribute to improvement of 1+ element | Very Certain | <10000 |  |  |  | EA | Council, residents, water companies, developers | [27 empty] | Unfunded |  | Yes |  | 2013-11-26 | 2013-11-26 | TENTWISTLE
SE2011-00611 | GB106039017110_RFF003 |  | RH channel d/s Lower Mill | No |  | Improve modified habitats | Removal or easement of barriers to fish migration | Improvements to longitudinal connectivity | Fisheries | GB106039017080 | Contribute to improvement of more than 1 elelment | Very Certain | <10000 | 500 |  |  | EA | land owner |  |  | 1 year | [14 empty] | SU6718354038 | [9 empty] | unfunded |  | No |  | 2013-11-26 | 2013-11-26 | TENTWISTLE
SE2011-00611 | GB106039017110_RFF002 |  | Run a targetted water efficiency campaign for all licensed abstractors in a waterbody. | No |  | To control or manage abstraction | Water Demand Management | Water efficiency activity | EM | GB106039017080 | No deterioration | Uncertain | <10000 |  |  |  | EA | Council, residents, water companies, developers | [27 empty] | Unfunded |  | Yes |  | 2013-11-26 | 2013-11-26 | TENTWISTLE
SE2011-00611 | GB106039017110_RFF002 |  | Saunders field (headwater of the Loddon). Improve ressilience, wetlands, SUDS. | No |  | Improve modified habitats | Improvement to condition of riparian zone and/or wetland habitats | Preserve and restore habitats | FCRM | GB106039017080 | No deterioration |  | <10000 | 300 m |  |  | EA | WLT |  |  | 1 year | [14 empty] | SU6221052074 | [9 empty] | unfunded |  | Yes |  | 2013-11-26 | 2013-11-26 | TENTWISTLE
SE2011-00611 | GB106039017110_RFF002 |  | Take The Vyne stillwater off-line to restore river gradient and morphology upstream. | No |  | Improve modified habitats | Improve condition of channel bed and/or banks/shoreline | Preserve and restore habitats | Fisheries Ops | GB106039017080 | Contribute to improvement of more than 1 elelment | Very Certain | <10000 | 4km |  |  | EA | National Trust |  |  | 3 years | [14 empty] | SU6363456910 | [9 empty] | unfunded |  | Yes |  | 2013-11-26 | 2013-11-26 | TENTWISTLE
SE2011-00611 | GB106039017110_RFF002 |  | Water company led water efficiency campaign | No |  | To control or manage abstraction | Water Demand Management | Water efficiency activity | EM | GB106039017080 | No deterioration | Uncertain | <10000 |  |  |  | EA | Council, residents, water companies, developers | [27 empty] | Unfunded |  | Yes |  | 2013-11-26 | 2013-11-26 | TENTWISTLE
SE2011-00611 | GB106039017110_RFF003 |  | Creation of buffer strips to reduce land run off | No |  | To control or manage diffuse source inputs | Reduce diffuse pollution pathways (i.e. control entry to water environment) | Riparian management | EM | GB106039017090 | Contribute to improvement to 1+ element. | Uncertain | <10000 |  |  |  | EA | EA, WLT, NFU , TW, UCL,KCL, RU, | [27 empty] | unfunded |  | Yes |  | 2013-11-26 | 2013-11-26 | TENTWISTLE
SE2011-00611 | GB106039017110_RFF003 |  | Creation of buffer strips to reduce sediments carrying hosphates efrom entering the river. | No |  | To control or manage diffuse source inputs | Reduce diffuse pollution pathways (i.e. control entry to water environment) | Riparian management | EM | GB106039017090 | Contribute to improvement to 1+ element. | Uncertain | <10000 |  |  |  | EA | EA, WLT, NFU , TW, UCL,KCL, RU, | [27 empty] | unfunded |  | Yes |  | 2013-11-26 | 2013-11-26 | TENTWISTLE
SE2011-00611 | GB106039017110_RFF003 |  | Effluent re-use, uel water use. | No |  | To control or manage abstraction | Use alternative source/relocate abstraction or discharge | Water efficiency activity | Groundwater Hydrology | GB106039017090 | Contribute to improvement of 1+ element | Very Certain | <10000 |  |  |  | EA | Council, residents, water companies, developers | [27 empty] | Unfunded |  | No |  | 2013-11-26 | 2013-11-26 | TENTWISTLE
|  |  | Elvetham Estate weir removal/lowering or installation of fish pass as required and habitat enhancement | No |  | Improve modified habitats | Removal or easement of barriers to fish migration | Improvements to longitudinal connectivity | Fisheries | GB106039017090 | Contribute to improvement of more than 1 elelment | Very Certain | <10000 | 5 km |  |  | EA | Hotel/Estate WTT WLT |  |  | 1 year | [14 empty] | SU7841556756 | [9 empty] | Unfunded |  | No |  | 2013-11-26 | 2013-11-26 | TENTWISTLE
SE2011-00629 | GB106039017290_RFF001 |  | Elvetham to M3 improve morphology. New channel,Re meander, add Gravel riffles, bank reprofiling. | Yes |  | Improve modified habitats | Removal or easement of barriers to fish migration | Improvements to longitudinal connectivity | Fisheries | GB106039017090 | Contribute to improvement of more than 1 elelment | Very Certain | <10000 | 1 km |  |  | EA | Highways, landowner/estate |  |  | 2 years | [14 empty] | Hotel to M3 | [9 empty] | Unfunded |  | Yes |  | 2013-11-26 | 2013-11-26 | TENTWISTLE
SE2011-00629 | GB106039017290_RFF001 |  | Fencing to reduce cattle poaching and sediments carrying hosphates efrom entering the river. | No |  | To control or manage diffuse source inputs | Reduce diffuse pollution pathways (i.e. control entry to water environment) | Field & Crop - Livestock | EM | GB106039017090 | Contribute to improvement to 1+ element. | Uncertain | <10000 |  |  |  | EA | EA, WLT, NFU , TW, UCL,KCL, RU, | [27 empty] | unfunded |  | Yes |  | 2013-11-26 | 2013-11-26 | TENTWISTLE
SE2011-00629 | GB106039017290_RFF001 |  | Investigate Boxalls Lane, Oak Park Golf Club and Itchell puming station effect on biology. | No |  | To control or manage abstraction | Water Demand Management | Water efficiency activity | Hydrology | GB106039017090 | Contribute to improvement of 1+ element | Very Certain | <10000 |  |  |  | EA | Council, residents, water companies, developers | [27 empty] | Unfunded |  | Yes |  | 2013-11-26 | 2013-11-26 | TENTWISTLE
SE2011-00629 | GB106039017290_RFF001 |  | larinier or bristle or pre barrage on weir structure at Pilcot Mill and habitat enhancement. | No |  | Improve modified habitats | Removal or easement of barriers to fish migration | Improvements to longitudinal connectivity | Fisheries | GB106039017090 | Contribute to improvement of more than 1 elelment | Very Certain | <10000 | 4 km |  |  | EA | Mill owner WTT WLT SE water |  |  | 1 year | [14 empty] | SU7864252793 | [9 empty] | Unfunded |  | Yes |  | 2013-11-26 | 2013-11-26 | TENTWISTLE
SE2011-00620 | GB106039017160_RFF001 |  | Pre barrage fish pass at Basingstoke canal culvert and habitat enhancement. | No |  | Improve modified habitats | Removal or easement of barriers to fish migration | Improvements to longitudinal connectivity | Fisheries | GB106039017090 | Contribute to improvement of more than 1 elelment | Very Certain | <10000 | 3 km |  |  | EA | WTT WLT BCA |  |  | 1 year | [14 empty] | SU7943851601 | [9 empty] | Unfunded |  | Yes |  | 2013-11-26 | 2013-11-26 | TENTWISTLE
SE2011-00620 | GB106039017160_RFF001 |  | Provide advice and training on identification, control and disposal of invasive non-native species to all relevant groups and encourage monitoring schemes. Rolled out through partner organisations BVCP, LFCC etc. Advertise the need for authorisation from the Environment Agency and that traps need to be compliant. | No |  | Control or manage invasive species. | Building awareness and understanding. | Seek sustainable and cost-effective methods for managing established invasions of species. | Fisheries | GB106039017090 | No deterioration | Uncertain | <10000 | whole catchment |  |  | EA | LFCC, NE, BVCP, WPS |  |  | 4 weeks | [14 empty] | SU7255165634 (centre of catchment) | [9 empty] | Unfunded |  | Yes |  | 2013-11-26 | 2013-11-26 | TENTWISTLE
SE2011-00620 | GB106039017160_RFF001 |  | Reduce abstraction impact by 3 Ml/d if further investigation indicates need | No |  | To control or manage abstraction | Water Demand Management | Water efficiency activity | Hydrology Groundwater | GB106039017090 | Contribute to improvement of 1+ element | Very Certain | <10000 |  |  |  | EA | Council, residents, water companies, developers | [27 empty] | Unfunded |  | No |  | 2013-11-26 | 2013-11-26 | TENTWISTLE
SE2011-00623 | GB106039017180_RFF012 |  | Run a targetted water efficiency campaign for all licensed abstractors in a waterbody. | No |  | To control or manage abstraction | Water Demand Management | Water efficiency activity | EM | GB106039017090 | No deterioration | Uncertain | <10000 |  |  |  | EA | Council, residents, water companies, developers | [27 empty] | Unfunded |  | Yes |  | 2013-11-26 | 2013-11-26 | TENTWISTLE
SE2011-00623 | GB106039017180_RFF012 |  | Run an awareness campaign through on-farm demonstrations and undertake individual advisory farm visits on high risk farms, to reduce the amount of sediment, nutrients and chemicals entering a waterbody from farmland. Educate the farming | No |  | To control or manage diffuse source inputs | Reduce diffuse pollution at source | Field & Crop - Arable soils | EM | GB106039017090 | Contribute to improvement to 1+ element. | Uncertain | <10000 |  |  |  | EA | EA, WLT, NFU , TW, UCL,KCL, RU, | [27 empty] | unfunded |  | Yes |  | 2013-11-26 | 2013-11-26 | TENTWISTLE
SE2011-00623 | GB106039017180_RFF013 |  | Use the Catchment Sensitive Farming initative to raise awareness and reduce pesticide\phosphate\sediment pollution in this waterbody. | No |  | To control or manage diffuse source inputs | Reduce diffuse pollution at source | Field & Crop - Arable soils | EM | GB106039017090 | Contribute to improvement to 1+ element. | Uncertain | <10000 |  |  |  | EA | EA, WLT, NFU , TW, UCL,KCL, RU, | [27 empty] | unfunded |  | Yes |  | 2013-11-26 | 2013-11-26 | TENTWISTLE
SE2011-00623 | GB106039017180_RFF009 |  | Use the Catchment Sensitive Farming initative to raise awareness and reduce pesticide\phosphate\sediment pollution in this waterbody. | No |  | To control or manage diffuse source inputs | Reduce diffuse pollution at source | Field & Crop - Arable soils | EM | GB106039017090 | Contribute to improvement to 1+ element. | Uncertain | <10000 |  |  |  | EA | EA, WLT, NFU , TW, UCL,KCL, RU, | [27 empty] | unfunded |  | Yes |  | 2013-11-26 | 2013-11-26 | TENTWISTLE
SE2011-00623 | GB106039017180_RFF001 |  | Water company led water efficiency campaign | No |  | To control or manage abstraction | Water Demand Management | Water efficiency activity | EM | GB106039017090 | No deterioration | Uncertain | <10000 |  |  |  | EA | Council, residents, water companies, developers | [27 empty] | Unfunded |  | Yes |  | 2013-11-26 | 2013-11-26 | TENTWISTLE
SE2011-00623 | GB106039017180_RFF001 |  | Creation of buffer strips to reduce land run off | No |  | To control or manage diffuse source inputs | Reduce diffuse pollution pathways (i.e. control entry to water environment) | Riparian management | EM | GB106039017110 | Contribute to improvement to 1+ element. | Uncertain | <10000 |  |  |  | EA | EA, WLT, NFU , TW, UCL,KCL, RU, | [27 empty] | unfunded |  | No |  | 2013-11-26 | 2013-11-26 | TENTWISTLE
SE2011-00623 | GB106039017180_RFF009 |  | Fencing to reduce cattle poaching and sediments carrying hosphates efrom entering the river. | No |  | To control or manage diffuse source inputs | Reduce diffuse pollution pathways (i.e. control entry to water environment) | Field & Crop - Livestock | EM | GB106039017110 | Contribute to improvement to 1+ element. | Uncertain | <10000 |  |  |  | EA | EA, WLT, NFU , TW, UCL,KCL, RU, | [27 empty] | unfunded |  | Yes |  | 2013-11-26 | 2013-11-26 | TENTWISTLE
SE2011-00623 | GB106039017180_RFF001 |  | Run an awareness campaign through on-farm demonstrations and undertake individual advisory farm visits on high risk farms, to reduce the amount of sediment, nutrients and chemicals entering a waterbody from farmland. Educate the farming | No |  | To control or manage diffuse source inputs | Reduce diffuse pollution at source | Field & Crop - Arable soils | EM | GB106039017110 | Contribute to improvement to 1+ element. | Uncertain | <10000 |  |  |  | EA | EA, WLT, NFU , TW, UCL,KCL, RU, | [27 empty] | unfunded |  | Yes |  | 2013-11-26 | 2013-11-26 | TENTWISTLE
SE2011-00623 | GB106039017180_RFF001 |  | Use the Catchment Sensitive Farming initative to raise awareness and reduce pesticide\phosphate\sediment pollution in this waterbody. | No |  | To control or manage diffuse source inputs | Reduce diffuse pollution at source | Field & Crop - Arable soils | EM | GB106039017110 | Contribute to improvement to 1+ element. | Uncertain | <10000 |  |  |  | EA | EA, WLT, NFU , TW, UCL,KCL, RU, | [27 empty] | unfunded |  | No |  | 2013-11-26 | 2013-11-26 | TENTWISTLE
SE2011-00623 | GB106039017180_RFF013 |  | Businesses and households should ensure all applies are connected to the right drain. For example dish washer, washing machine etc are commonly just plumbed into the surface water drains. | No |  | To control or manage point source inputs | Reduce point source pollution at source | Sewerage system re-design and rebuild | EM | GB106039017120 | Contribute to improvement to 1+ element. | Uncertain | <10000 |  |  |  | EA | EA, WLT, NFU , TW, UCL,KCL, RU, | [27 empty] | unfunded |  | Yes |  | 2013-11-26 | 2013-11-26 | TENTWISTLE
SE2011-00623 | GB106039017180_RFF012 |  | Businesses and households should ensure all applies are connected to the right drain. For example dish washer, washing machine etc are commonly just plumbed into the surface water drains. | No |  | To control or manage point source inputs | Reduce point source pollution at source | Sewerage system re-design and rebuild | EM | GB106039017120 | Contribute to improvement to 1+ element. | Uncertain | <10000 |  |  |  | EA | EA, WLT, NFU , TW, UCL,KCL, RU, | [27 empty] | unfunded |  | Yes |  | 2013-11-26 | 2013-11-26 | TENTWISTLE
SE2011-00627 | GB106039017240_RFF003 |  | Creation of buffer strips to reduce land run off | No |  | To control or manage diffuse source inputs | Reduce diffuse pollution pathways (i.e. control entry to water environment) | Riparian management | EM | GB106039017120 | Contribute to improvement to 1+ element. | Uncertain | <10000 |  |  |  | EA | EA, WLT, NFU , TW, UCL,KCL, RU, | [27 empty] | unfunded |  | Yes |  | 2013-11-26 | 2013-11-26 | TENTWISTLE
SE2011-00627 | GB106039017240_RFF003 |  | Ensure that all discharges from urban areas are being discharged to the correct drainage system. For example, All car washes should be discharged to foul sewer under a consent from the local water authority. | No |  | To control or manage point source inputs | Reduce point source pathways (i.e. control entry to water environment) | Sewerage system re-design and rebuild | EM | GB106039017120 | Contribute to improvement to 1+ element. | Uncertain | <10000 |  |  |  | EA | EA, WLT, NFU , TW, UCL,KCL, RU, | [27 empty] | unfunded |  | No |  | 2013-11-26 | 2013-11-26 | TENTWISTLE
SE2011-00627 | GB106039017240_RFF003 |  | Ensure that all discharges from urban areas are being discharged to the correct drainage system. For example, All car washes should be discharged to foul sewer under a consent from the local water authority. | No |  | To control or manage point source inputs | Reduce point source pathways (i.e. control entry to water environment) | Sewerage system re-design and rebuild | EM | GB106039017120 | Contribute to improvement to 1+ element. | Uncertain | <10000 |  |  |  | EA | EA, WLT, NFU , TW, UCL,KCL, RU, | [27 empty] | unfunded |  | Yes |  | 2013-11-26 | 2013-11-26 | TENTWISTLE
SE2011-00632 | GB106039017330_RFF005 |  | Install LWD, manage canopy and introduce gravel between Mwy and Turners Green | No |  | Improve modified habitats | Improve condition of channel bed and/or banks/shoreline | Preserve and restore habitats | Fisheries Ops | GB106039017120 | Contribute to improvement of more than 1 elelment | Quite Certain | <10000 | 2km |  |  | EA | Thames Water |  |  | 1 year | [14 empty] | SU8078156569 | [9 empty] | unfunded |  | Yes |  | 2013-11-26 | 2013-11-26 | TENTWISTLE
SE2011-00632 | GB106039017330_RFF005 |  | PP MOD | No |  | To control or manage diffuse source inputs | Reduce diffuse pollution at source | Surface run-off & drainage management | EM | GB106039017120 | Overall improvement, but below GES or GEP | Uncertain | <10000 | 5.7 km |  |  | EA | MOD, HWLT Fleet Pond Sociecty HDC | [17 empty] | SU8375252243 | [9 empty] | 0 |  | Yes |  | 2013-11-26 | 2013-11-26 | TENTWISTLE
SE2011-00632 | GB106039017330_RFF005 |  | Run an awareness campaign through on-farm demonstrations and undertake individual advisory farm visits on high risk farms, to reduce the amount of sediment, nutrients and chemicals entering a waterbody from farmland. Educate the farming | No |  | To control or manage diffuse source inputs | Reduce diffuse pollution at source | Field & Crop - Arable soils | EM | GB106039017120 | Contribute to improvement to 1+ element. | Uncertain | <10000 |  |  |  | EA | EA, WLT, NFU , TW, UCL,KCL, RU, | [27 empty] | unfunded |  | No |  | 2013-11-26 | 2013-11-26 | TENTWISTLE
SE2011-00632 | GB106039017330_RFF005 |  | Use the Catchment Sensitive Farming initative to raise awareness and reduce pesticide\phosphate\sediment pollution in this waterbody. | No |  | To control or manage diffuse source inputs | Reduce diffuse pollution at source | Field & Crop - Arable soils | EM | GB106039017120 | Contribute to improvement to 1+ element. | Uncertain | <10000 |  |  |  | EA | EA, WLT, NFU , TW, UCL,KCL, RU, | [27 empty] | unfunded |  | Yes |  | 2013-11-26 | 2013-11-26 | TENTWISTLE
SE2011-00632 | GB106039017330_RFF005 |  | Bank alterations to give channel width variation and two-stage channels. Introduction of meanders in straightened river sections. | No |  | Improve modified habitats | Improve condition of channel bed and/or banks/shoreline | Bank rehabilitation / reprofiling | Fisheries | GB106039017130 | Contribute to improvement of more than 1 elelment | Very Certain | <10000 |  |  |  | EA | BVCP, Cove Brook Group, LA |  |  | 1 year | [24 empty] | unfunded |  | No |  | 2013-11-26 | 2013-11-26 | TENTWISTLE
SE2011-00632 | GB106039017330_RFF005 |  | Bank alterations to give channel width variation and two-stage channels. Introduction of meanders in straightened river sections. | No |  | Improve modified habitats | Improve condition of channel bed and/or banks/shoreline | Bank rehabilitation / reprofiling | Fisheries Ops | GB106039017130 | Contribute to improvement of more than 1 elelment | Very Certain | <10000 |  |  |  | EA | BVCP, Cove Brook Group, LA |  |  | 1 year | [24 empty] | unfunded |  | Yes |  | 2013-11-26 | 2013-11-26 | TENTWISTLE
SE2011-00632 | GB106039017330_RFF003 |  | Businesses and households should ensure all applies are connected to the right drain. For example dish washer, washing machine etc are commonly just plumbed into the surface water drains. | No |  | To control or manage point source inputs | Reduce point source pollution at source | Sewerage system re-design and rebuild | EM | GB106039017130 | Contribute to improvement to 1+ element. | Uncertain | <10000 |  |  |  | EA | EA, WLT, NFU , TW, UCL,KCL, RU, | [27 empty] | unfunded |  | No |  | 2013-11-26 | 2013-11-26 | TENTWISTLE
SE2011-00700 |  |  | Businesses and households should ensure all applies are connected to the right drain. For example dish washer, washing machine etc are commonly just plumbed into the surface water drains. | No |  | To control or manage point source inputs | Reduce point source pollution at source | Sewerage system re-design and rebuild | EM | GB106039017130 | Contribute to improvement to 1+ element. | Uncertain | <10000 |  |  |  | EA | EA, WLT, NFU , TW, UCL,KCL, RU, | [27 empty] | unfunded |  | No |  | 2013-11-26 | 2013-11-26 | TENTWISTLE
SE2011-00703 | GB106039023190_RFF003 |  | Creation of buffer strips to reduce land run off | No |  | To control or manage diffuse source inputs | Reduce diffuse pollution pathways (i.e. control entry to water environment) | Riparian management | EM | GB106039017130 | Contribute to improvement to 1+ element. | Uncertain | <10000 |  |  |  | EA | EA, WLT, NFU , TW, UCL,KCL, RU, | [27 empty] | unfunded |  | Yes |  | 2013-11-26 | 2013-11-26 | TENTWISTLE
SE2011-00703 | GB106039023190_RFF003 |  | Ensure that all discharges from urban areas are being discharged to the correct drainage system. For example, All car washes should be discharged to foul sewer under a consent from the local water authority. | No |  | To control or manage point source inputs | Reduce point source pathways (i.e. control entry to water environment) | Sewerage system re-design and rebuild | EM | GB106039017130 | Contribute to improvement to 1+ element. | Uncertain | <10000 |  |  |  | EA | EA, WLT, NFU , TW, UCL,KCL, RU, | [27 empty] | unfunded |  | No |  | 2013-11-26 | 2013-11-26 | TENTWISTLE
SE2011-00703 | GB106039023190_RFF003 |  | Ensure that all discharges from urban areas are being discharged to the correct drainage system. For example, All car washes should be discharged to foul sewer under a consent from the local water authority. | No |  | To control or manage point source inputs | Reduce point source pathways (i.e. control entry to water environment) | Sewerage system re-design and rebuild | EM | GB106039017130 | Contribute to improvement to 1+ element. | Uncertain | <10000 |  |  |  | EA | EA, WLT, NFU , TW, UCL,KCL, RU, | [27 empty] | unfunded |  | Yes |  | 2013-11-26 | 2013-11-26 | TENTWISTLE
SE2011-00703 | GB106039023190_RFF004 |  | Introduction of gravels to create spawning opportunities for fish, and restore bed profile variation. Reduce shading to promote in channel vegetation growth and install woody debris in the channel. | No |  | Improve modified habitats | Improve condition of channel bed and/or banks/shoreline | Preserve and restore habitats | Fisheries | GB106039017130 | Contribute to improvement of more than 1 elelment | Very Certain | <10000 | 2km |  |  | EA | BVCP, Cove Brook Group, LA |  |  | 1 year | [14 empty] | SU8558855587 | [9 empty] | unfunded |  | No |  | 2013-11-26 | 2013-11-26 | TENTWISTLE
SE2011-00703 | GB106039023190_RFF003 |  | weir removal/lowering or installation of fish pass as required and habitat enhancement | No |  | Improve modified habitats | Removal or easement of barriers to fish migration | Improvements to longitudinal connectivity | Fisheries | GB106039017130 | Contribute to improvement of more than 1 elelment | Very Certain | <10000 | 3 km |  |  | EA | BVCP, Cove Brook Group, LA |  |  | 1 year | [14 empty] | SU8555756773 | [9 empty] | unfunded |  | Yes |  | 2013-11-26 | 2013-11-26 | TENTWISTLE
SE2011-00703 | GB106039023190_RFF003 |  | Fish pass or bypass channel on Longbridge Mill sluice/weir | No |  | Improve modified habitats | Removal or easement of barriers to fish migration | Improvements to longitudinal connectivity | Fisheries | GB106039017150 | Contribute to improvement of more than 1 elelment | Very Certain | <10000 | 11 km |  |  | EA | Estate/landowner, brewery |  |  | 2 years | [14 empty] | SU6835758189 | [9 empty] | unfunded |  | Yes |  | 2013-11-26 | 2013-11-26 | TENTWISTLE
SE2011-00703 | GB106039023190_RFF003 |  | Remove Longbridge Mill sluice/weir | No |  | Improve modified habitats | Removal or easement of barriers to fish migration | Improvements to longitudinal connectivity | Hydrology Fisheries | GB106039017150 | Contribute to improvement of more than 1 elelment | Very Certain | <10000 | 11 km |  |  | EA | Estate/landowner, brewery |  |  | 2 years | [14 empty] | SU6835758189 | [9 empty] | unfunded |  | No |  | 2013-11-26 | 2013-11-26 | TENTWISTLE
SE2011-00703 | GB106039023190_RFF004 |  | Creation of buffer strips to reduce land run off | No |  | To control or manage diffuse source inputs | Reduce diffuse pollution pathways (i.e. control entry to water environment) | Riparian management | EM | GB106039017160 | Contribute to improvement to 1+ element. | Uncertain | <10000 |  |  |  | EA | EA, WLT, NFU , TW, UCL,KCL, RU, | [27 empty] | unfunded |  | No |  | 2013-11-26 | 2013-11-26 | TENTWISTLE
| GB106039017080_RFF003 |  | Run an awareness campaign through on-farm demonstrations and undertake individual advisory farm visits on high risk farms, to reduce the amount of sediment, nutrients and chemicals entering a waterbody from farmland. Educate the farming | No |  | To control or manage diffuse source inputs | Reduce diffuse pollution at source | Field & Crop - Arable soils | EM | GB106039017160 | Contribute to improvement to 1+ element. | Uncertain | 10001-25001 |  |  |  | EA | EA, WLT, NFU , TW, UCL,KCL, RU, | [24 empty] | SU6616053090 |  |  | unfunded |  | No |  | 2013-11-26 | 2013-11-26 | TENTWISTLE
| GB106039017080_RFF003 |  | Use the Catchment Sensitive Farming initative to raise awareness and reduce pesticide\phosphate\sediment pollution in this waterbody. | No |  | To control or manage diffuse source inputs | Reduce diffuse pollution at source | Field & Crop - Arable soils | EM | GB106039017160 | Contribute to improvement to 1+ element. | Uncertain | 10001-25001 |  |  |  | EA | EA, WLT, NFU , TW, UCL,KCL, RU, | [24 empty] | SU6649853302 |  |  | unfunded |  | No |  | 2013-11-26 | 2013-11-26 | TENTWISTLE
| GB106039017080_RFF003 |  | Badshot Lea Lake outlet. Take Badshot Lea offline. | No |  | Improve modified habitats | Removal or easement of barriers to fish migration | Improvements to longitudinal connectivity | Fisheries | GB106039017180 | Contribute to improvement of more than 1 elelment | Very Certain | 10001-25001 | 2 km |  |  | EA | LFCC, BVCP, LA |  |  | 3 years | [14 empty] | SU8649249177 | [9 empty] | unfunded |  | No |  | 2013-11-26 | 2013-11-26 | TENTWISTLE
| GB106039017080_RFF003 |  | Businesses and households should ensure all applies are connected to the right drain. For example dish washer, washing machine etc are commonly just plumbed into the surface water drains. | No |  | To control or manage point source inputs | Reduce point source pollution at source | Sewerage system re-design and rebuild | EM | GB106039017180 | Contribute to improvement to 1+ element. | Uncertain | 10001-25001 |  |  |  | EA | EA, WLT, NFU , TW, UCL,KCL, RU, | [24 empty] | SU6689253812 |  |  | unfunded |  | No |  | 2013-11-26 | 2013-11-26 | TENTWISTLE
| GB106039017080_RFF003 |  | Businesses and households should ensure all applies are connected to the right drain. For example dish washer, washing machine etc are commonly just plumbed into the surface water drains. | No |  | To control or manage point source inputs | Reduce point source pollution at source | Sewerage system re-design and rebuild | EM | GB106039017180 | Contribute to improvement to 1+ element. | Uncertain | <10000 |  |  |  | EA | EA, WLT, NFU , TW, UCL,KCL, RU, | [24 empty] | SU6689253812 |  |  | unfunded |  | No |  | 2013-11-26 | 2013-11-26 | TENTWISTLE
| GB106039017080_RFF003 |  | Creation of buffer strips to reduce land run off | No |  | To control or manage diffuse source inputs | Reduce diffuse pollution pathways (i.e. control entry to water environment) | Riparian management | EM | GB106039017180 | Contribute to improvement to 1+ element. | Uncertain | <10000 |  |  |  | EA | EA, WLT, NFU , TW, UCL,KCL, RU, | [24 empty] | SU6689254019 |  |  | unfunded |  | No |  | 2013-11-26 | 2013-11-26 | TENTWISTLE
| GB106039017080_RFF003 |  | Creation of buffer strips to reduce land run off | No |  | To control or manage diffuse source inputs | Reduce diffuse pollution pathways (i.e. control entry to water environment) | Riparian management | EM | GB106039017180 | Contribute to improvement to 1+ element. | Uncertain | <10000 |  |  |  | EA | EA, WLT, NFU , TW, UCL,KCL, RU, | [18 empty] | SU6692653885 |  |  | SU6765354632 | [5 empty] | unfunded |  | No |  | 2013-11-26 | 2013-11-26 | TENTWISTLE
| GB106039017080_RFF003 |  | Ensure that all discharges from urban areas are being discharged to the correct drainage system. For example, All car washes should be discharged to foul sewer under a consent from the local water authority. | No |  | To control or manage point source inputs | Reduce point source pathways (i.e. control entry to water environment) | Sewerage system re-design and rebuild | EM | GB106039017180 | Contribute to improvement to 1+ element. | Uncertain | <10000 |  |  |  | EA | EA, WLT, NFU , TW, UCL,KCL, RU, | [24 empty] | SU6495352413 |  |  | unfunded |  | No |  | 2013-11-26 | 2013-11-26 | TENTWISTLE
| GB106039017080_RFF003 |  | Ensure that all discharges from urban areas are being discharged to the correct drainage system. For example, All car washes should be discharged to foul sewer under a consent from the local water authority. | No |  | To control or manage point source inputs | Reduce point source pathways (i.e. control entry to water environment) | Sewerage system re-design and rebuild | EM | GB106039017180 | Contribute to improvement to 1+ element. | Uncertain | <10000 |  |  |  | EA | EA, WLT, NFU , TW, UCL,KCL, RU, | [24 empty] | SU6691053900 |  |  | unfunded |  | No |  | 2013-11-26 | 2013-11-26 | TENTWISTLE
| GB106039017080_RFF003 |  | Ensure that all discharges from urban areas are being discharged to the correct drainage system. For example, All car washes should be discharged to foul sewer under a consent from the local water authority. | No |  | To control or manage point source inputs | Reduce point source pathways (i.e. control entry to water environment) | Sewerage system re-design and rebuild | EM | GB106039017180 | Contribute to improvement to 1+ element. | Uncertain | <10000 |  |  |  | EA | EA, WLT, NFU , TW, UCL,KCL, RU, | [24 empty] | SU6689253812 |  |  | unfunded |  | No |  | 2013-11-26 | 2013-11-26 | TENTWISTLE
| GB106039017080_RFF003 |  | Introduction of gravels to create spawning opportunities for fish, and restore bed profile variation. Reduce shading to promote in channel vegetation growth and install woody debris in the channel. Bank alterations to give channel width variation and two-stage channels. Introduction of meanders in straightened river sections. | No |  | Improve modified habitats | Improve condition of channel bed and/or banks/shoreline | Preserve and restore habitats | FCRM | GB106039017180 | 0 |  | <10000 |  |  |  | EA | Hansons BVCP EA WTT | [17 empty] | Farnham Quarry Phase 3 | [9 empty] | 0 |  | No |  | 2013-11-26 | 2013-11-26 | TENTWISTLE
| GB106039017080_RFF001 |  | Introduction of gravels to create spawning opportunities for fish, and restore bed profile variation. Reduce shading to promote in channel vegetation growth and install woody debris in the channel. Bank alterations to give channel width variation and two-stage channels. Introduction of meanders in straightened river sections. | No |  | Improve modified habitats | Improve condition of channel bed and/or banks/shoreline | Preserve and restore habitats | Fisheries | GB106039017180 | Contribute to improvement of more than 1 elelment | Very Certain | <10000 | 1 km |  |  | EA | LFCC, BVCP |  |  | 1 year | [14 empty] | SU8594659275 and SU8812348988 | [9 empty] | unfunded |  | No |  | 2013-11-26 | 2013-11-26 | TENTWISTLE
| GB106039017080_RFF001 |  | Morphology options will help. | No |  | 0 | 0 | 0 | Fisheries | GB106039017180 | Contribute to improvement of more than 1 elelment |  | <10000 |  |  |  | EA | 0 | [27 empty] | 0 |  | No |  | 2013-11-26 | 2013-11-26 | TENTWISTLE
| GB106039017080_RFF001 |  | Provide advice and training on identification, control and disposal of invasive non-native species to all relevant groups and encourage monitoring schemes. Rolled out through partner organisations BVCP, LFCC etc. Advertise the need for authorisation from the Environment Agency and that traps need to be compliant. | Yes |  | Control or manage invasive species. | Building awareness and understanding. | Seek sustainable and cost-effective methods for managing established invasions of species. | Fisheries | GB106039017180 | No deterioration | Uncertain | <10000 | 15 km |  |  | EA | LFCC, NE, BVCP, WPS |  |  | 4 weeks | [14 empty] | SU8502749906 to SU8632958331 | [9 empty] | 0 |  | No |  | 2013-11-26 | 2013-11-26 | TENTWISTLE
| GB106039017080_RFF001 |  | Provide advice and training on identification, control and disposal of invasive non-native species to all relevant groups and encourage monitoring schemes. Rolled out through partner organisations BVCP, LFCC etc. Advertise the need for authorisation from the Environment Agency and that traps need to be compliant. | Yes |  | Control or manage invasive species. | Building awareness and understanding. | Seek sustainable and cost-effective methods for managing established invasions of species. | Fisheries | GB106039017180 | No deterioration | Uncertain | <10000 | 15 km |  |  | EA | LFCC, NE, BVCP, WPS |  |  | 4 weeks | [14 empty] | SU8502749906 to SU8632958331 | [9 empty] | 0 |  | No |  | 2013-11-26 | 2013-11-26 | TENTWISTLE
| GB106039017080_RFF001 |  | Run an awareness campaign through on-farm demonstrations and undertake individual advisory farm visits on high risk farms, to reduce the amount of sediment, nutrients and chemicals entering a waterbody from farmland. Educate the farming | No |  | To control or manage diffuse source inputs | Reduce diffuse pollution at source | Field & Crop - Arable soils | EM | GB106039017180 | Contribute to improvement to 1+ element. | Uncertain | <10000 |  |  |  | EA | EA, WLT, NFU , TW, UCL,KCL, RU, | [27 empty] | unfunded |  | No |  | 2013-11-26 | 2013-11-26 | TENTWISTLE
| GB106039017080_RFF001 |  | Run an awareness campaign through on-farm demonstrations and undertake individual advisory farm visits on high risk farms, to reduce the amount of sediment, nutrients and chemicals entering a waterbody from farmland. Educate the farming | No |  | To control or manage diffuse source inputs | Reduce diffuse pollution at source | Field & Crop - Arable soils | EM | GB106039017180 | Contribute to improvement to 1+ element. | Uncertain | <10000 |  |  |  | EA | EA, WLT, NFU , TW, UCL,KCL, RU, | [27 empty] | unfunded |  | No |  | 2013-11-26 | 2013-11-26 | TENTWISTLE
| GB106039017080_RFF008 |  | Use the Catchment Sensitive Farming initative to raise awareness and reduce pesticide\phosphate\sediment pollution in this waterbody. | No |  | To control or manage diffuse source inputs | Reduce diffuse pollution at source | Field & Crop - Arable soils | EM | GB106039017180 | Contribute to improvement to 1+ element. | Uncertain | <10000 |  |  |  | EA | EA, WLT, NFU , TW, UCL,KCL, RU, | [27 empty] | unfunded |  | Yes |  | 2013-11-26 | 2013-11-26 | TENTWISTLE
SE2011-00607 | GB106039017090_RFF007 |  | Use the Catchment Sensitive Farming initative to raise awareness and reduce pesticide\phosphate\sediment pollution in this waterbody. | No |  | To control or manage diffuse source inputs | Reduce diffuse pollution at source | Field & Crop - Arable soils | EM | GB106039017180 | Contribute to improvement to 1+ element. | Uncertain | <10000 |  |  |  | EA | EA, WLT, NFU , TW, UCL,KCL, RU, | [27 empty] | unfunded |  | Yes |  | 2013-11-26 | 2013-11-26 | TENTWISTLE
TH2009-15551 | GB106039017090_RFF003 |  | Castle Mill, lower wier and bypass channel and habitat enhancement. | No |  | Improve modified habitats | Removal or easement of barriers to fish migration | Improvements to longitudinal connectivity | Fisheries | GB106039017240 | Contribute to improvement of 1 elelment | Very Certain | <10000 | 2km |  |  | EA | landowner | [17 empty] | SU7272651962 | [9 empty] | 0 |  | No |  | 2013-11-26 | 2013-11-26 | TENTWISTLE
TH2009-15551 | GB106039017090_RFF003 |  | Creation of buffer strips to reduce land run off | No |  | To control or manage diffuse source inputs | Reduce diffuse pollution pathways (i.e. control entry to water environment) | Riparian management | EM | GB106039017240 | Contribute to improvement to 1+ element. | Uncertain | 10001-25001 |  |  |  | EA | EA, WLT, NFU , TW, UCL,KCL, RU, | [27 empty] | unfunded |  | No |  | 2013-11-26 | 2013-11-26 | TENTWISTLE
TH2009-15551 | GB106039017090_RFF003 |  | Dipley Mill complex (5 structures) technical and bypass, as well as habitat enhancement. | No |  | Improve modified habitats | Removal or easement of barriers to fish migration | Improvements to longitudinal connectivity | Fisheries | GB106039017240 | Contribute to improvement of 1 elelment | Very Certain | <10000 | 3km |  |  | EA | landowner |  |  | 3 years | [14 empty] | SU7423957695 | [9 empty] | 0 |  | No |  | 2013-11-26 | 2013-11-26 | TENTWISTLE
TH2009-15551 | GB106039017090_RFF003 |  | Educate Mill owners on connectivity and flow. | No |  | Improve modified habitats | Removal or easement of barriers to fish migration | Improvements to longitudinal connectivity | Fisheries | GB106039017240 | Contribute to improvement of 1 elelment | Uncertain | 10001-25001 |  |  |  | EA | WWPS | [17 empty] | waterbody | [9 empty] | 0 |  | No |  | 2013-11-26 | 2013-11-26 | TENTWISTLE
| GB106039017080_RFF001 |  | Habitat enhancemets to ensure that weirs at Lodge Farm complex (7 weirs) and gauging weir ar e passable. | No |  | Improve modified habitats | Removal or easement of barriers to fish migration | Improvements to longitudinal connectivity | Fisheries | GB106039017240 | Contribute to improvement of 1 elelment | Very Certain | <10000 | 1km |  |  | EA | landowner | [17 empty] | SU7341552346 | [9 empty] | 0 |  | No |  | 2013-11-26 | 2013-11-26 | TENTWISTLE
|  |  | Poland Mill structures, technical fish pass or removal and habitat enhancement. | No |  | Improve modified habitats | Removal or easement of barriers to fish migration | Improvements to longitudinal connectivity | Fisheries | GB106039017240 | Contribute to improvement of 1 elelment | Very Certain | <10000 | 2km |  |  | EA | landowner |  |  | 2 years | [14 empty] | SU7428853140 | [9 empty] | 0 |  | No |  | 2013-11-26 | 2013-11-26 | TENTWISTLE
SE2011-00614 | GB106039017120_RFF002 |  | Provide advice and training on identification, control and disposal of invasive non-native species to all relevant groups and encourage monitoring schemes. Rolled out through partner organisations BVCP, LFCC etc. Advertise the need for authorisation from the Environment Agency and that traps need to be compliant. | No |  | Control or manage invasive species. | Building awareness and understanding. | Seek sustainable and cost-effective methods for managing established invasions of species. | Fisheries | GB106039017240 | No deterioration | Uncertain | <10000 | Catchment |  |  | EA | LFCC, NE, BVCP, WPS |  |  | 4 weeks | [14 empty] | SU8594354787 | [9 empty] | 0 |  | No |  | 2013-11-26 | 2013-11-26 | TENTWISTLE
SE2011JR-131 | GB106039017130_RFF003 |  | remove weir d/s Whitwater Mill, Scotts Farm and habitat enhancement. | No |  | Improve modified habitats | Removal or easement of barriers to fish migration | Improvements to longitudinal connectivity | Fisheries | GB106039017240 | Contribute to improvement of 1 elelment | Very Certain | <10000 | 1km |  |  | EA | Landowner Parish Council |  |  | 2 years | [14 empty] | SU7383755503 | [9 empty] | 0 |  | No |  | 2013-11-26 | 2013-11-26 | TENTWISTLE
SE2011JR-131 | GB106039017130_RFF001 |  | Risley Mill, bypass channel/easement and habitat enhancement. | No |  | Improve modified habitats | Removal or easement of barriers to fish migration | Improvements to longitudinal connectivity | Fisheries | GB106039017240 | Contribute to improvement of 1 elelment | Very Certain | <10000 | 6 km |  |  | EA | landowaner |  |  | 2 years | [14 empty] | SU7381762353 | [9 empty] | 0 |  | No |  | 2013-11-26 | 2013-11-26 | TENTWISTLE
SE2011JR-131 | GB106039017130_RFF003 |  | Run an awareness campaign through on-farm demonstrations and undertake individual advisory farm visits on high risk farms, to reduce the amount of sediment, nutrients and chemicals entering a waterbody from farmland. Educate the farming | No |  | To control or manage diffuse source inputs | Reduce diffuse pollution at source | Field & Crop - Arable soils | EM | GB106039017240 | Contribute to improvement to 1+ element. | Uncertain | <10000 |  |  |  | EA | EA, WLT, NFU , TW, UCL,KCL, RU, | [27 empty] | unfunded |  | No |  | 2013-11-26 | 2013-11-26 | TENTWISTLE
SE2011JR-131 | GB106039017130_RFF002 |  | technical and bypass Whitewater Mill and habitat enhancement. | No |  | Improve modified habitats | Removal or easement of barriers to fish migration | Improvements to longitudinal connectivity | Fisheries | GB106039017240 | Contribute to improvement of 1 elelment | Very Certain | 10001-25001 | 2.5km |  |  | EA | landowner |  |  | 2 years | [14 empty] | SU7363455117 | [9 empty] | 0 |  | No |  | 2013-11-26 | 2013-11-26 | TENTWISTLE
SE2011-00634 | GB106039017330_RFF002 |  | The Mill House, Warnborough Green. Lower weir and narrow stream to make the weir passable as well as habitat enhancement. | No |  | Improve modified habitats | Removal or easement of barriers to fish migration | Improvements to longitudinal connectivity | Fisheries | GB106039017240 | Contribute to improvement of 1 elelment | Very Certain | 10001-25001 | 500m |  |  | EA | landowner | [17 empty] | SU7315652146 | [9 empty] | 0 |  | No |  | 2013-11-26 | 2013-11-26 | TENTWISTLE
SE2011-00634 | GB106039017330_RFF002 |  | Use the Catchment Sensitive Farming initative to raise awareness and reduce pesticide\phosphate\sediment pollution in this waterbody. | No |  | To control or manage diffuse source inputs | Reduce diffuse pollution at source | Field & Crop - Arable soils | EM | GB106039017240 | Contribute to improvement to 1+ element. | Uncertain | 10001-25001 |  |  |  | EA | EA, WLT, NFU , TW, UCL,KCL, RU, | [27 empty] | unfunded |  | No |  | 2013-11-26 | 2013-11-26 | TENTWISTLE
SE2011JR-107 | GB106039017180_RFF014 |  | Enable fish passage at the Swallowfield gauging stations and consider replacing with non-impounding gauging equipment. | No |  | Improve modified habitats | Removal or easement of barriers to fish migration | Improvements to longitudinal connectivity | Fisheries | GB106039017320 | Contribute to improvement of 1 elelment | Very Certain | <10000 | 5km |  |  | EA | Hydrometry |  |  | 1 year | [14 empty] | SU7309964786 | [9 empty] | 0 |  | Yes |  | 2013-11-26 | 2013-11-26 | TENTWISTLE
SE2011JR-107 | GB106039017180_RFF003 |  | Creation of buffer strips to reduce land run off | No |  | To control or manage diffuse source inputs | Reduce diffuse pollution pathways (i.e. control entry to water environment) | Riparian management | EM | GB106039017330 | Contribute to improvement to 1+ element. | Uncertain | <10000 |  |  |  | EA | EA, WLT, NFU , TW, UCL,KCL, RU, | [27 empty] | unfunded |  | Yes |  | 2013-11-26 | 2013-11-26 | TENTWISTLE
SE2011JR-107 | GB106039017180_RFF014 |  | Creation of buffer strips to reduce land run off | No |  | To control or manage diffuse source inputs | Reduce diffuse pollution pathways (i.e. control entry to water environment) | Riparian management | EM | GB106039017330 | Contribute to improvement to 1+ element. | Uncertain | <10000 |  |  |  | EA | EA, WLT, NFU , TW, UCL,KCL, RU, | [27 empty] | unfunded |  | Yes |  | 2013-11-26 | 2013-11-26 | TENTWISTLE
SE2011JR-107 | GB106039017180_RFF003 |  | Fencing to reduce cattle poaching and sediments carrying hosphates efrom entering the river. | No |  | To control or manage diffuse source inputs | Reduce diffuse pollution pathways (i.e. control entry to water environment) | Field & Crop - Livestock | EM | GB106039017330 | Contribute to improvement to 1+ element. | Uncertain | <10000 |  |  |  | EA | EA, WLT, NFU , TW, UCL,KCL, RU, | [27 empty] | unfunded |  | Yes |  | 2013-11-26 | 2013-11-26 | TENTWISTLE
SE2011JR-107 | GB106039017180_RFF003 |  | Improve habitats and connectivity at the Priory Mill complex, removal/lowering or installation of fish pass as required and habitat enhancement | No |  | Improve modified habitats | Removal or easement of barriers to fish migration | Improvements to longitudinal connectivity | Fisheries | GB106039017330 | Contribute to improvement of more than 1 elelment | Uncertain | <10000 | 2km |  |  | EA | landowner |  |  | 2 years | [14 empty] | SU7032363443 | [9 empty] | unfunded |  | No |  | 2013-11-26 | 2013-11-26 | TENTWISTLE
SE2011JR-107 | GB106039017180_RFF003 |  | Provide advice and training on identification, control and disposal of invasive non-native species to all relevant groups and encourage monitoring schemes. Rolled out through partner organisations BVCP, LFCC etc. Advertise the need for authorisation from the Environment Agency and that traps need to be compliant. | No |  | Control or manage invasive species. | Building awareness and understanding. | Seek sustainable and cost-effective methods for managing established invasions of species. | Fisheries | GB106039017330 | No deterioration | Uncertain | <10000 | whole catchment |  |  | EA | LFCC, NE, BVCP, WPS |  |  | 4 weeks | [14 empty] | SU7255165634 (centre of catchment) | [9 empty] | 0 |  | No |  | 2013-11-26 | 2013-11-26 | TENTWISTLE
SE2011-00626 | GB106039017240_RFF004 |  | Remove imounding structure at Priory Mill | No |  | Improve modified habitats | Removal or easement of barriers to fish migration | Improvements to longitudinal connectivity | Fisheries | GB106039017330 | Contribute to improvement of 1 elelment | Quite Certain | <10000 | 1km |  |  | EA | Estate / Landowner |  |  | 1 year | [14 empty] | SU7086464119 | [9 empty] | unfunded |  | Yes |  | 2013-11-26 | 2013-11-26 | TENTWISTLE
SE2011-00626 | GB106039017240_RFF002 |  | Remove imounding structure at Priory Mill | No |  | Improve modified habitats | Removal or easement of barriers to fish migration | Improvements to longitudinal connectivity | Fisheries | GB106039017330 | Contribute to improvement of 1 elelment | Quite Certain | <10000 | 1km |  |  | EA | Estate / Landowner |  |  | 2 year | [14 empty] | SU7086464119 | [9 empty] | unfunded |  | No |  | 2013-11-26 | 2013-11-26 | TENTWISTLE
SE2011-00626 | GB106039017240_RFF002 |  | Run an awareness campaign through on-farm demonstrations and undertake individual advisory farm visits on high risk farms, to reduce the amount of sediment, nutrients and chemicals entering a waterbody from farmland. Educate the farming | No |  | To control or manage diffuse source inputs | Reduce diffuse pollution at source | Field & Crop - Arable soils | EM | GB106039017330 | Contribute to improvement to 1+ element. | Uncertain | 10001-25000 |  |  |  | EA | EA, WLT, NFU , TW, UCL,KCL, RU, | [27 empty] | unfunded |  | No |  | 2013-11-26 | 2013-11-26 | TENTWISTLE
SE2011-00626 | GB106039017240_RFF002 |  | Run an awareness campaign through on-farm demonstrations and undertake individual advisory farm visits on high risk farms, to reduce the amount of sediment, nutrients and chemicals entering a waterbody from farmland. Educate the farming | No |  | To control or manage diffuse source inputs | Reduce diffuse pollution at source | Field & Crop - Arable soils | EM | GB106039017330 | Contribute to improvement to 1+ element. | Uncertain | 10001-25000 |  |  |  | EA | EA, WLT, NFU , TW, UCL,KCL, RU, | [27 empty] | unfunded |  | No |  | 2013-11-26 | 2013-11-26 | TENTWISTLE
SE2011-00626 | GB106039017240_RFF002 |  | Take the broadwater off-line | No |  | Improve modified habitats | Removal or easement of barriers to fish migration | Improvements to longitudinal connectivity | Fisheries | GB106039017330 | Contribute to improvement of 1 elelment | Very Certain | 10001-25001 | 5km |  |  | EA | Estate / Landowner |  |  | 3 years | [14 empty] | SU7047961821 | [6 empty] | SU7362955129 |  |  | unfunded |  | No |  | 2013-11-26 | 2013-11-26 | TENTWISTLE
SE2011-00626 | GB106039017240_RFF002 |  | Use the Catchment Sensitive Farming initative to raise awareness and reduce pesticide\phosphate\sediment pollution in this waterbody. | No |  | To control or manage diffuse source inputs | Reduce diffuse pollution at source | Field & Crop - Arable soils | EM | GB106039017330 | Contribute to improvement to 1+ element. | Uncertain | <10000 |  |  |  | EA | EA, WLT, NFU , TW, UCL,KCL, RU, | [27 empty] | unfunded |  | No |  | 2013-11-26 | 2013-11-26 | TENTWISTLE
SE2011-00626 | GB106039017240_RFF002 |  | Use the Catchment Sensitive Farming initative to raise awareness and reduce pesticide\phosphate\sediment pollution in this waterbody. | No |  | To control or manage diffuse source inputs | Reduce diffuse pollution at source | Field & Crop - Arable soils | EM | GB106039017330 | Contribute to improvement to 1+ element. | Uncertain | 10001-25001 |  |  |  | EA | EA, WLT, NFU , TW, UCL,KCL, RU, | [27 empty] | unfunded |  | No |  | 2013-11-26 | 2013-11-26 | TENTWISTLE
SE2011-00626 | GB106039017240_RFF002 |  | Remove structure / install fish pass or bypass channel at Riverside walk, Wokingham and enhance river morphology | No |  | Improve modified habitats | Removal or easement of barriers to fish migration | Improvements to longitudinal connectivity | 0 | GB106039023130 | Contribute to improvement of more than 1 elelment | Quite Certain | 10001-25001 | 3km |  |  | EA | LA |  |  | 2 years | [14 empty] | SU7983769265 | [9 empty] | unfunded |  | No |  | 2013-11-26 | 2013-11-26 | TENTWISTLE
SE2011-00626 | GB106039017240_RFF002 |  | Fencing to reduce cattle poaching and sediments carrying hosphates efrom entering the river. | No |  | To control or manage diffuse source inputs | Reduce diffuse pollution pathways (i.e. control entry to water environment) | Field & Crop - Livestock | EM | GB106039023160 | Contribute to improvement to 1+ element. | Uncertain | 10001-25001 |  |  |  | EA | EA, WLT, NFU , TW, UCL,KCL, RU, | [27 empty] | unfunded |  | No |  | 2013-11-26 | 2013-11-26 | TENTWISTLE
SE2011-00626 | GB106039017240_RFF002 |  | Improvements to bypass channel at Sheepbridge and enhance habitat | No |  | Improve modified habitats | Removal or easement of barriers to fish migration | Improvements to longitudinal connectivity | Fisheries | GB106039023160 | Contribute to improvement of more than 1 elelment | Very Certain | <10000 | 5km |  |  | EA | Landowner, Swallowfield fishing club, Hydrometry |  |  | 2 years | [14 empty] | SU7188364976 | [9 empty] | unfunded |  | Yes |  | 2013-11-26 | 2013-11-26 | TENTWISTLE
TH2009-15584 | GB106039017320_RFF002 |  | Sandford Farm weir removal/lowering or installation of fish pass as required and habitat enhancement | No |  | Improve modified habitats | Removal or easement of barriers to fish migration | Improvements to longitudinal connectivity | Fisheries | GB106039023160 | Contribute to improvement of 1 elelment | Very Certain | 10001-25001 | 3km |  |  | EA | Developer / LA / Landowner |  |  | 1 | [14 empty] | SU7824473743 | [9 empty] | unfunded |  | No |  | 2013-11-26 | 2013-11-26 | TENTWISTLE
SE2011-00634 | GB106039017330_RFF002 |  | Sheep Bridge (2) weir removal/lowering or installation of fish pass as required and habitat enhancement | No |  | Improve modified habitats | Removal or easement of barriers to fish migration | Improvements to longitudinal connectivity | Fisheries | GB106039023160 | Contribute to improvement of more than 1 elelment | Quite Certain | <10000 | 5km |  |  | EA | Hydrometry, Landowner |  |  | 2 years | [14 empty] | SU7203565318 | [9 empty] | unfunded |  | No |  | 2013-11-26 | 2013-11-26 | TENTWISTLE
SE2011-00634 | GB106039017330_RFF002 |  | Sindlesham Mill (3) weir removal/lowering or installation of fish pass as required and habitat enhancement | No |  | Improve modified habitats | Removal or easement of barriers to fish migration | Improvements to longitudinal connectivity | Fisheries | GB106039023160 | Contribute to improvement of 1 elelment | Quite Certain | 10001-25001 | 3km |  |  | EA | Farnham AC |  |  | 2 years | [14 empty] | SU7668270272 | [9 empty] | unfunded |  | No |  | 2013-11-26 | 2013-11-26 | TENTWISTLE
SE2011-00634 | GB106039017330_RFF002 |  | St Patricks Stream, river and wetland project. Create a back water and use the gravel to create riffles and spawning habitat, include woody debris. | Yes |  | Improve modified habitats | Improve condition of channel bed and/or banks/shoreline | Preserve and restore habitats | Fisheries | GB106039023160 | Contribute to improvement of 1 elelment | Very Certain | 10001-25001 | 4 km |  |  | EA | Twyford & District, New AC, residents, FCRM, Barbel Society, CLPS, |  |  | 2 years | [14 empty] | SU7720477553 | [9 empty] | 0 |  | No |  | 2013-11-26 | 2013-11-26 | TENTWISTLE
SE2011-00634 | GB106039017330_RFF010 |  | Stanford End (3)weir removal/lowering or installation of fish pass as required and habitat enhancement | No |  | Improve modified habitats | Removal or easement of barriers to fish migration | Improvements to longitudinal connectivity | Fisheries | GB106039023160 | Contribute to improvement of more than 1 elelment |  | <10000 |  |  |  | EA | 0 | [17 empty] | SU7072563071 | [9 empty] | 0 |  | Yes |  | 2013-11-26 | 2013-11-26 | TENTWISTLE
SE2011-00699 | GB106039023160_RFF001 |  | Stratfield Saye weir removal/lowering or installation of fish pass as required and habitat enhancement | No |  | Improve modified habitats | Removal or easement of barriers to fish migration | Improvements to longitudinal connectivity | Fisheries | GB106039023160 | Contribute to improvement of more than 1 elelment | Quite Certain | 10001-25001 | 3km |  |  | EA | Landowner |  |  | 2 years | [14 empty] | SU6829659537 | [9 empty] | unfunded |  | No |  | 2013-11-26 | 2013-11-26 | TENTWISTLE
SE2011-00699 | GB106039023160_RFF001 |  | Tumbling Bay weirs (2)weir removal/lowering or installation of fish pass as required and habitat enhancement | No |  | Improve modified habitats | Removal or easement of barriers to fish migration | Improvements to longitudinal connectivity | Fisheries | GB106039023160 | Contribute to improvement of more than 1 elelment |  | 10001-25001 | 3km |  |  | EA | Landowner |  |  | 2 years | [14 empty] | SU7051462085 | [9 empty] | unfunded |  | No |  | 2013-11-26 | 2013-11-26 | TENTWISTLE
SE2011-00699 | GB106039023160_RFF001 |  | Twyford Mill structures (2) weir removal/lowering or installation of fish pass as required and habitat enhancement | No |  | Improve modified habitats | Removal or easement of barriers to fish migration | Improvements to longitudinal connectivity | Fisheries | GB106039023160 | Contribute to improvement of 1 elelment | Very Certain | 10001-25001 | 4km |  |  | EA | LA |  |  | 1 year | [14 empty] | SU7852276002 | [9 empty] | unfunded |  | No |  | 2013-11-26 | 2013-11-26 | TENTWISTLE
SE2011-00699 | GB106039023160_RFF001 |  | Weir feeding distributary u/s Sandford Bridge weir removal/lowering or installation of fish pass as required and habitat enhancement | No |  | Improve modified habitats | Removal or easement of barriers to fish migration | Improvements to longitudinal connectivity | Fisheries | GB106039023160 | Contribute to improvement of 1 elelment | Uncertain | 10001-25001 | 1km |  |  | EA | Country Park / LA |  |  | 1 Year | [14 empty] | SU7792772716 | [9 empty] | unfunded |  | No |  | 2013-11-26 | 2013-11-26 | TENTWISTLE
SE2011-00634 | GB106039017330_RFF002 |  | Creation of buffer strips to reduce land run off | No |  | To control or manage diffuse source inputs | Reduce diffuse pollution pathways (i.e. control entry to water environment) | Riparian management | EM | GB106039023190 | Contribute to improvement to 1+ element. | Uncertain | 10001-25001 |  |  |  | EA | EA, WLT, NFU , TW, UCL,KCL, RU, | [27 empty] | unfunded |  | No |  | 2013-11-26 | 2013-11-26 | TENTWISTLE
SE2011-00699 | GB106039023160_RFF001 |  | Creation of buffer strips to reduce land run off | No |  | To control or manage diffuse source inputs | Reduce diffuse pollution pathways (i.e. control entry to water environment) | Riparian management | EM | GB106039023190 | Contribute to improvement to 1+ element. | Uncertain | 10001-25001 |  |  |  | EA | EA, WLT, NFU , TW, UCL,KCL, RU, | [27 empty] | unfunded |  | No |  | 2013-11-26 | 2013-11-26 | TENTWISTLE
SE2011-00699 | GB106039023160_RFF001 |  | Fencing to reduce cattle poaching | No |  | 0 | 0 | 0 | EM | GB106039023190 | Contribute to improvement to 1+ element. | Uncertain | 10001-25001 |  |  |  | EA | EA, WLT, NFU , TW, UCL,KCL, RU, | [27 empty] | unfunded |  | No |  | 2013-11-26 | 2013-11-26 | TENTWISTLE
SE2011-00699 | GB106039023160_RFF001 |  | Fencing to reduce cattle poaching and sediments carrying hosphates efrom entering the river. | No |  | To control or manage diffuse source inputs | Reduce diffuse pollution pathways (i.e. control entry to water environment) | Field & Crop - Livestock | EM | GB106039023190 | Contribute to improvement to 1+ element. | Uncertain | 10001-25001 |  |  |  | EA | EA, WLT, NFU , TW, UCL,KCL, RU, | [27 empty] | unfunded |  | No |  | 2013-11-26 | 2013-11-26 | TENTWISTLE
SE2011-00699 | GB106039023160_RFF001 |  | Run an awareness campaign through on-farm demonstrations and undertake individual advisory farm visits on high risk farms, to reduce the amount of sediment, nutrients and chemicals entering a waterbody from farmland. Educate the farming | No |  | To control or manage diffuse source inputs | Reduce diffuse pollution at source | Field & Crop - Arable soils | EM | GB106039023190 | Contribute to improvement to 1+ element. | Uncertain | 10001-25001 |  |  |  | EA | EA, WLT, NFU , TW, UCL,KCL, RU, | [27 empty] | unfunded |  | No |  | 2013-11-26 | 2013-11-26 | TENTWISTLE
SE2011-00699 | GB106039023160_RFF001 |  | Run an awareness campaign through on-farm demonstrations and undertake individual advisory farm visits on high risk farms, to reduce the amount of sediment, nutrients and chemicals entering a waterbody from farmland. Educate the farming | No |  | To control or manage diffuse source inputs | Reduce diffuse pollution at source | Field & Crop - Arable soils | EM | GB106039023190 | Contribute to improvement to 1+ element. | Uncertain | 10001-25001 |  |  |  | EA | EA, WLT, NFU , TW, UCL,KCL, RU, | [27 empty] | unfunded |  | No |  | 2013-11-26 | 2013-11-26 | TENTWISTLE
SE2011-00699 | GB106039023160_RFF001 |  | Use the Catchment Sensitive Farming initative to raise awareness and reduce pesticide\phosphate\sediment pollution in this waterbody. | No |  | To control or manage diffuse source inputs | Reduce diffuse pollution at source | Field & Crop - Arable soils | EM | GB106039023190 | Contribute to improvement to 1+ element. | Uncertain | 10001-25001 |  |  |  | EA | EA, WLT, NFU , TW, UCL,KCL, RU, | [27 empty] | unfunded |  | No |  | 2013-11-26 | 2013-11-26 | TENTWISTLE
SE2011-00699 |  |  | Use the Catchment Sensitive Farming initative to raise awareness and reduce pesticide\phosphate\sediment pollution in this waterbody. | No |  | To control or manage diffuse source inputs | Reduce diffuse pollution at source | Field & Crop - Arable soils | EM | GB106039023190 | Contribute to improvement to 1+ element. | Uncertain | <10000 |  |  |  | EA | EA, WLT, NFU , TW, UCL,KCL, RU, | [27 empty] | unfunded |  | No |  | 2013-11-26 | 2013-11-26 | TENTWISTLE